## Annual Review

| Title: Tax Reform and Institutional Development: His Majesty’s Revenue and Customs’ (HMRC) Tax Capacity Building Unit (CBU) |  |
| --- | --- |
| Programme Value £ (full life): The Capacity Building Unit was formally established in April 2015. Its funding runs from April 2022 to April 2025 under the settlement reached at the Spending Review covering the period 2022/23 to 2024/25. Budget for 2022-23: £4.9 Million | Review date: 1 April 2022 to 31 March 2023 |

## A. SUMMARY AND OVERVIEW

Background

Since its establishment in April 2015, the Capacity Building Unit (CBU) has emerged as a global leader in delivering bilateral and multilateral peer to peer capacity development to the UK’s partner tax administrations.

CBU primarily uses its own staff to deliver capacity building, but it also draws on short-term expertise from wider HMRC. Key factors in deciding which countries CBU support include UK Official Development Assistance (ODA) requirements, alignment with wider Government priorities, the level of in-country engagement, and potential to progress.

CBU activity is funded directly from the ODA budget and the unit aligns with HM Government’s International Development Strategy, which encompasses the UN Sustainable Development Goals and the Addis Tax Initiative (2015). The CBU’s main governance mechanism is its Steering Group (SG), which has responsibility for decision-making and oversight of the programme, including issues such as resourcing and country selection. Operational-level discussions are held at the programme management committee (PMC). Both the SG and PMC have representatives from the Foreign, Commonwealth and Development Office (FCDO), His Majesty’s Treasury (HMT), and HMRC. The CBU maintains a close relationship with FCDO and its country offices.

During the review period the CBU operated programmes in fourteen countries, at various stages in their lifecycle, from inception to closure. These countries were Ghana, Sierra Leone, Rwanda, Tanzania, Ethiopia, Pakistan, India, Nigeria, Malaysia, Kenya, Uganda, Zimbabwe, Ukraine, and Jordan. The unit also delivered capacity building in countries where it does not have an ongoing wider programme: these included Cambodia, Azerbaijan, Thailand, Mozambique, Ecuador, Montserrat, and Egypt.

The CBU provides support across all aspects of revenue administration, with specific expertise in transfer pricing (TP), tax transparency, compliance, country-by-country reporting (CbCr), data, and human resources (HR). It also delivers the Commonwealth Association of Tax Administrators (CATA) Senior Leadership Programme.

Methodology

This review was conducted by an independent FCDO Governance Adviser. To produce this report the reviewer interviewed CBU programme teams and specialists and reviewed programme documents, including logical frameworks (logframes).

Summary

The review period was the first year when substantial in-person delivery was possible after two consecutive years when CBU had to operate almost entirely remotely, due to the COVID Pandemic. Headline successes include:

- Improvements in tax collection in revenue administrations including Rwanda and Pakistan.

- Agreeing new Memoranda of Understanding (MoUs) with Pakistan and India, new areas of programme work in Malaysia, Tanzania and Sierra Leone and the expansion of the OECD Tax Inspectors Without Borders (TIWB) work in six countries.

- Introducing new systems to different administrations such as the sharing of the OECD Tax Risk Evaluation and Assessment Tool (TREAT) with Pakistan, enabling them to start using their Country by Country (CbC) data; and demonstrating risking and IT systems to Ethiopia.

- Support for legislative change in several administrations, which include CBU-recommended changes being taken forward in Ethiopia on Transfer Pricing (TP); and support to Kenya in introducing domestic enabling legislation to meet the requirements to join the global Common Reporting Standard (CRS).

- Establishing and proving the value of TP support with multiple administrations.

- Supporting governments in Nigeria, Jordan, Ukraine, and Kenya to achieve international standards. CBU assisted Kenya in meeting the requirements to join the CRS, Jordan in data governance techniques to meet the standards for their OECD Global Forum review, and Ukraine to meet the CbCr appropriate use condition for their OECD peer review.

- Supporting gender and equality by realigning the programme in Rwanda to support the UK Government’s commitments on women and girls.

- Supporting improvements in compliance through the development of reform initiatives. Examples include the compliance risk framework for the floriculture sector in Ethiopia, and for Doctors in Jordan, which succeeded in increasing revenue.

- Supporting HR activity and improving organisational development in Rwanda, Tanzania, Uganda, Pakistan, and Malaysia. Success stories include the introduction of a New Operating Model (NOM) in Rwanda, supporting Malaysia through their organisation’s transformation, and introducing behavioural and technical competency frameworks in Uganda (which delivered an increase in employee engagement of 6% in relation to learning and development).

- Supporting multiple countries in data analytics, including Ethiopia, Pakistan, Jordan, India, Nigeria, Ghana, Rwanda, Kenya, Sierra Leone, Uganda, and Zimbabwe. These countries are at various stages of data governance, so tailored support was provided in line with their needs. For example, Sierra Leone was assisted in setting up a Data Analytics Project Team (DAPT) and Kenya was supported to develop a data quality scorecard and reporting tool.

- The CATA Senior Leadership Programme continues to successfully support senior leaders from multiple revenue administrations to develop the leadership skills required to steer their organisations through a dynamic and complex landscape. Feedback from the 2022-23 cohort was extremely positive, with 81% of survey respondents stating that the Programme had exceeded their expectations.

Recommendations for change

- Improving monitoring and evaluation

## The CBU Theory of Change should be refreshed to describe and monitor delivery more holistically. It should have clear lines of sight between country level ambitions and outcomes and the overall objectives of the CBU. It should also align with broader discussions regarding CBU strategy and how this links to wider HMRC/FCDO strategies.

## CBU should recruit a permanent Monitoring Evaluation and Learning (MEL) adviser to guide on success stories and develop a library of resources and theories of change. This will allow a narrative to be built around the CBU’s work and give a qualitative assessment of CBU interventions.

- CBU should also build a knowledge management system, undertake ‘train the trainer’ sessions and improve MEL capacity to ensure sustainability of knowledge and experience in the CBU.

- Improving the long-term advisor model

## Long term advisors (LTA) are CBU representatives embedded in foreign revenue administrations (typically for 2 years) to provide greater traction and influence for capacity building work. For 2022/23, CBU had LTAs in Rwanda and Ghana.

## Recommendations:

## Regularly review the criteria for prioritising which countries have LTAs to maximise their value.

- Clarify the scope of each LTA role. For example, whether they should focus on strategy, innovation, project management, transformation, or a combination of elements.

- Including IT Infrastructure in scoping exercises

- Include a formal assessment of IT infrastructure in scoping exercises to ensure tax authorities’ digital capacities are considered and align with IT-based systems and solutions.

- Improving communication and coordination processes

- Outline standard operating procedures where communication issues arise with administrations. For example, in administrations where information technology is less embedded, emails could be followed by hard copy letters through local FCDO offices to ensure all beneficiaries are aware of upcoming events and requests.

- Developing a standardised process to handover workstreams

  - Develop a more standardised process to handover workstreams to recipient tax authorities as the requirement for HMRC support reduces.

- Increasing provision of non-programme support

- Increase provision of non-programme support. This would provide greater flexibility in deployment of CBU technical assistance in line with demand from non-programme countries.

7) Thematic areas

- Undertake a short analysis of the political economy during scoping exercises to aid selection of thematic areas with a high chance of success.

- Consider the value of promoting tax and climate and gender issues.

- Consider cross-cutting thematic areas, as CBU success stories have shown coordinating work across multiple areas can lead to greater impact and value for money.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

## Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

## The expected impact of the programme is ‘ODA eligible countries are able to finance their own development in a way that is inclusive and sustainable’ with the outcome being ‘increased capacity in tax authorities to administer tax policy and collect revenue, with strong partnerships built and maintained between HMRC and senior counterparts in partner revenue authorities’. There are no intermediate outcomes in the Theory of Change (ToC) that could have linked the programme outputs to this outcome statement. The ToC is structured around five outputs:

## Strengthening core functions of revenue institutions in partner countries.

## Supporting the implementation of effective revenue strategy, policy, and regulatory mechanisms.

## Creating an environment which encourages coordination between key domestic actors.

## Ensuring the CBU effectively delivers on UK commitments related to the global tax and development agenda, particularly on international tax.

## Addressing capacity gaps in the revenue authorities and/or finance ministries of HMG's priority countries, especially among leadership cadres.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

## There has been a material change in the underlying problem statement, strategic direction, and overall design of the programme since the ToC was designed. The programme management team should review the original ToC and its accompanying narrative to assess which areas may need revising and how the programme fits within HMG’s broader development and diplomacy objectives. The revised ToC should clearly outline how workstream outputs lead to the desired outcomes and feed into overall impact. The ToC should be reviewed and updated annually.

## Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

## The Programme should continue. This should be accompanied by ongoing iterative improvements in its MEL practices.

## C. THEMATIC PERFORMANCE REVIEW

Briefly describe the output’s activities and provide supporting narrative

The following paragraphs give an overview of progress in six thematic areas, followed by an overview of non- programme country delivery, titled ‘others’. The purpose is to organise the programme delivery along thematic lines so that logframes can be reviewed in line with these themes and progress can be tracked against SMART and quantifiable milestones.

## A. Transfer Pricing:

## During the review period CBU has supported four different revenue authorities in building their Transfer Pricing (TP) capacity.

## In Ethiopia, CBU technical experts supported the closure of two legacy TP cases and provided updated OECD guidance on TP, as well as demonstrating how to use risking IT systems to enable data utilisation for benchmarking cases.

## In Pakistan, CBU experts supported continuation of a key IT system, reviewed and prepared a delivery plan for case handling, and prepared the administration for risk-based audit selection.

## In Nigeria, a 3-year MoU was signed at the end of the review period which agreed TP as an area where technical assistance will be provided from a subject matter expert.

## There are some non-programme countries where support is being provided. These include Ecuador, Mozambique, and Cambodia.

B. Country by Country (CbC) reporting:

CBU support in utilising CbC data is detailed below:

- In Pakistan, CBU experts shared the OECD Tax Risk Evaluation and Assessment Tool (TREAT) which enabled the Federal Board of Revenue (FBR) to access the CbC data. The next step is to establish an IT-enabled platform that utilises CbC reporting for risk assessment and audit selection.

- In Nigeria, upskilling sessions were held to provide advice on how to transfer CbC data while keeping the data secure. The next stage of support would help the administration utilise data effectively.

- In Ukraine, CBU suggested several approaches on using CbC to help the administration meet a condition of an OECD peer review. The support resulted in the condition being met.

C. Compliance and Audit:

CBU support in compliance, risk, and audit is outlined as below:

- In Ghana, CBU supported the development of a compliance improvement plan and risk-based audit modelling. A cadre of 10 trainers and 80 auditors received training for the delivery of supplementary audit skills, in line with logframe targets. CBU also supported the Ghana Revenue Authority (GRA) to develop a compliance risk dashboard to enable real-time viewing and cross-referrals.

- In Rwanda, significant progress was made on a Voluntary Disclosure scheme. Primary legislation has been published and secondary legislation was presented before the cabinet.

- In Ethiopia, CBU support targeted improving risking through building data matching, data cleansing, and evaluation skills.

- Compliance support was also provided to other administrations, which included High-Net Worth Individual (HNWI) work in India, Thailand, and Jordan.

D. Data:

The data strand achieved a considerable amount of progress over the review period across different countries:

- In Ethiopia, CBU risk & data experts delivered training sessions on foundational analytical skills using theory and practical examples.

- In Sierra Leone, HMRC signed the Terms of Reference (ToR) with the administration to provide peer advice on data analytics. CBU delivered workshops and supported the development of a collaboration tool and a mentoring agreement.

- In Kenya, the data strand achieved considerable progress through a mixture of workshops, case studies and practical exercises.  A framework was developed for key performance indicators to measure data quality and improve capacity in data protection impact assessments and predictive analytics. Data analytics case studies showcased how to use analytics to tackle debt collection and missing trader analysis to identify those who avoid paying VAT.

- Other jurisdictions where technical support on data was delivered during the review period included Rwanda, India, Malaysia, Ghana and Zimbabwe. In Pakistan support was in scoping, and delivery began in Nigeria towards the end of the review period.

E. Transparency:

- Working with Ukraine, CBU has shared UK experience of implementing CRS, and challenges with making exchanges via the Common Transmission System (CTS). This strengthened Ukraine’s commitment to implementing Automatic Exchange of Information (AEOI).

- In Kenya, CBU support contributed to the passing of primary legislation in 2022, as well as detailed secondary regulations implementing the CRS in 2023.  Support has been provided to enable the authority to build a bespoke IT system.

- In Uganda, CBU, in conjunction with the OECD, supported the administration in the development of their AEOI domestic legislation, improving mechanisms for bilateral and multilateral information exchange to meet international standards. Closely aligned with this is the support CBU provided in the development of a Voluntary Disclosure scheme using CRS data and strategy.

- Drawing on support from CBU, the AEOI Unit in Ghana developed a roadmap for the effective implementation of AEOI. CBU experts also supported developing the Voluntary Disclosure programme, which is ready to be implemented.

- In Rwanda, work focused on helping the RRA prepare for and pass its imminent Exchange of Information on Request (EOIR) Peer Review by addressing the Steering Committee and helping with completion of the pre-review questionnaire.

- In Thailand, support on data handling and filing compliance was provided virtually.

- In Ethiopia, the CBU technical expert recommended changes in legislation to enable the administration to join CRS.

F. HR and Organisational Management:

- In Tanzania, HMRC support during the review period was in the inception phase, with the Memorandum of Understanding (MOU) signed in February 2023. The MOU included the provision of support on organisational design, change management, rewards, and employee engagement. Insight sessions on operating models and organisational design were also delivered.

- In Malaysia, CBU delivered insight workshops on change management, performance management, and smarter ways of working.

- In Kenya, the customer service strand designed and delivered a new programme to improve customer engagement and compliance.

- In Uganda, technical and behavioural competency frameworks and assessment processes were implemented across the organisation. The employee engagement score relating to learning and development increased by 6%. A leadership bootcamp was also delivered to senior leaders in partnership with a Leadership Works consultant. Following this delivery, the December 2022 staff leadership & engagement score increased by 11% from the 2020 baseline.

- In Rwanda, the new operating model and organisation structure received ministerial approval and was implemented from January 2023. A survey of activities completed by the HR team between 2017 and 2022 showed a shift from 14% to 58% of its time dedicated to strategic activity. The HR team has also significantly increased its professional capability, with 11 members of staff having achieved or studying to attain CIPD accreditation.

G. Others:

- CATA SLP: Each year HMRC organises and hosts a leadership training programme for senior officials within the Commonwealth Association of Tax Administrators (CATA). The CATA Senior Leadership Programme (SLP) is a unique opportunity for senior leaders in tax administrations to develop the leadership skills required to steer their organisations through a dynamic and complex landscape. The CATA SLP has been running for over 30 years and is an integral part of CBU’s delivery. The programme offers a multi-disciplinary approach to learning in a highly interactive and engaging environment. Led by experts in leadership development, the programme includes input from senior leaders in HMRC and subject-matter experts from the wider tax sector. The programme is further enriched by Commonwealth delegates contributing their diverse experience and expertise. In 2022, a delivery partner was procured for two years to design and deliver the training in collaboration with the CATA SLP team. Feedback from the 2022-23 cohort has been extremely positive, with 81% of survey respondents stating that the programme had exceeded their expectations and all saying it had met their expectations.

- Tax Inspectors Without Borders (TIWB): In collaboration with OECD, CBU is delivering the TIWB work in 8 countries – TP (Azerbaijan, Cambodia, Ecuador, Mozambique, and Thailand), Digital Transformation (Kenya), Trusts (Malaysia) and Criminal Investigations (Pakistan).  HMRC experts provide peer to peer learning through working on cases as well as providing training to build capacity. To ensure sustainability, bespoke products such as case management software, catalogues and training modules are developed to showcase how it works in HMRC. The products stay with administrations and can be utilised by newcomers to ensure sustainability.

- Gender: The gender workstream is making significant progress in Rwanda. From a baseline of no gender work in May 2022, there is now a draft strategy comprising four workstreams: data, research, tax officials, and taxpayers. The administration will publish gender disaggregated data on its taxpayers alongside its tax statistics. The administration is now contributing to cross-governmental research projects on gender, as well as participating in international fora. CBU is considering replicating this work in other countries.

- Climate: HMRC’s International Relations team is exploring opportunities to identify priorities for environmental tax issues through our work with regional organisations, such as the Commonwealth Association of Tax Administrators. The CATA work programme includes a cross-cutting theme on climate. CBU could use relationships with partner revenue authorities to further this work.

- Partnership and regional working:	 Working alongside other donors and delivery partners can help with one of the UK’s core objectives to improve coordination both internationally and within countries. The CBU engages with the OECD’s Forum on Tax Administration’s Capacity Building Network subgroup to coordinate countries delivering capacity building assistance, as well as with the African Tax Administration Forum (ATAF) and West African Tax Administration Forum (WATAF) which provide opportunities for partnership working in participating countries. CBU has been delivering FCDO funded programming on tax reform in Saudi Arabia since 2018, in Oman since 2019, in Qatar and Kuwait since 2020 and in UAE since 2022.

## D: VALUE FOR MONEY

Key cost drivers and performance:

The FCDO’s ‘Best Buys’ analysis concludes that both Tax Policy and Tax Administration support are Great Buys (i.e., Strong evidence of cost-effectiveness across many contexts). The review considers value for money by assessing the programme against the ‘four Es’ (economy, efficiency, effectiveness, and equity). Finally, it gives a summary of the programme’s cost-effectiveness.

Economy: The cost of the programme is driven entirely by staff costs and in-country visits to deliver technical assistance. Although factors such as inflation can cause variation, the programme management team should continue to monitor travel costs and establish benchmarks for expected spend per trip and FTE cost, which can be used to assess commercial performance.

Efficiency: CBU should undertake cost comparison of various resourcing models and choose the option which provides maximum efficiency at the lowest cost. There can be non-monetary benefits of one model over the other, so cost as well as productivity should be compared to determine the most viable option. Similarly, whether having a permanent MEL adviser is good value for money to improve programme efficiency is a question worth probing. Currently there is no data available to measure the efficiency of programme outputs such as annual revenues raised from TP supported audits or the proportion of tax paid through voluntary compliance. Country logframes should have specific indicators for such initiatives so the overall efficiency can be measured.

Effectiveness: While the programme has delivered the majority of log-frame milestones, progress has been slower in some administrations. Where expectations have not been met, this might be because milestones have been too ambitious (for example, expected tax to GDP ratio increases).

Equity:  CBU should identify countries where there is an appetite for gender related reforms that match their expertise and expand the gender work in line with the approach in Rwanda. Gender related milestones should be considered for future reviews accordingly. Moreover, revenue coming out from HNWI initiatives reflects how programme works towards improving equity.

Cost-Effectiveness: Overall, the programme delivers significant value for money and is highly cost-effective, although evidence of value for money would be further strengthened by improved impact evaluation.

E: RISK

Overview of risk management

Overall, the risks on this programme are being managed well. Given the nature of the programme, its limited scope and mode of delivery, there are no risks associated with areas requiring assurance such as: gender equality, counter-terrorism financing, public sector equality duty, climate and environment, disability, safeguarding against sexual exploitation and abuse and sexual harassment (SEAH) or child safeguarding. A risk register for CBU covering delivery across programmes is maintained. However, the register does not capture some of the risks which were identified during the review of this programme which are recommended to be added in the register from now onwards.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues

This review did not consider the commercial performance of the programme. The CBU financial position 22/23 is that it remained generally on budget (£60k underspend out of a budget of £4.9m). This is in part due to delays in posting further Long Term Advisors (LTAs) in country. However, 23/24 is likely to be financially challenging with the costs for LTAs to absorb a significant proportion of the budget (forecasts for year ending 22/23 as examples – Ghana £167k, Rwanda £212k). Programme management and overall delivery have been captured throughout this Annual Review.

G: MONITORING, EVIDENCE AND LEARNING

MEL good practices are being embedded in CBU processes. Programmes are at various stages of the programme lifecycle, with most having a ToC and log-frame (as part of a dashboard) which form key elements of any approach to MEL.  In addition, the CBU conducts annual reviews of all programmes which feed into an overarching review with the aim to publish each year to ensure transparency. Work is also ongoing to share good practice by introducing a library of MEL tools and capturing regular impact stories. Review of logframes and theory of change on a regular basis will help improve MEL practices with monitoring against the updated targets and evaluation of progress at regular intervals.