## Slide 1
PCP UGANDA
Uganda Dairy Credit
Facility (UDCF)
Annual Report 2025
Contract Partner: PCP Uganda Limited
Reporting Period: January – December 2025
Date Submitted: 31 March 2026
41
Retail Partners
(Cumulative)
€2.83M
Cumulative
Disbursement
3,487
SHFs Reached
(Cumulative)
135%
2025 Target
Achieved
EKN-Funded | October 2022 – September 2028

## Slide 2
Presentation Agenda
01
Performance Overview
Financial & portfolio performance highlights
02
SHF Credit Access
Reach, gender inclusion, and loan utilization
03
SACCO Governance
Training, AGMs, and institutional capacity
04
Portfolio Sustainability
PAR, refinancing, and co-investment
05
Impact Achieved
Job creation, financial inclusion, ESG outcomes
06
Risk Management
Key risks and mitigation strategies
07
Lessons & Innovations
Learnings, agro-insurance, contract financing
08
Recommendations
Strategic priorities for 2026 and beyond

## Slide 3
01
Performance Overview
Financial & portfolio performance highlights

## Slide 4
2025 Key Performance Indicators
€1.52M
Disbursed in 2025
135% of target
2,351
SHFs Reached in 2025
203% of target
€2.83M
Cumulative Disbursement
Since inception
35%
Women Borrowers
+11pp vs 2024
41
Retail Partners
39 SACCOs, 1 MFI, 1 SME
2.2%
Portfolio at Risk >30d
Below 3% target

## Slide 5
Credit Disbursement Performance
Chart: 
| 2023 | 2024 | 2025
Target (€) | 622370 | 696375 | 1117375
Actual (€) | 622370 | 696380 | 1515000
€2.83M
Cumulative disbursed
to retail partners
€907K
Capital recovered
(principal + interest)
€2.94M
Credit obtained
by smallholder farmers
€101.7K
Amount revolved
at investee level

## Slide 6
02
SHF Credit Access & Gender Inclusion
Reach, gender inclusion, and loan utilization patterns

## Slide 7
Smallholder Farmer Reach & Inclusion
3,487
Cumulative SHFs
Since inception
2,351
SHFs in 2025
203% of 1,155 target
35%
Women (2025)
Up from 24% in 2024
23%
Youth (2025)
Up from 14% in 2024
Chart: Gender & Youth Inclusion (% of Borrowers)
| Women | Youth
2024 | 24 | 14
2025 | 35 | 23

## Slide 8
Loan Utilization by Enterprise Category (2025)
Chart: 
| Dairy Breed Improvement | Pasture & Feeds | Poultry | Goats | Farm Infrastructure | Piggery | Vet/Health | Water Harvesting
Loan Share | 50.8 | 12.2 | 12 | 7.3 | 7.4 | 6.6 | 2.7 | 0.9
50.8% Dairy Breed
Dairy breed improvement dominates—primary livelihood in Ankole & Kigezi.
25.9% Small Ruminants
Poultry, goats & piggery growing, especially in Busoga region.
12.2% Feed & Pasture
Farmers investing in feed sustainability and soil improvement.
7.4% Infrastructure
Fencing, cattle sheds, kraals and water systems expanding.

## Slide 9
03
SACCO Governance & Performance
Training, compliance, and institutional capacity

## Slide 10
SACCO Training & Governance Compliance
40
SACCOs Trained
Cumulative since inception
(110% of target)
100%
AGMs Conducted
All retail partners compliant
within 4 months of year-end
100%
Board Meetings
All conducting quarterly
board meetings
7
AGMs Attended
Physical DHCL
participation in 2025

## Slide 11
04
Portfolio Sustainability
PAR, refinancing, and co-investment outcomes

## Slide 12
Portfolio Quality & Sustainability
Portfolio at Risk > 30 Days
2.2%
Current PAR
✓ Below 3% target
68% of SACCOs have PAR <10%
37 investees (90%) show portfolio growth
Chart: EKN Capital Draw Downs (€)
| 1st Draw | 2nd Draw | 3rd Draw | 4th Draw | 5th Draw
EKN Draw Down (€) | 622370 | 845750 | 520720 | 638228 | 222751

## Slide 13
05
Impact Achieved
Job creation, financial inclusion, ESG outcomes

## Slide 14
Impact at Smallholder Farmer Level
~24,107 Jobs Created
Estimated based on 1 job/farmer (MTR survey). 81 additional jobs created at SACCO level.
4,830+ SACCO Members Added
New memberships driven by farmer-centered credit products and group lending innovation.
€556K Women's Credit (30%)
Women's share of total credit increased. Group lending enables collateral-free access.
€353K Youth Credit (19%)
Youth access growing. Group guarantee methodology enables youth without land title.
€147K ESG Investments
Pasture (€92K), infrastructure (€23K), water harvesting (€32K) advancing climate resilience.
4 Partners Unlocked External Finance
Busiaga, Kitojo, Kijura & Nakanyonyi SACCOs accessed Stanbic, aBi and MSC credit.

## Slide 15
06
Risk Management
Key risks, assessments, and mitigation strategies

## Slide 16
Risk Register Summary
Risk Category | Level | Mitigation Strategy
Credit Risk | Moderate | Robust credit management, TA & financial literacy
Market/Price Risk | Medium | Agriterra TA; contract financing with off-takers
Collateral Risk (Women/Youth) | Medium | Group lending methodology adopted widely
Natural Disaster / Climate | Medium | Agro-insurance pilot with AIC (24 partners)
Regulatory Risk (Large SACCOs) | Medium | Focus on Cat C/D/E SACCOs
FX Risk | Low | Capital converted to UGX at receipt

## Slide 17
07
Lessons Learned & Innovations
Key learnings and new approaches for 2026

## Slide 18
Lessons Learned & Innovations
Lessons Learned
Innovations in the Fund
BDS Remains Critical
TA and business development services strengthen SACCO management, financial literacy and farmer productivity.
Market Systems Drive Uptake
Input/output market linkages ensure loan repayment and reinvestment in productive activities.
Agro-Insurance is Essential
Bundled agro-insurance protects farmers against natural calamities reducing credit risk.
Capital Must Match Demand
Fund is over-committed. Recapitalization needed to meet growing demand from retail partners.
Agro-Insurance Pilot
24 retail partners selected. AIC collaboration to expand to all partners.
Contract Financing
Tripartite agreements with off-takers underway. Input market partnerships being fast-tracked.
UDCF + HCL Merger
Merger of two credit lines approved to ease administration and reporting.
Agri-Fintech Expansion
Digital delivery channels piloted to reach farmers in areas without SACCOs.

## Slide 19
08
Recommendations & 2026 Priorities
Strategic interventions for greater impact and sustainability

## Slide 20
Priority Recommendations for 2026
1
Recapitalize the Fund
Mobilize additional capital to meet growing credit demand across retail partners and value chains.
2
Scale Agro-Insurance
Extend bundled insurance to all retail partners to protect against climate and production risks.
3
Deepen Gender Inclusion
Intensify group lending and targeted mobilization to close gender gap and reach 40% women target.
4
Expand Credit Delivery Channels
Leverage Agri-Fintech and Agri-SMEs to reach underserved farmers in areas with nascent SACCOs.
5
Strengthen Market Linkages
Prioritize contract financing and input-output market partnerships to maximize loan impact in 2026.

## Slide 21
Thank You
Uganda Dairy Credit Facility — Annual Report 2025
PCP Uganda Limited | Supported by Embassy of the Kingdom of the Netherlands
3,487
SHFs Reached
€2.83M
Disbursed
41
Retail Partners
2026–2028
Road Ahead