Annual Review

| Title: Ocean Country Partnership Programme |  |  |
| --- | --- | --- |
| Programme Value £ (full life): £65m |  | Review date: July 2024-June 2025 |
| Programme Code: | Start date: June 2021 | End date: March 2026 |

Summary of Programme Performance

| Year | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Overall Output Score | N/A | B | B | A |  |  |  |  |
| Risk Rating | N/A | Medium | High | Medium |  |  |  |  |

| DevTracker Link to Business Case: | DevTracker Programme GB-GOV-7-BPFOCPP (fcdo.gov.uk) |
| --- | --- |
| DevTracker Link to results framework: | DevTracker Programme GB-GOV-7-BPFOCPP (fcdo.gov.uk) |

# A: SUMMARY AND OVERVIEW

## A1. Description of programme

The Ocean Country Partnership Programme (OCPP) delivers technical assistance to support countries to manage the marine environment more sustainably and build the resilience of coastal communities, ocean economies, and livelihoods. It does so by strengthening marine science expertise, developing science-based policy and management tools, and creating educational resources. The programme forms part of the UK’s Blue Planet Fund (BPF), a portfolio of programmes supporting developing countries to protect the marine environment and reduce poverty. This is the programme’s last annual review, as the programme is scheduled to close March 2026.

The OCPP has a budget of up to £65m, spread over five years (June 2021-March 2026).

Bilateral partnership support is delivered by three UK government Arm's Length Bodies (ALBs): Centre for Environment, Fisheries and Aquaculture Science (Cefas), Joint Nature Conservation Committee (JNCC), and Marine Management Organisation (MMO). These partnerships seek to reduce poverty by building local and regional marine science capabilities to improve policymaking and address multiple marine environment challenges. Bilateral partnerships are demand-led, with partner country needs identified according to one or more of themes: marine biodiversity, sustainable seafood, or marine pollution. ALBs focus on capacity-building for partner governments, local universities, regional organisations, and civil society organisations to improve the delivery of applied scientific solutions.

The OCPP also funds the Global Ocean Accounts Partnership (GOAP) and Friends of Ocean Action (FOA), which support partner countries in the development of global public goods relevant to the programme’s objectives. GOAP is a membership-driven partnership, convening governments, international organisations, and research institutions to build a global community of practice for ocean natural capital accounting, designed to ensure the diverse values of the ocean are recognised in decision-making. GOAP supports countries to develop ocean accounting systems to inform decision-making on the sustainable and equitable use of marine resources, including overseeing a global expert panel to advance knowledge production and implementing ocean accounting in pilot countries. Ocean accounts can be used to inform future and existing ocean development projects, programmes, and activities including support to the development of sustainable livelihoods for coastal communities. GOAP prioritises sustainability within its delivery model, working to ensure that supported countries can continue ocean accounting practices independently, ultimately eliminating the need for GOAP’s ongoing involvement. GOAP’s Secretariat is hosted by the University of New South Wales (UNSW).

The Friends of Ocean Action (FOA) is a platform hosted by the World Economic Forum (WEF), in collaboration with the World Resources Institute (WRI). From April 2021 to March 2024, FOA delivered on two priority areas for the BPF and the OCPP: (1) improving the sustainability of blue food production, and (2) supporting developing countries to build sustainable ocean economies. No new FOA projects were delivered for Year 4 under the OCPP and therefore FOA is absent from this annual review’s reporting of results. FOA has entered into a grant agreement with Defra for Year 5 to deliver a continuation of the Blue Food Partnerships project in Ghana.

To date, 20 ODA-eligible countries have received support from OCPP, bilaterally or through the strategic partnerships. There have been other interventions at a regional and global level, via task forces, governance structures, coalitions, and networks, including Emergency Response work (with the bilateral programme) and GOAP’s ocean accounting communities of practice and steering committees.

## A2. Summary supporting narrative for the overall score in this review

OCPP has been awarded an A for the 2024/25 annual review period (1 July 2024 to 30 June 2025). This is a significant improvement of previous performance, having scored two consecutive Bs in previous reviews. The programme has successfully completed its Programme Improvement Plan (PIP) which represents a great deal of hard work to improve. However, the programme continues to face challenges in demonstrating progress towards outcome-level change. This result was assessed through output and outcome scoring from the reporting period and supported by a review of programme documents, including previous annual reviews, country progress reports (dated April 2025), and GOAP quarterly reports, as well as findings from interviews with the Defra team, ALB and GOAP Programme Directors, FOA, Country Coordinators, and BPF Regional Coordinators.

- Two outputs scored A+, three outputs scored A, and one FOA-specific output was not reported on as delivery through FOA was not funded during Year 4. During this reporting period, the programme faced uncertainties and contextual challenges. The Independent Commission on Aid Impact (ICAI) report into the BPF led to an internal review of programme design and delivery resulting in revised workplans for Years 4 and 5. The programme has scored strongly across output reporting, demonstrating flexibility and adaptability to budget adjustments and technical delivery changes in line with the PIP and last year’s annual review recommendations.

In addition to indicator reporting, in May – July 2025 OCPP’s independent MEL supplier NIRAS conducted three case studies (one in Sri Lanka and two in Ghana) to explore the impact of OCPP on livelihood and well-being outcomes. 271 stakeholders were engaged including beneficiaries, half of those being women. Beneficiaries reported a range of outcomes including better market access, increase in youth employment and increased food security. The case studies found that better integration and tailoring of poverty outcomes for specific groups at the start of intervention would have increased poverty reduction outcomes.

Overall, the A score reflects the programme’s growing maturity within its countries of delivery. Strengthened relationships with in-country stakeholders have enabled delivery teams to advance policy recommendations and support policy adoption, contributing to the programme’s potential for greater impact. Results achievement has been positively impacted by increased capacity and capability within the programme partners in line with previous interim evaluation recommendations (2024). The measurement of progress is more accurate due to upskilling of delivery teams in Monitoring, Evaluation and Learning (MEL). This has enhanced their ability to report against the logframe and to recognise and evidence – to a certain extent – intermediate and outcome-level changes.

- Though positive results are occurring at the output level, the programme is still underachieving against two of the four outcome indicators and it is unclear if OCPP can meet its final year targets against these outcomes by March 2026. At this point in the programme’s lifecycle, it is expected that more outcome level results would be reported.

## A3. Major lessons and recommendations for the year ahead

The section below outlines key lessons learned from the Year 4 annual review, along with associated recommendations. These insights are intended to inform the final stages of the programme.

- Lesson: Sustainability and transition are intrinsically linked: while some ALB-led activities are expected to conclude at the end of the programme, ensuring the continued impact of OCPP’s interventions requires defining clear exit strategies to sustain key outcomes beyond closure.

Recommendation(s):

  - Priority for ALB-led delivery in Year 5 should be given to the most viable intermediate outcome results, that is those with strong potential for uptake and use by in-country stakeholders. OCPP’s outcome indicators are linked to sustainability which stipulate to reach outcome level change, resourcing must be made available by in-country partners. Clear transition guidelines and a handover of the associated outputs and higher level results must be communicated to in-country stakeholders so that these stakeholders have all the tools needed to allow them to use OCPP’s outputs in the sustainable management of the marine environment.

Lead(s): ALB delivery partner teams (including Programme Directors, Country Coordinators and Project Managers)

Deadline: March 2026.

  - During the last year of delivery, sustainability needs to be assured as much as possible within each bilateral partnership transition strategy and multilateral project, with identification and/or consideration of sustainable financing options or other alternatives for each workstreams/outputs. While sustainable financing might not be feasible for each workstream or within each partnership, a clear rationale should be provided.

Lead(s): Delivery partner teams (including Programme Directors, Country Coordinators and Project Managers)

Deadline: December 2025.

- Lesson: For a programme to be able to demonstrate Value for Money (VfM), a robust and systematic VfM framework is required and needs to be mandated by Defra from the outset. In Year 4, the delivery partners reported on VfM in a standardised way against a framework for the first time. Though financial reporting was required in previous years, delivery partners faced challenges in agreeing what was required to report on during the co-development of the framework. This required Defra to confirm what VfM metrics were required for the remainder of the programme.

Recommendation(s):

  - Looking ahead to the final phase of the programme, it will be important to focus on strengthening the evidence base to inform the closing review. Over the remaining duration of the programme, partners and Defra should therefore prioritise gathering and consolidating evidence on both effectiveness and cost-effectiveness. This will also enable comparison with the economic estimates set out in the programme Business Case.

Lead(s): Defra and delivery partner Programme Directors.

Deadline: December 2025.

- Lesson: Positioning the programme to influence and contribute to policy change is essential to achieve longer term environmental and poverty alleviation outcomes. Focusing the strategy on narrow objectives at the activity level without linking to an overall policy influencing strategy is not effective. For example, Belize’s bilateral partnership and activities are clearly aligned to supporting the in-country government stakeholders to achieve their requirements under the Blue Bond Agreement. This has enabled better traction, buy-in and uptake of OCPP’s activities with government partners.

Recommendation(s):

  - As part of close out activities, the NIRAS MEL team should engage and support delivery teams to draw lessons on how to align with policies and influence stakeholders to sustainably effect policy change, and share these lessons with wider fora, such as the BPF MEL Working Group and other learning spaces.

Lead(s): NIRAS MEL partner and delivery partners.

Deadline: March 2026.

- Lesson: Technical assistance programmes may present unique challenges in monitoring and reporting on higher level changes, especially if the assistance is delivered through an intermittent presence model where evidencing the implementation of a programme’s outputs relies on either being in-country or through in-country stakeholder reporting. While the programme’s capacity and capability in MEL has grown since Year 3, gaps in evidencing higher level changes remain for the programme.

Recommendation(s):

  - Delivery teams should make a concerted effort to evidence the implementation and resourcing of policy recommendations, guidelines, or improved practices (Outcome 2) and/or enforcement and monitoring activities (Outcome 3).

Leads: Delivery partners

Deadline: February 2026.

  - The wording of Outcome 3: “Number of countries where enforcement or monitoring activities are implemented and resourced” is currently limiting the programme’s ability to capture multiple instances of change within a single country. The wording of the outcome should be changed to allow for a broader spectrum of compliance and enforcement work and reflect “Number of instances…”. This will enable the programme to capture multiple instances of outcome level change within a country. This outcome’s target should be revised with delivery partners.

Leads: NIRAS MEL partner and MEL working group

Deadline: October 2025, before the final round of Year 5 reporting

- Lesson: In-country presence continues to remain an important driver of effectiveness for bilateral and multilateral partnership delivery. For the bilateral partnerships, ways to achieve this can be flexible, as demonstrated by the effective use of FCDO Posts, who are closer to day-to-day delivery. For example, in Vanuatu the use of a FCDO Climate Ocean Lead has been effective for coordination. For GOAP, in-country research fellows have been integral to advancing ocean accounting practices within host countries.

Recommendation(s):

  - Programme delivery should continue utilising in-country resources and support, particularly during transition, such as through the BPF Regional Coordinators and/or FCDO Posts who have resource to support on the programme.

Lead(s): Delivery partners and Defra.

Deadline: March 2026.

  - As part of close out activities, the NIRAS MEL team should engage and support delivery teams to draw lessons on how to mobilise key in-country stakeholders to advance programme objectives and sharing these lessons with wider fora, such as the BPF MEL Working Group and other learning spaces.

Lead(s): NIRAS MEL partner and delivery partners.

Deadline: March 2026.

# B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

## B1. Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Theory of Change Summary

The OCPP Theory of Change (ToC) sets out the challenge affecting vulnerable coastal communities and their supporting ecosystems and the use of science to address this challenge:

The ocean is negatively impacted by a breadth of human activities, endangering fragile environments and the livelihoods and wellbeing of vulnerable communities that rely on them;

Partner country stakeholders require increased capacity to generate and use scientific knowledge to inform robust policymaking and implement actions to address ocean pollution, biodiversity loss, access to sustainable seafood and the impacts of climate change.

The following constraints were identified:

- Limited funding for research, resulting in knowledge and evidence gaps to support new policies;

- Low capacity levels for science, technology, and governance, including lack of physical resources and limited access to training;

- Limited knowledge exchange of importance of healthy ocean ecosystems and local context;

- Limited capabilities for effective evidence interpretation and policy response / implementation;

- Competing priorities, particularly in lower income developing countries, that would deprioritise marine conservation, sustainable fisheries, and climate challenges for economic development in the near term, but leaving vulnerable communities worse off in the long term;

- Lack of clear and consistent economic arguments for the importance of conservation.

There are four pathways to change (causal pathways) for the OCPP:

- Capacity building;

- Governance and regulation;

- Science, education and knowledge exchange;

- Value chain and market access improvements for seafood.

The causal pathways demonstrate how the OCPP’s activities and inputs tackle these constraints and increase marine science and management capacity and capabilities within partnership countries and regional/ global partnerships, aiding the effective and sustainable management of marine environments which in turn will improve the livelihoods of coastal communities. For example, technical assistance via the OCPP enacts a positive change and increase a country’s capacity (i.e. resources) and capability (i.e. ability) to respond to marine pollution.

Change along pathways is not linear. The pathways also interact, collectively supporting each other and resulting in synergies. For instance, technical assistance for marine pollution involves both training in-country scientists and providing access to better datasets to support in-country work, while simultaneously working with country governments and ministries to strengthen policies around marine pollution. GESI and safeguarding cross-cut the four causal pathways and are factored into the OCPP’s design.

Evidence for the efficacy of these causal pathways is outlined within the programme ToC narrative and is linked with interdependent inputs (i.e. the activities or resources provided by the programme) that result in the OCPP’s outputs. The inputs for the OCPP include:

Research and evidence;

Technical expertise;

Assets and equipment;

UK leadership;

Partner country government leadership;

Global and regional delivery;

Consultations, knowledge processes and participation from local communities.

At the intermediate outcome level, the OCPP will result in: ‘Improved policies and regulation with enhanced capabilities and inclusive governance in place to implement and enforce these’. To reach this intermediate outcome level, the programme must achieve the following:

Improved capability to implement improved policies, regulations, and approaches for sustainable marine environment management and emergency response;

Implementation of improved policies, regulation frameworks, and approaches for sustainable marine environmental management & emergency response;

Community ownership and / or support from public-private partnerships for policies, regulations and practices that support effective management of the marine environment.

The programme’s stated outcome is: ‘Partner country stakeholders take enhanced collaborative action to effectively and sustainably manage and protect their marine environments’. To achieve this Outcome, the intervention must first result in the effective implementation of the following by partner countries:

Improved policies and practices that protect and conserve marine environment effectively, with strengthened preparedness to respond to emergencies;

Effective enforcement of enhanced and inclusive regulations that protect and conserve marine environment;

Enhanced and inclusive community ownership, resourcing, and public-private partnerships and action [including scale-up of successful innovations] to effectively manage their marine environment.

Year 4 Update

In Year 4, the delivery partners (ALBs and GOAP) began preparing narratives on how their interventions would contribute to Poverty Alleviation (PA). It is expected that these PA narratives will be reviewed and incorporated into the programme’s ToC narrative in Year 5, by December 2025.

The logframe underwent a biannual review with delivery partner ALB and GOAP Programme Directors in November 2024, to update milestones and targets and make adjustments to certain indicators to better reflect the programme. During this review, the indicator ‘Number of projects / planning and/or governance processes with increased inclusion of local people and their knowledge in decision making’ (intermediate outcome indicator 3), was removed. The indicator was not considered reflective of the level of technical assistance is delivered by OCPP in practice.

The delivery teams underwent upskilling and training in GESI and safeguarding throughout Year 4 and it was decided by the Programme Directors to focus reporting efforts on Output 6 (GESI) and Outcome 4 (Inclusion). In addition, some output indicators incorporated a disaggregation of ‘disability’. Further narrative on the logframe changes as a result of the biannual review is covered in C2.

## B2. Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme demonstrates a mixed picture in its reporting of higher level results in the year before closure: while there is some success for Outcome 1 and limited progress in Outcome 4, Outcomes 2 and 3 reported below target and progress. More is reported for intermediate outcomes, the indicators intended to capture the steps towards outcome level change, demonstrating positive progression albeit late in the programme’s lifecycle. No data is available for the three impact level indicators. For impact indicator 1 (hectares under sustainable management), ALBs and GOAP are expected to report for Year 5 within the programme completion review. Impact indicator 2 (livelihoods and wellbeing) and impact indicator 3 (ICF KPI 15 transformational change) will be examined via follow-up analysis and evaluation work.

Results from the intermediate outcome and outcome reporting are presented below.

Intermediate outcome reporting

| ​ |  | Indicator​ |  | Programme Target (2026)​ |  | Progress​ 24/25 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Intermediate outcome “Improved policies and regulations and practices established with enhanced awareness, capabilities and inclusive governance in place to implement and enforce them”​ |  | Intermediate Outcome 1: Number of cases where there is evidence of uptake of policy recommendations or demonstration of practical improvements and / or uptake of sustainable practices by country stakeholders​ |  | No target​. These indicators are intended to show progress towards outcome level and are not a metric for the programme to ‘aim’ for numerically |  | Reported: 18 Note: this is a non-cumulative indicator |  |
|  |  | Intermediate Outcome 2: Extent to which partner countries have demonstrated change in 5 key dimensions of the policy process​ |  | No target​. These indicators are intended to show progress towards outcome level and are not a metric for the programme to ‘aim’ for numerically. |  | Reported: 9 Note: this is a non-cumulative indicator |  |

The intermediate outcome (IO) reporting identifies 27 areas of change that could progress to outcome level in the next 6 months, representing a large pipeline of work for the OCPP to drive forward to outcome level change before closing. For example, most results for ALBs (13) and GOAP (5) for intermediate outcome 1 are for ‘best practice standards’ and ‘guidelines’, where stakeholders (mostly government departments or ministries) were involved in helping to draft improved marine environments standards or practices and then agreed to embed them into practice. For intermediate outcome 2, most results (6 for ALBs and 3 for GOAP) for policy change are for ‘adoption’, stakeholders agreeing to move forward with a policy change and ‘formulation’, stakeholders co-drafting the policy change with OCPP.

Outcome reporting

| ​ | Indicator​ | Programme Target (2026)​ | Progress​ 24/25 |
| --- | --- | --- | --- |
| Outcome​ “Partner country stakeholders take action to effectively and sustainably manage and protect their marine environments” | Outcome 1: Number of partner countries where there is evidence of strengthened preparedness to respond to emergencies​ [Only reported by ALBs] | 10 (ALBs)​ | Cumulative achieved: 6 24/25 achieved: 6 |
|  | Outcome 2: Number of improved policies, regulations and guidelines or recommended practices implemented​ | 10 (ALBs)​ | Cumulative achieved: 10 24/25 achieved: 8 ALBs: 3 GOAP: 5 |
|  | Outcome 3: Number countries where enforcement or monitoring activities are implemented and resourced​ | 11 (ALBs)​ | Cumulative achieved: 4 24/25 achieved: 3 ALBs: 2 GOAP: 1 |
|  | Outcome 4: Increased effective and equitable representation and participation of coastal resources stakeholders in management ​ | GESI Sensitive | Cumulative achieved: Partially Gender Sensitive (ALBs and GOAP) 24/25 achieved: Partially Gender Sensitive (ALBs and GOAP) |

Outcome 1: Emergency Preparedness and Response

Significant progress has been made in six (6) countries that have undergone a baseline assessment, with changes noted across more than one of the five self-assessment dimensions. Maldives and Sri Lanka have seen reported change in additional dimensions since last year. Madagascar, Senegal, Solomon Islands, and Vanuatu have reported change across two or more dimensions.

The current target for this indicator is ten (10) countries. During delivery in Y4, it was agreed by the programme that the maximum number of emergency response countries to engage would be those with established baseline assessments. The programme should consider revising this target down to seven (7) to reflect the planned progress within Mozambique and also pivoting delivery away from Ghana due to its already robust emergency response capacity. Ghana’s baselines were high compared to the other countries, given the strong private and public sector investment in oil and gas in the country. Delivery in Mozambique was curtailed due to civil unrest in the country.

If revised to seven (7), there is a high likelihood of the programme achieving its targets for O1 by the end of the programme in countries with active emergency response work, based on the strong results in reporting from previous years’ delivery and in this year’s reporting.

Outcome 2: Improved policies, regulation and guidelines or recommended practices implemented

For this year, the programme has produced eight (8) results for "Number of improved policies, regulations and guidelines or recommended practices implemented," bringing the cumulative total for the programme up to ten (10) across Year 3 and Year 4. Of the eight (8) results, three (3) results were reported for the bilateral (ALB) programme in Year 4. The target for ALBs is to achieve ten (10) results by Year 5. GOAP reported five (5) results related to the integration and implementation of ocean accounting into government. See Annex 1 for details.

The bilateral programme is below target. More results should be expected at this stage of delivery, particularly for the longest-standing partner countries (Sri Lanka, Maldives and Belize). There are several reasons for being below target: 1) Bilateral delivery teams indicated that there are more results that have not been captured in this round of reporting due to lack of evidence available from in-country partners; 2) some programme teams struggled to track and articulate what has happened with previously reported outputs from previous years; and 3) the programme’s outputs have not matured potentially due to prohibiting country contexts beyond the control of the programme (e.g. lack of traction due to civil unrest, change of government, etc.). While the latter reason is beyond the control of the programme, a significant effort is needed from the delivery teams to evidence and capture results occurring within their partnerships in the last year of the programme.

GOAP made a significant improvement in their reporting of higher-level changes and evidencing the results. A final target needs to be set for Year 5.

There is a medium likelihood of the programme achieving its final target for O2, if the following conditions are met: improved evidence gathering and reporting from the programme team and if delivery continues as planned for Year 5.

Outcome 3: Number countries where enforcement or monitoring activities are implemented and resourced

Through GOAP, Indonesia conducted its first ever Earth observation-based comprehensive mapping of seagrass ecosystems and carbon stocks at a national scale. Via the ALBs, the National Centre for Coastal Research in India have built on OCPP training to use a microplastic pump to conduct routine monitoring without OCPP assistance. In the Maldives partners are conducting surveillance and monitoring of South Ari Atoll Marine Protected Area to monitor and manage interactions between tourists, operators and whale sharks and ensure rules and regulations are adhered to.

The bilateral programme, run by the ALBs, is below target, suggesting potentially stalled progress within the countries receiving compliance and enforcement support. Delivery of compliance and enforcement work has ceased in countries where there was little traction, such as Vanuatu, Solomon Islands and Senegal. Resources were focused in countries where demand was greater (Sri Lanka, Ghana and Madagascar). This may explain the underperformance to a certain extent, but also indicates that results should be expected from the higher-demand countries. Additionally, Belize was unable to provide evidence to support reporting into this outcome in Y4.

There is a level of ambition in the definition of this indicator, since to achieve it stakeholders must be delivering and monitoring with their own allocated resources and without OCPP support. The bilateral programme should take stock as to where the partnerships are in relation to progress against this indicator and seek to understand where and why results are potentially stalling at either output level or intermediate outcome level change. In Year 5, delivery teams should make a concerted effort to evidence the implementation and resourcing of enforcement and monitoring activities.

Currently, there is a low likelihood of the programme achieving its target by the close of the programme. The wording of this indicator should be adjusted to reflect ‘number of instances’, to remove the limitation of only counting ‘number of countries’ where a result occurs. This will better reflect the change in programme delivery with the increased focus on the higher-demand countries. As with outcome 2, GOAP is anticipated to set a target for this indicator in Year 5 as well.

Outcome 4: effective and equitable representation and participation of stakeholders in management

As articulated in the OCPP’s ToC narrative, marginalised groups such as women, girls and indigenous people have specific coastal marine resource knowledge, capabilities, needs, and priorities that are linked to marine resource use. Evidence demonstrates the importance to promote, mainstream and sustain integrated, gender transformative, and participatory approaches to coastal-marine science and management and development.

Due to the late implementation of GESI into the programme, it is unclear whether outcome-level change will be achieved in the lifetime of the programme. However, good progress has been made by delivery partners on GESI mainstreaming in OCPP. ALBs participated in capacity building activities, such as training and workshop events, to introduce GESI concepts and create awareness on the relevance of GESI in OCPP. The development of a live GESI tracker enables systematic reporting on how GESI is integrated within workstreams and the country teams have undertaken a self-assessment on the level of GESI integration according to the Defra-set criteria of ‘unaware, sensitive, empowering, and transformative’ by workstream within each country. Together, the self-assessment and tracker allow country teams to reflect on how to continually strengthen GESI in their work and assess their own progress. For GOAP, their social accounts are intended to ensure visibility of GESI issues within the macro-frameworks. ​

The MEL partner conducted an independent quality assurance review of the ALB delivery team’s GESI self-assessment and GOAP’s social accounts to provide a scoring for this outcome indicator based on the methodology set out in the OCPP’s MEL framework, which is adapted from the methodology for BPF KPI 3. From the evidence provided, the MEL partner have graded the programme as ‘partially sensitive’, which is not an official Defra GESI category and reflects the MEL partner’s recognition of GOAP's progress developing social accounts for Belize, Maldives, and Costa Rica recognition and ALBs progress in some countries and workstreams are nearly there on meeting the ‘sensitive’ category. Across 9 countries and 53 workstreams, the ALB GESI self-assessments show that delivery partners have made progress in addressing gender and social inclusion into programme activities. Many teams have submitted their respective GESI analysis, applied GESI agendas, engaged specialist expertise, and tailored training materials and stakeholder engagement to ensure an inclusive and participatory activity. Encouragingly, there is increasing collection of sex-disaggregated data, and in some cases intersectional analysis, to inform delivery. Promising examples include youth-led awareness campaigns, inclusive MPA management and aquaculture initiatives that consider the different roles, needs, and access barriers for women and marginalised groups. Of the 53 workstreams assessed, 18 were assessed as sensitive (33%), 14 as partially sensitive (26%); the remaining 14 were graded as ‘unaware’.

While delivery partners are increasingly becoming aware of the importance of GESI, there is a need for more systematic utilisation of information from the GESI analysis to improve GESI mainstreaming in implementation and monitoring. This entails a good understanding of GESI concepts as well as Defra’s GESI strategy, providing evidence which documents adaptations in workstream design and implementation as a result of intentional integration of GESI considerations. The formulation of a country gender analysis marks a key step towards reaching gender sensitive status. This provides the country teams the opportunity to use information obtained from the GESI analysis to enhance GESI mainstreaming in implementation activities. The ‘partially sensitive’ grading and results can be used as a tool to inform the delivery teams on where to focus their efforts in bringing workstreams up to GESI ‘sensitive’ before closure.

Looking ahead, the bilateral programme plans to incorporate the specific country and thematic GESI-analyses into the transition plans with their in-country stakeholders. Another self-assessment will be conducted by ALB delivery teams in December 2025, providing a further opportunity to capture progress. GOAP plans to continue developing social accounts for their frameworks within partner countries. This will require technical support especially from partner countries where team capacity in GESI is weak. These forward plans indicate that delivery teams are aware implementation time is rather limited and GESI mainstreaming is a process - a process that can be taken beyond the life of the programme.

Overall assessment

For Outcome 1, based on progress against outputs and the demonstration of the programme of converting outputs to outcome-level change, there is a high likelihood that the target will be achieved for this outcome indicator by the end of the programme in operational countries if the target is revised to seven. For Outcome 2, the reported results at the outcome level remain below target. Given the limited progress this year, there is a low likelihood of the programme achieving its target as it is currently set for Outcome 3, unless the target is adjusted to reflect the changes in programming experienced during this year’s delivery. For Outcome 4, positive improvement has been made towards GESI sensitive status, however, the late introduction of GESI and application of commissioned GESI analyses on the OCPP means that the programme’s ability to achieve GESI outcome-level change is limited.

While the programme reported a number of IO level results, the short amount of time left for the programme means the progression of intermediate results to outcome level before closure (e.g. implementation) is not guaranteed. There is a risk that the results could ‘bottleneck’ at the IO level at programme closure. This risk could be mitigated to some extent, through focused programming, identifying IOs with the greatest potential to progress quickly and ensuring activities are undertaken to drive these forwards or are handed over to in-country stakeholders as the programme begins its transition to closure. Additionally, it is important that robust evidence capture and reporting continues until the end of the programme to document any progression occurring within the programme period.  If handed over with efficacy by the delivery team to in-country stakeholders, some IO-level results could mature to outcome level change after the programme closes in March 2026.

Despite this risk, in Year 4, change is occurring as a result of the programme in notable areas, including emergency response, and the adoption of improved policies, best practice standards, and guidelines.

## B3. Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

OCPP has demonstrated improved performance and strategic relevance in Year 4. After two years of underperformance and B scored ARs, the programme was placed on a PIP. Delivery partners performed well against actions within the plan, which contributed to improved performance across the programme. Nonetheless, the programme continues to struggle to demonstrate progress towards outcome-level change. Despite this, there is a rationale to continue delivery to enable better realisation of Outcomes in the final year.  There is a strong rationale to continue delivery through GOAP beyond the closure of OCPP due to their consistent high performance throughout the programme. For example, additional benefits have been felt with organisations such as the World Bank utilising GOAP ocean accounting data to inform decision making. The programme has delivered robust output-level results and made meaningful progress towards outcome-level achievements. The programme performed particularly well in producing policy and regulatory recommendations; enhancing the capacity and capability of partner country stakeholders in marine science, management, and governance; and supporting active ocean-science knowledge networks and partnerships. It also strengthened its approaches to GESI, reinforcing safeguarding, and is beginning to evidence its potential contribution to poverty alleviation in delivery countries.

The overall risk rating for Year 4 is Medium. This rating reflects notable improvements in risk management processes, the restructuring of delivery arrangements, and strong progress in addressing key structural issues highlighted in previous reviews, particularly those related to poverty alleviation and safeguarding. Current risks are primarily linked to programme resourcing, transition planning, and GESI integration; however, all identified risks have appropriate mitigation measures in place, with clear ownership and regular monitoring at both programme and partner levels.

Looking ahead, Year 5 will be critical both for finalising activities and maximising outcome-level results, and for consolidating gains through transition planning. Key strategies will include strengthening the engagement with other BPF programmes, development partners, and governments, as well as mobilising sustainable finance to support uptake and continuation of results.

# C. DETAILED OUTPUT SCORING

## Output 1

| Output Title | Partner country stakeholders have strengthened capacity and capability in marine science, management and governance |  |  |  |
| --- | --- | --- | --- | --- |
| Output number: |  | 1 | Output Score: | A+ |
| Impact weighting (%): |  | 16.66 | Weighting revised since last annual review? | N/A |

| Indicator(s) | Description | Milestone(s) for this review | Progress |
| --- | --- | --- | --- |
| 1.1 | Participants report increased knowledge and capacity following training and/or mentoring | Milestone: Total: 80% ALB: 80% GOAP: 80% FOA: N/A 24/25 milestone: Total: 80% ALBs: 80% GOAP: 80% FOA: N/A | Milestone achieved: Total: 87%, A ALB: 88% GOAP: 87% FOA: N/A 24/25 achieved: Total: 86% ALBs: 86% GOAP: 86% FOA: N/A |
| 1.2 | Target organisations / institutions in partner countries have increased access to functioning marine scientific equipment and staff trained in its use | Cumulative milestone: Total: 10 ALB cumulative: 10 GOAP cumulative: N/A FOA cumulative: N/A 24/25 milestone: Total: 8 ALBs: 8 GOAP: N/A FOA: N/A | Cumulative achieved: Total: 17, A++ ALB cumulative: 17 GOAP cumulative: N/A FOA cumulative: N/A 24/25 achieved: Total: 15 ALBs: 15 GOAP: N/A FOA: N/A |
| 1.3 | Number of individuals receiving TA support (ICF TA KPI 2) | Cumulative milestone: Total: 1,938 ALB: 1,600 GOAP: 320 FOA: 18 24/25 milestone: Total: 654 ALBs: 578 GOAP: 76 FOA: N/A | Cumulative achieved: Total: 4,187, A++ ALB: 2,748 GOAP: 1,461 FOA: 18 24/25 achieved: Total: 3,081 ALBs: 1,876 GOAP: 1,222 FOA: N/A |
| 1.4 | Number of organisations receiving TA support (ICF TA KPI 2) | Cumulative milestone: Total: 402 ALB: 366 GOAP: 50 FOA: 52 24/25 milestone: Total: 74 ALBs: 70 GOAP: 4 FOA: N/A | Cumulative achieved: Total: 1,057, A++ ALB: 680 GOAP: 420 FOA: 52 24/25 achieved: Total: 860 ALBs: 511 GOAP: 395 FOA: N/A |

C1. Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 monitors the programmes’ progress in strengthening the capacity of country stakeholders in marine science, management and governance.

ALBs revised their workplans for Years 4 and 5, terminated a number of planned activities and focussed on strengthening the delivery of ongoing technical assistance (TA) and capacity building activities, thereby impacting positively Indicators 1.3 (Number of individuals receiving TA) and 1.4 (Number of organisations receiving TA). For GOAP, there was an increase in budget in Year 4, enabling a further expansion of these activities.

  - – A. This indicator measures the increase in understanding, skills, and proficiency among individuals participating in training, mentoring, and knowledge exchange activities delivered by OCPP. The findings are indicative of strengthened knowledge and capacity among participants, but should be interpreted with caution. Measurement relied on post-training surveys, which were not applied to all activities: only 11% of 1,876 participants in ALB trainings and 7% of 1,222 participants in GOAP trainings completed a post-training survey.

  - – A++. In Year 4, ALBs exceeded their target of providing functioning marine scientific equipment and trained staff in their use. Equipment delivered in the Maldives, Solomon Islands, Sri Lanka, and Vanuatu included deep-sea camera equipment, laboratory equipment, post-spill monitoring boxes, and personal protective equipment. The provision of equipment is a longer-term process, often involving customs clearance, training, and follow-up support to ensure it becomes fully operational. It is likely therefore expected that more progress was recorded in Year 4 as these steps were completed and earlier deliveries became embedded in-country.

  - – A++. Since the beginning of the programme, delivery partners have delivered technical assistance (TA) support to 4,187 individuals. In Year 4, ALBs and GOAP delivered TA support to 3,081 individuals: ALBs reached 1,876 individuals (29.7% female; 51,7% male; 18.5% unreported) and GOAP reached 1,222 individuals (41.5% female; 35.1% male; 23.3% unreported). Of the ALB participants, 347 came from rural geographies and 447 from urban geographic areas, with the remaining individuals unreported. Only four individuals were reported as ‘disabled’ by ALBs, with many (1,100 individuals) reported as ‘not disabled’. Of the total individuals trained this year, 1,359 (44%) were not reported with their Age category. Some 1,068 were reported as ‘Adults aged 25-64’ (35%), with 196 (6%) reported as ‘Youth ages 15-24’ and 446 (15%) individuals reported as ‘Elder age 65+’. ALBs reached nearly twice as many individuals and GOAP reached nearly four times as many individuals compared to Year 3. These results are partly explained by the delivery pivot outlined above. They also reflect the stronger traction delivery partners achieved in Year 4, supported by a more established presence and better-developed relationships in-country, which led to positive responses to proposed activities.

Note: Some individuals benefitted from support provided by both ALBs and GOAP, the total number of beneficiaries is lower than the aggregate of the individual component figures.

  - – A++. TA has been delivered to 1,057 organisations since the beginning of the programme, with. most organisations were reached in Year 4. Organisations reached include government ministries, departments and directorates, central banks, universities, research institutes, NGOs and civil society organisations. This result also reflects the pivot in delivery outlined above, as well as  being able to reach organisations via several regional and global events held this year.

Detailed output example for indicators 1.3 and 1.4

- Marine Pollution Emergency Response: Emergency Response work was initially designed to be delivered on a country-by-country basis. However, OCPP shifted to a regional approach to expand reach and strengthen cross-country collaboration. In Year 4, the Maldives and Sri Lanka were engaged jointly, recognising the need for mutual support along their shared maritime border. Coastguards and experts from both countries participated in Geographical Information Systems (GIS) and in Emergency Response capacity-building trainings to enhance resilience and preparedness for pollution incidents.

- GOAP Global Events: GOAP delivered several events, including a webinar on “Ocean Accounts as a Foundation for Climate Action: From Commitments to Implementation” in May 2025 (173 participants), and training on “Introduction to Ocean accounting, Principles and Tools” in July 2024 (128 participants).

## Output 2

| Output Title | Policy and regulatory recommendations proposed, and guidelines developed |  |  |
| --- | --- | --- | --- |
| Output number: | 2 | Output Score: | A+ |
| Impact weighting (%): | 16.66 | Weighting revised since last annual review? | N/A |

| Indicator(s) | Description | Milestone(s) for this review | Progress |
| --- | --- | --- | --- |
| 2.1 | Number of outputs (policy briefs, roadmaps, recommendations or guidelines) developed that contribute to sustainable management | Cumulative milestone: Total: 81 ALB: 50 GOAP: 28 FOA: 3 24/25 milestone: Total: 36 ALBs: 26 GOAP: 12 FOA: N/A | Cumulative achieved: Total: 110, A+ ALB: 60 GOAP : 47 FOA: 3 (23/24) 24/25 achieved: Total: 67 ALBs: 36 GOAP: 31 |
| 2.2 | % of outputs developed that included inclusive consultation processes | Flat milestone: 60% | Cumulative achieved: Total: 73%, A+ ALB progress: 89% GOAP progress: 53% 24/25 achieved: Total: 70% ALB progress: 91% GOAP progress: 48% |

C1. Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 monitors the programme’s progress towards providing policy and regulatory recommendations and guidelines to stakeholders.

2.1 – A+. This indicator reports the number of policy briefs, roadmaps, and recommendations or guidelines that contribute to sustainable development. In Year 4, delivery partners both exceeded their targets, reflecting the cumulative effect of relationships that have been built and strengthened over several years. Many of the products delivered this year mark the realisation of work initiated in earlier phases, enabled by established collaboration, regular engagement, and stronger coordination with in-country stakeholders.

2.2 – A+. This indicator measures the percentage of outputs that included an inclusive consultation process, assessed using the inclusive consultation tool with eight levels of participation ranging from manipulation (1) to citizen control (8) (please refer to Annex 2 for detail on the levels of participation). For this indicator, a process is considered inclusive if it scores 4 (consultation) or above. The indicator recognises that inclusive consultation or participation may not be appropriate for all outputs (hence a milestone of 60%) but aims to document the inclusive nature of much of the programme’s work. In Year 4, this target was surpassed with a score of 70%. Among delivery partners, ALBs achieved 91% (against the 60% target), while GOAP scored 48%. This is partly because, in Year 4, GOAP focused on developing social account products independently to introduce the concept ahead of broader engagement. These products were primarily designed to inform and stimulate dialogue, laying the groundwork for more inclusive consultation processes in subsequent phases.

Detailed example outputs for indicators 2.1 and 2.2

Belize Green Listing Recommendations Phase 1: Under its Blue Bond agreement, Belize has committed to strengthening the management and conservation of its marine protected areas (MPAs). To support this, the country is applying the International Union for Conservation of Nature  (IUCN) Green List Standard, a global benchmark for effective and equitable conservation. In Year 4, ALBs worked with the Belize Fisheries Department to finalise Phase 1 of the Green Listing Recommendations. Developed through a consultative process, these provide practical guidance for applying the Standard across Belize’s MPA network and help the country prioritise investments to meet its Blue Bond commitments.

Senegal Marine Spatial Planning (MSP) Roadmap: The Government of Senegal is using Marine Spatial Planning (MSP) to promote sustainable development, address marine-related challenges, and reduce conflicts between marine activities and users. In Year 4, ALBs supported the re-establishment of the national MSP Working Group and the update of the outdated MSP Roadmap, which was reviewed and revised with key government stakeholders before being finalised within the group. OCPP also contributed to developing a draft MSP framework and plans to consult further with stakeholders, including CSOs, during a visit to Senegal in November 2025 to finalise the document.

GOAP social accounts: In Year 4, GOAP supported several country-led processes: in Indonesia, it developed the ‘Revised Roadmap for Ocean Accounting Implementation 2025–2045’ through consultative workshops and focus groups; in Vanuatu, it produced the ‘Ocean Accounts Implementation Roadmap’ following a national workshop; and in Samoa, it contributed to finalising the ‘Marine Spatial Plan 2024–2034’ by providing expert review at the government’s request.

## Output 3

| Output Title | Enhanced education, awareness and exchange of scientific, technical knowledge and data in relevant topics |  |  |  |
| --- | --- | --- | --- | --- |
| Output number: |  | 3 | Output Score: | A |
| Impact weighting (%): |  | 16.66 | Weighting revised since last annual review? | N/A |

| Indicator(s) | Description | Milestone(s) for this review | Progress |
| --- | --- | --- | --- |
| 3.1 | Number of datasets or monitoring systems developed or improved; ocean accounts compiled; educational resources produced | Cumulative milestone: Total: 105 ALB: 80 GOAP: 25 FOA: N/A 24/25 milestone: Total: 45 ALBs: 43 GOAP: 2 FOA: N/A | Cumulative achieved: Total: 102, B ALB: 71 GOAP: 31 FOA: N/A 24/25 achieved: Total: 42 ALBs: 34 GOAP: 8 FOA: N/A |
| 3.2 | Number of scholars who enrolled and % who achieved a qualification (Masters, PhD) in relevant topics Note: This indicator also intends to report the number of ACU scholars who achieve a qualification. This has not yet been captured as the first cohort is expected to complete their studies in the first quarter of Year 5. | Cumulative milestone: Total: 114 ALB: 94 GOAP: 20 FOA: N/A 24/25 milestone: Total: 20 ALBs: 0 GOAP: 20 FOA: N/A | Cumulative achieved: Total: 126, A+ ALB: 102 GOAP : 24 FOA: N/A 24/25 achieved: Total: 32 ALBs: 8 GOAP: 24 FOA: N/A |
| 3.3 | Scientific papers, reports, strategies, tools and/or databases developed or published which are freely available | Cumulative milestone: Total: 54 ALB: 15 GOAP: 28 FOA: 11 24/25 milestone: Total: 11 ALBs: 7 GOAP: 4 FOA: N/A | Cumulative achieved: Total: 105, A+ ALB: 38 GOAP: 56 FOA: 11 (23/24) 24/25 achieved: Total: 62 ALBs: 30 GOAP: 32 FOA: N/A |

C1. Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 seeks to monitor the programme’s progress towards providing enhanced education, awareness and exchange of scientific, technical knowledge and data in relevant topics.

3.1 – B. This indicator tracks the number of education, awareness, scientific or knowledge resources (such as datasets, technical assessments, monitoring systems, ocean account or education resources) developed with support from OCPP funding. In Year 4: ALBs developed 34 products, underdelivering against a target of 43 products; and GOAP delivered eight (8), surpassing a target of two (2) products. ALBs developed education resources such as the MPA Short Course in Ghana and the Seagrass Monitoring Training Resources in Madagascar, as well as monitoring systems and datasets, such as the Waste Monitoring Methodology for Sri Lanka. GOAP also developed educational resources, such as the Introduction to Ocean Accounting and Plastic Accounting for university of Cape Coast, and datasets including Fiji Social Account Dataset.

The table below provides a breakdown of resources developed in Year 4, broken down by resource type and delivery partner.

| Resource type | Delivery partner | Level of support |  | Total |
| --- | --- | --- | --- | --- |
|  |  | New | Improved |  |
| Dataset | ALBs | 8 | 1 | 9 |
|  | GOAP | 3 | 0 | 3 |
| Educational Resources | ALBs | 15 | 1 | 16 |
|  | GOAP | 2 | 0 | 2 |
| Monitoring system | ALBs | 3 | 1 | 4 |
| Ocean accounts | GOAP | 3 | 0 | 3 |
| Technical assessments | ALBs | 5 | 0 | 5 |
| Total |  | 39 (93%) | 3 (7%) | 42 |

3.2 – A+. This indicator reports the number of scholars who registered on a formal academic programme (Masters or PhD) in themes of marine pollution, sustainable seafood, biodiversity, with the support of ALBs (coordinated by ACU). It also includes fellows who undertake a period of research with the support of GOAP. This indicator also intends to report the number of ACU scholars who achieve a qualification: the first cohort is expected to complete their studies in the first quarter of Year 5.

The figure below shows the number of ACU scholars by their home country (Year 3 and Year 4).

For GOAP’s fellows reported in OP3.2, 67% (16) were male and 33% (8) were female. The age distribution shows that 92% (22) of fellows were between 25–64 years, while 8% (2) were aged 15–24 years. For geography, 42% (10) fellow reported originating from an urban location and 17% (4) from a rural location. It was not feasible to collect this information from 42% (10) fellows. Disability data was not feasible to report.

In the ALBs programme, the gender distribution was more balanced, with 52% (53) of scholars identifying as female and 48% (49) as male. Age, geography, and disability data were not feasible for this group.

3.3 – A+. This indicator measures the number of publications produced by OCPP that are freely available. In Year 4, delivery partners significantly exceeded targets, producing 62 publications: ALBs developed 30 publications (against a target of 7) and GOAP developed 32 (against a target of four (4)). These publications reflect the programme’s growing maturity, as activities are completed and findings are consolidated into reports, scientific papers, and tools. GOAP outputs included scientific papers such as “Role of Ocean Accounts in Transitioning Towards a Sustainable Blue Economy” and “Building Ocean Accounting for Mangrove and Seagrass Ecosystems in Marine Protected Areas.” ALB outputs included reports such as “Assessing Potential Impacts of Climate Change-Related Hazards on the Marine Environment of Senegal” and “Pervasive Microplastic Ingestion by Commercial Fish Species from a Natural Lagoon Environment” in Sri Lanka.

In light of this progress, a more ambitious target could have been set for Year 4 targets. In Year 3, ALBs delivered 8 publications and GOAP 32, suggesting that targets could have better reflected the programme’s trajectory and growing maturity.

## Output 4

| Output Title | Active ocean-science related knowledge networks and partnerships (either UK – partner country or in-country coalitions) developed or supported by OCPP activities |  |  |  |
| --- | --- | --- | --- | --- |
| Output number: |  | 4 | Output Score: | A |
| Impact weighting (%): |  | 16.66 | Weighting revised since last annual review? | N/A |

| Indicator(s) | Description | Milestone(s) for this review | Progress |
| --- | --- | --- | --- |
| 4.1 | MoUs or similar agreement between OCPP and partner country stakeholders signed | Cumulative milestone: Total: 21 ALB: 6 GOAP: 14 FOA: 1 24/25 milestone: Total: 4 ALBs: 4 GOAP: 5 FOA: N/A | Cumulative achieved: Total: 21, A ALB: 8 GOAP: 12 FOA: 1 (23/24) 24/25 achieved: Total: 7 ALBs: 4 GOAP: 3 FOA: N/A |
| 4.2 | Number of public- private sector partnerships or business clusters mobilised | Cumulative milestone: Total: 12 ALB: 10 GOAP: N/A FOA: N/A 24/25 milestone: Total: 4 ALBs: 4 GOAP: N/A FOA: N/A | Cumulative achieved: Total: 10, B ALB: 8 GOAP: N/A FOA: 2 (23/24) 24/25 achieved: Total: 2 ALBs: 2 GOAP: N/A FOA: N/A |
| 4.3 | Number of in-country coalitions, governance structures, networks or task forces established, engaged or strengthened | Cumulative milestone: Total: 41 ALB: 20 GOAP: 15 FOA: N/A 24/25 milestone: Total: 13 ALBs: 11 GOAP: 2 FOA: N/A | Cumulative achieved: Total: 68, A++ ALB: 22 GOAP: 40 FOA: 6 (23/24) 24/25 achieved: Total: 40 ALBs: 13 GOAP: 27 FOA: N/A |

C1. Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 monitors active ocean-science related knowledge networks and partnerships (either UK–partner country or in-country coalitions) developed or supported by OCPP activities.

4.1 – A. This indicator measures the number of MOUs or similar agreements signed between OCPP and partner country stakeholders. In Year 4 reporting the OCPP achieved its target. ALB’s exceeded their target, with an MoU between the British High Commission and the Ministry of Sea, Inland Waters and Fisheries of the Republic of Mozambique, and three frameworks for collaboration with the Department of Fisheries in Bangladesh; the High Authority for Maritime Safety and Security in Senegal; and one establishing MSP working group terms of reference in Senegal. GOAP formalised agreements with two new GOAP members in the Maldives, National Oceanography Centre UK and The Baltic Marine Environment Protection Commission, plus an MoU with the Ministry of the Environment and Energy in Costa Rica.

4.2 – B. This indicator measures the number of public–private sector partnerships or business clusters mobilised. These are evidenced by formal agreements or commitments to deliver a project or service, traditionally provided by the public sector, that aligns with OCPP objectives. In Year 4, ALBs signed a donor partnership agreement in Belize with the International Atomic Energy Agency, and a contract for sampling, eDNA, and water quality analysis in Chilika Lagoon, Odisha, India, aimed at developing a holistic understanding of species diversity to support fisheries management.

Note: Please note that Indicator 4.2 is not applicable to GOAP, and that FOA did not implement any activities under OCPP in Year 4.

4.3 – A++. This indicator measures the number of in-country coalitions, governance structures, networks, or task forces that have been established, engaged, or strengthened. ALBs and GOAP exceeded their targets, with GOAP accounting for most of this progress. GOAP notably included the KPI Framework: Ocean Accounts Alignment Working Group in Belize; the Resource Mobilisation Committee, a regional task force in Kenya; and the Indonesia Ocean Accounts Task Force. ALBs established almost half of these coalitions in Sri Lanka, including 5 networks and 1 in-country coalition, the Water Sampling Team. The tables below provide a detailed breakdown of results by type and by delivery partner.

| Type​ | Level of support​ |  |  | Total​ |
| --- | --- | --- | --- | --- |
|  | Established | Engaged | Strengthened​ |  |
| Governance structure | 1 |  | 3 | 4 |
| Coalition​ | ​4 | 2 | 1 | 7 |
| Network​ | 9 | 6 | 6 | 21​ |
| Task force​ | 3 | 5 | 0 | 8 |
| Total​ | 17 | 13 | 10 | 40 |

- OCPP support to coalitions takes different forms: groups may be established as new entities; engaged when pre-existing groups agree to work towards shared objectives aligned with OCPP; or strengthened when existing groups receive training, organisational support, facilitation, or resources. Delivery teams noted that variation between planned and achieved results could partly be due to uncertainty in applying logframe definitions, particularly around how formal coalition structures needed to be and the duration of engagement. This led to targets being set lower than necessary. Nevertheless, the notable overachievement is widely attributed to the strong relationships consolidated during Year 4 of programme implementation.

## Output 5

| Output Title | Innovative initiatives piloted that support equitable market access and value chain improvement |  |  |  |
| --- | --- | --- | --- | --- |
| Output number: |  | 5 | Output Score: | N/A |
| Impact weighting (%): |  | 16.66 | Weighting revised since last annual review? | N/A |

- This indicator is aimed at FOA. No new FOA projects were delivered in Year 4 and therefore the delivery partner is absent from this annual review’s reporting of results. However, FOA has entered into a grant agreement with Defra for Year 5.

## Output 6

| Output Title | OCPP intervention design adequately considers gender, equity and social inclusion and safeguarding |  |  |  |
| --- | --- | --- | --- | --- |
| Output number: |  | 6 | Output Score: | A |
| Impact weighting (%): |  | 16.66 | Weighting revised since last annual review? | N/A |

| Indicator(s) | Description | Milestone(s) for this review | Progress |
| --- | --- | --- | --- |
| 6.1 | Number of GESI analyses (at a national, thematic or intervention level) completed | Cumulative milestone: Total: 9 24/25 milestone: Total: 8 Indicator planned at programme level | Cumulative achieved: Total: 9, A 24/25 achieved: Total: 8 FOA: 1 (23/24) Indicator planned at programme level |
| 6.2 | Number of cases which demonstrate integration of GESI analysis recommendations into delivery | Cumulative milestone: Total: 9 ALB: 8 GOAP: 0 FOA: N/A 24/25 milestone: Total: 8 ALBs: 8 GOAP: N/A FOA: N/A | Cumulative achieved: Total: 9, A ALB: 6 GOAP: 5 FOA: 1 (23/24) 24/25 achieved: Total: 8 ALBs: 6 GOAP: 5 FOA: N/A |

C1. Briefly describe the output’s activities and provide supporting narrative for the score.

Output 6 monitors progress towards OCPP intervention design adequately considering gender, equity and social inclusion and safeguarding.

In Year 4, ALBs and GOAP renewed their focus on GESI and took actions to strengthen the mainstreaming of GESI in activities. The wording of Indicator 6.1 and Indicator 6.2 was adjusted during the biannual review of the logframe to better reflect planned delivery for the remaining half of Year 4. The wording was also adjusted to account for the GESI training the delivery teams were undertaking throughout the delivery period.

6.1 – A. This indicator captures the number of GESI analyses carried out by OCPP to inform intervention design. These analyses are intended to inform the design of activities and interventions and as a result, their target is not disaggregated by delivery partner type. In Year 4, ALBs mobilised external expertise to deliver eight (8) additional GESI analyses in Bangladesh, Belize, Ghana, Madagascar, Mozambique, the Maldives, Senegal, and Sri Lanka.

6.2 – A. This indicator reports on how OCPP is designing its interventions to respond to the needs and priorities of women and marginalised groups, based on analyses carried out in Indicator 6.1. The indicator seeks to identify evidence of the integration of GESI considerations into OCPP activities, interventions or workstreams. To note, the milestone for this indicator is based on the number of countries where such evidence exists. In Year 4, the programme made progress in integrating GESI considerations across eight (8) countries.  ALBs integrated GESI priorities identified through gender analyses in six (6) countries (against a target of eight (8)) so did not meet their target, while GOAP, which had no formal target, reported integrating GESI considerations into its work in five (5) countries.

This year’s results demonstrate a strong push to integrate GESI into programming and good progress against indicators. However, embedding GESI considerations in the fourth year of implementation has proved challenging. ALBs in particular reported difficulties integrating GESI into programme activities, as several workstreams were already at a more advanced stage of delivery, making it harder to adapt or pivot activities. For GOAP, GESI analyses commissioned by OCPP in Belize, Madagascar, Maldives, Mozambique, and Sri Lanka informed the planned development of social accounts in those countries, but did not lead to significant changes in activities already under implementation.

Detailed output example for indicators 6.1 and 6.2

GESI integration evidence: Output 6.2 has been designed to count cases of GESI integration. In Year 4, ALBs provided 132 pieces of evidence on how they drew on GESI analyses to inform their interventions. These have included examples of GESI mainstreaming in activity design, stakeholder engagement, monitoring, and team capacity building, as well as the identification and mitigation against safeguarding risks. Examples are included below:

- Bangladesh Black Soldier Fly Farming: OCPP activities have created new opportunities for women’s participation in Black Soldier Fly (BSF) farming in Bangladesh, a field traditionally dominated by men. To encourage inclusion, the programme tailored training to address women’s specific needs. Only a few women attended the first session, their numbers have since grown, with more women than men participating in the second training, which focused on building BSF farming equipment. This activity is, helping position BSF farming as a more gender-inclusive enterprise that could offer women valuable opportunities for income generation their first formal employment.

Mozambique Capacity Building for Effective MPA Management: OCPP supported the upskilling of marine protected area (MPA) practitioners in Mozambique in topics such as management planning, sustainable financing, and coastal ecosystem data analysis. This included contributions to the development of an MPA Leadership Academy and the Western Indian Ocean Certification of Marine Protected Areas Professionals (WIO-COMPAS) programme. GESI mainstreaming strategies ensured diverse perspectives were integrated into MPA management. The Gender in Marine Protected Areas study provided a resource for shaping training activities, while a GESI workshop checklist was developed to make capacity-building activities more inclusive. Training materials were designed for accessibility, with interactive sessions to support learning and networking. In addition, under the Academy scoping contract, OCPP required the contractor, Nautilus Conservacao, to develop a GESI and SEAH policy for the Academy’s creation.

GOAP’s social accounts: GOAP’s Ocean Accounts framework aims to provide a more comprehensive understanding of the oceans’ contribution to societal well-being than current economic and nature metrics alone. In Year 4, GOAP has been progressing in the development of social accounts to capture and analyse the social, cultural and equity dimensions of the human-ocean relationship within Ocean Accounts. This work includes the development of a database to assess secondary data available for social accounts and social inclusion issues (including OCPP GESI analyses). In addition, work on social accounts is ongoing in Vanuatu, Costa Rica and Fiji, with GESI analyses planned for Indonesia, Samoa, Tonga and Costa Rica in Year 5.

C2. Describe any changes to outputs during the past year, and any planned changes as a result of this review.

In November 2024, the logframe underwent a biannual review with Programme Directors to make small adjustments to indicators to better reflect the programme and update Year 4 milestones and targets. See Annex 3 for details.

- Year 4 was the first time Programme Directors could base the setting of targets and milestones on data generated from the revised and strengthened MEL framework. Monitoring results from Year 3 were used to inform decision-making, aiming to ensure targets aligned more closely with the programme’s trajectory and workplans; this approach proved effective for many indicators. For example, under Indicator 3.1 (number of datasets or monitoring systems developed or improved; ocean accounts compiled; educational resources produced), OCPP scored a C in Year 3. In Year 4, with ALBs and GOAP more familiar with the indicators and drawing on the lessons of the previous year, the target was adjusted to a more achievable milestone.

- However, some targets were perhaps set too low. Under Indicator 3.3 (scientific papers, reports, strategies, tools and/or databases developed or published which are freely available), delivery partners significantly exceeded expectations, producing 62 publications: ALBs developed 30 against a target of seven (7), while GOAP produced 32 against a target of 4. These outputs reflected the consolidation of work into reports, scientific papers, and tools as the programme matured. Yet the Year 3 performance (eight (8) publications from ALBs and 32 from GOAP) suggested that Year 4 targets could have been set at a more ambitious level. Nonetheless, these results reflect delivery partners’ efforts to accelerate progress in Year 4, bringing forward elements of Year 5 and demonstrating a strong commitment to making resources publicly accessible.

- Targets appeared to be similarly low for Indicator 4.3 (tracking the number of in-country coalitions, governance structures, networks, or task forces), with 40 coalitions achieved against a target of 13 in Year 4. GOAP exceeded their targets, establishing 27 coalitions compared to a target of two (2). Delivery teams explained that part of the variation between planned and actual results stemmed from uncertainty in applying logframe definitions, particularly around how formal coalition structures needed to be and how long they should be engaged, which in turn led to more conservative target setting.

For GOAP, some Year 5 budget was redirected into Year 4, enabling a further expansion of these activities. This pivot demonstrates the programme’s flexibility and adaptability in responding to changing circumstances.

The planned changes to the logframe include adjusting targets at the outcome level (per section B2) and adjusting the wording of Outcome 3 to reflect ‘number of cases’, instead of ‘number of countries,’ which currently limits the programme’s ability to report multiple cases occurring within a country.

C3. Progress on recommendations from the previous annual review (if completed)

Of the 21 recommendations issued in the Year 3 annual review, 18 have been completed by the delivery partners, demonstrating an agile and adaptive response to the results of last year. The 3 ‘in-progress’ recommendations relate to: poverty alleviation narratives; delivery chain mapping and International Aid Transparency Initiative (IATI) reporting; and promoting the adoption and use of their policy and guidance recommendations with partner governments. Most of the recommendations from Year 3 focus on ALB delivery, though one (1) was specific to GOAP. The full update on progress is provided in Annex 4.

# D: RISK

## Overview of risk management

The overall risk rating for OCPP in Year 4 is Medium. This assessment is based on several factors, detailed below, including improvements in risk management processes, and progress made in addressing key structural issues identified in previous reviews, specifically poverty alleviation and safeguarding. However, there is a risk to the sustainability of programme impact due to challenges in progressing towards outcome-level change. Though some progress has been demonstrated within this AR, achievement is not at the level expected at this stage of programme delivery. Transition planning and execution in Year 5 is critical to maximising sustainability of outcomes. The programme team has assessed 'risk appetite' levels in year 4 of the programme and have implemented within the programme's risk management processes. Fraud Risk Assessments (FRA) for delivery partners have been refreshed.

- Revised ALB delivery structure and risk management processes: Year 4 provides a full year of implementation with Cefas as the Tier 1 delivery partner and JNCC and MMO as Tier 2 partners (see Section E1.1). The Tier 1/Tier 2 structure led to a reorganisation of the risk management system for ALBs. In Year 4, risks were first managed at the country-level, discussed at fortnightly cross-ALB meetings, and included in progress reports. Where escalation was required, they were added to the programme-level RAID log. The RAID log was reviewed at a monthly meeting with Programme Directors and the Defra Programme Team, and quarterly by the Programme Management Board. Both Defra and ALBs noted improvements in risk management, with the streamlined approach making the RAID log more practical and easier to use.

- Revised GOAP risk management processes: A dedicated GOAP-level risk register was created for Year 4. Previously, risks had been managed through the register of the Centre for Sustainable Development Reform at the University of New South Wales (UNSW), which hosts the GOAP Secretariat. A new reporting structure was also agreed: the Risk Lead provides monthly email updates, with a detailed discussion held at quarterly progress meetings. High priority risks that require attention are escalated to Defra outside of regular reporting structures.

- Poverty and safeguarding: Defra introduced a Performance Improvement Plan (PIP) to address persistent programme challenges (see Section E1.1). The PIP prioritised strengthening the programme’s poverty reduction focus and enhancing the approach to Safeguarding against Sexual Exploitation, Abuse and Harassment (SEAH). In Year 4, delivery partners acted on these recommendations:

SEAH: ALBs established a SEAH working group. As Tier 1 partner, Cefas engaged Social Development Direct to review the SEAH risk assessment and adapt it to the specifics of each partnership. In addition, ALB staff received SEAH training. GOAP also engaged with the Global Safeguarding Team to review their internal safeguarding approach, as well as the UNSW policy, to ensure that they are in line with FCDO guidance.

Poverty alleviation: ALBs and GOAP worked together to develop a narrative on poverty alleviation, and NIRAS produced case studies demonstrating programme contributions in this area.

Current risks identified by this Annual Review are outlined in the table below, integrating information from KIIs and both Defra and ALB risk logs. They relate primarily to programme resources, transition planning, and GESI integration. All identified risks have mitigation measures in place, with clear ownership assigned and regular monitoring at programme and partner levels.

Year 4 Key OCPP Risks identified by this Annual Review

| Risk Description | Inherent Risk | Mitigation actions | Residual Risk | Risk Appetite & Target RAG |
| --- | --- | --- | --- | --- |
| Lack of delivery team resources and engagement There is a significant risk that within ALBs, delivery team resources decline from January-March 2026, and among in-country partners. This is linked to staff departures not being replaced and individuals shifting focus to new opportunities, and is expected to continue as closure approaches. | Medium | Ensure that ALBs continuously monitor the availability of resources and identify potential gaps at an early stage to enable timely mitigation. Defra should be kept informed of any developments through regular updates at tactical meetings. | Medium | (3) Open |
| Overrun of activities impacting reporting of results The programme is scheduled to conclude in March 2026. For ALBs, workstreams/activities are due to finish in December 2025, while delivery teams will have until 31 March 2026 to finish reporting. GOAP and FOA will finish activities and programme reporting at the same time by the end of March 2026. There is a risk that delivery overruns past these key dates, which might hamper delivery team’s ability to evidence and report on outputs and outcome level change. | High | The NIRAS MEL team has established a protocol for activity overrun and what happens if results occur after the set reporting period. This protocol has been published to delivery teams and all delivery partner Programme Directors, and is available on the shared monitoring and reporting database provided by the MEL partner. | Medium | (3) Open |
| Transition and sustainability Many transition activities are underway in bilateral partnerships. However, with a significant reduction in UK ODA funding, the sustainability of OCPP interventions remains a challenge. Strengthening these efforts into a coherent transition strategy at the country-level will be essential to safeguard the development gains achieved by OCPP. | High | ALBs to ensure that Defra is kept informed on transition progress through the progress reports and other updates. | High | (3) Open |
| Limited GESI implementation time Mainstreaming of GESI was introduced halfway through the programme’s lifecycle. While Defra’s stated ambition is for the programme to reach ‘GESI sensitive’ by December 2025, this might not be possible, given that many workstreams and activities have either already concluded, or are not applicable for GESI mainstreaming based on the rationale that key elements are now beyond the control of delivery partners for GESI implementation. As a result, there is a risk that GESI integration will not be fully realised in the final stages of programme implementation. | High | To maximise GESI integration within the remaining programme timeframe, delivery partners should be supported to identify and act on any remaining opportunities for meaningful GESI mainstreaming, particularly in ongoing or adaptable workstreams. Programme team members whose remit is for GESI delivery within the ALBs, GOAP and FOA (such as the Tier 1 social scientist for ALBs, for example) should provide targeted guidance and examples to help teams recognise where GESI considerations can still be embedded, even in seemingly closed activities (e.g. through reporting, dissemination, or legacy planning). Additionally, the NIRAS MEL partner should work with delivery partners to ensure that GESI-related learning is systematically captured, synthesised, and shared across the programme and with future initiatives. This will help ensure that even where full GESI sensitivity cannot be achieved, the programme contributes to long-term institutional learning and capacity building. | Medium | (3) Open |

# E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

## E.1. Summarise the performance of partners and Defra, notably on commercial and financial issues.

E1.1. Delivery Partners

Programme Management

Performance Improvement Plan (ALBs and GOAP): Defra introduced a Performance Improvement Plan (PIP) following two consecutive B scores in its Year 2 and 3 Annual Reviews. The PIP brought together key recommendations from the ICAI BPF review, the OCPP Interim Evaluation, and the Year 3 Annual Review, consolidating them into a focused set of actions to address persistent programme challenges. These included ensuring that poverty alleviation and GESI are central to the programme, and strengthening the approach to SEAH. Defra and delivery partners reported that the PIP has been a valuable tool, enabling long-standing issues to be addressed more systematically and aligning the programme more closely with good development practice.

MEL system (ALBs and GOAP): The MEL system was introduced partway through Year 3, with Year 4 representing the first full year of implementation under the revised logframe and ToC. ALBs and GOAP reported upskilling and becoming more familiar with the system, which contributed to improved reporting of results in Year 4. ALBs also noted that the MEL framework supported stronger delivery, while programme-wide engagement with the ToC and logframe has helped teams better understand the overall strategy, the links between different workstreams, and the importance of focusing on outcomes rather than activities alone. In addition, while there were constraints to GOAP’s reporting against intermediate outcomes and outcome-level indicators in Year 3, these constraints were overcome in Year 4, enabling reporting against these levels more fully for the first time.

Revised delivery structure (ALBs): Following the Year 2 annual review recommendation, OCPP’s delivery structure was revised in October 2023, designating Cefas as the Tier 1 delivery partner with JNCC and MMO as Tier 2 partners. Previously, Defra engaged directly with all three ALBs on delivery and risk matters without a central coordination mechanism. This structure was therefore set up partway through Year 3 and Year 4 provides a full year of implementation under the new structure. Under the new structure, Cefas is accountable for governance and coordination across the other ALBs, with a clearer decision-making chain and escalation process now in place. ALBs reported greater clarity in roles and responsibilities and stronger risk management processes, with defined escalation points. For Defra, the change meant a step back from day-to-day management, enabling the Programme Team to focus more on strategic oversight and direction. Both ALBs and GOAP reported improvements in communication, with Defra providing a clearer and more consistent steer on priorities.

Friends of Ocean Action (FOA): FOA did not implement activities in Year 4. Throughout Year 4, FOA and Defra worked on developing a new grant building on FOA’s earlier work, which was formally signed at the end of May 2025. The grant, originally designed as a 12-month project, will need to be delivered within a compressed period to meet OCPP’s hard deadline for all activities to be completed by March 2026. The project will support the incubation of a Food Innovation Hub in Ghana focused on blue food, building on FOA’s previous efforts to create a cluster of organisations working on aquaculture to drive job creation and promote inclusion of women and marginalised communities. It will also draw on lessons from FOA’s global sustainable aquaculture roadmap.

Financial performance

ALBs: Defra have worked with the ALBs to improve financial reporting in OCPP so that Defra can better assess VfM overall.  A new cost reporting approach was agreed and this approach is now applied alongside standard financial management processes.

ALBs achieved a budget execution rate of over 99%, demonstrating strong financial management under constrained circumstances.

GOAP: Under OCPP, GOAP has received three phases of funding, and in Year 4 Phases 2 and 3 overlapped, resulting in a higher volume of work and budget to absorb. Some Year 5 GOAP funding was move into Year 4 requiring a revised workplan. As a result, GOAP’s budget in Year 4 increased, enabling an expansion of activities. Despite these challenges, GOAP achieved a budget execution rate of 100% in Year 4.

E1.2. Defra

In Year 4, OCPP was overseen by a new SRO. In addition, Defra revised its internal structures by introducing a clear Responsible, Accountable, Consult and Inform (RACI) framework, which formalised levels of approval and clarified what issues needed to be escalated.

## E2. Assess the VfM compared to the proposition in the Business Case, based on performance over the past year

E2.1. Summary

The Year 4 Value for Money (VfM) assessment presents a broadly positive picture across all four VfM dimensions — Economy, Efficiency, Effectiveness, and Equity. The introduction and operationalisation of a tailored VfM framework this year has enabled more structured and consistent reporting across delivery partners, enhancing transparency.

- Economy: Delivery partners demonstrated strong financial discipline, with expenditures remaining within agreed budget ceilings and aligned with Defra expectations. The cost structures reflect the programme’s technical assistance modality, and the cost transparency exercise undertaken by Defra on the delivery partners has strengthened VfM assurance.

- Efficiency: Budget execution rates were high (99–100%), indicating robust financial planning and adaptive delivery. Good practice examples across partners show efforts to maximise impact while controlling costs, including localised delivery, collaboration with other donors, and strategic use of resources.

- Effectiveness: VfM indicators associated with effectiveness, ICF KPI 15 and KPI 17, are intended to be reported on in the evaluation assessment at the end of the programme to understand long-term impact. For Year 4, other programme evidence has emerged such as the poverty alleviation case study findings, showing potential for short, medium and long-term benefits to communities, and indicating effectiveness.

- Equity: Progress has been made in mainstreaming GESI considerations, with partners meeting agreed milestones under relevant logframe indicators.

For Year 4, the programme has made notable strides in embedding VfM principles into its delivery and reporting. Continued focus on learning, standardisation, and evaluation assessments to validate outcome and impact level results will be key to sustaining and evidencing VfM in the final year.

This year was the first year OCPP delivery partners reported against tailored metrics for OCPP’s VfM framework. The framework was developed and agreed upon during Year 4, with inputs from and consultations with the delivery partners and Defra. In the previous years, there was not a VfM framework, however some of the measures in that framework were being reported to Defra through other processes. The framework includes both qualitative and quantitative indicators, trying to look at cost, as well as results and benefit aspects of VfM performance. It also draws on the other MEL tools and evidence sources of the programme, such as the logframe and programme evaluations.  and evidence sources of the programme, such as the logframe and programme evaluations.

This year’s VfM reporting has a number of limitations. Firstly, it is difficult to reach definitive conclusions due to a lack of trend information over the years, and milestones and targets on some of the indicators. Secondly, while the indicators are programme-wide and for all the delivery partners to report against, the results are invariably a range. In other words, there isn’t one VfM result and often a set of results. Finally, four out of the five delivery partners reported this year, with the exception of FOA, which did not implement activities in Year 4.

VfM at Business Case:

A quantified economic analysis was carried out for the OCPP Business Case. Three main benefits were identified (livelihood improvements, health improvements and marine environment benefits). For each benefit, a number of themes were also mapped out (marine pollution, marine biodiversity and sustainable seafood) as to how those would contribute to the realisation of the benefit. The Business Case estimated Benefit to Cost Ratios of 2.9:1 to 9:1 which indicated significant cost-effectiveness (higher than break even 1:1, signifying for example, for £1 invested, there could be returns up to £9 equivalent). For FOA and GOAP fund allocations, separate Business Cases were prepared. They also used quantitative methods of economic analyses, and the result estimates were similarly good VfM. For GOAP, a BCR of 2.4:1 was estimated, and regarding FOA, it was offered that, based on data from similar projects, the returns could be between 3.1:1 and 12:1.

The Interim Evaluation found that the data requirements to revisit the original VfM calculations were high and unlikely to be met by the existing financial and monitoring data. Further, the duration of benefits applied in economic appraisals in BPF programmes is long, often around 30 years, which also presents a difficulty. During this review period, a VfM framework was developed and operationalised by the programme teams, and reporting is as below.

Economy

E.2.2. Key Cost Categories

This indicator seeks to understand the trends on important cost categories in financial statements. This VfM Economy analysis is concerned with changes and/or trends in key cost category items in budgets and expenditure statements and providing explanations as to why variations might exist. The objective is to demonstrate good financial management by staying within agreed budget ceilings for cost categories, as well as demonstrating that performance is within agreed benchmarks, if applicable. The analysis of a spending profile is important for answering questions of what ODA funds are spent on, and therefore serves an accountability purpose.

Across all delivery partners, expenditure in Year 4 remained within agreed budget ceilings and aligned with Defra’s expectations, demonstrating strong financial discipline. A number of VfM good practice examples were reported, indicating the delivery partner’s ability to reduce costs while maximising delivery and reflecting the high level of momentum achieved in the programme delivery. The cost transparency exercise and subsequent standardisation of reporting have significantly improved visibility and comparability of spending, which is a positive step for VfM assurance. The largest cost categories — notably frontline delivery and technical advisory staff — reflect the programme’s technical assistance modality and are consistent with what was agreed with Defra. Activity costs such as meetings or events would also be part of the frontline delivery costs. Further, there are travel costs associated with work travel to the programme countries. Finally, indirect programme costs or overhead costs are part of the financial statements for the delivery partners. It should be noted that, despite these similarities, there are differences across the partner organisations in what goes under a certain category of expenditure, as explained further below. Where variations occurred (e.g. elevated travel costs due to the Global Dialogue event), overhead costs remained below capped thresholds, and downstream allocations were appropriately prioritised.

All the indicators of this output scored highly in this annual review. For the ALBs’ component of the programme, Sri Lanka received the biggest share of expenditure among the OCPP countries over the reporting year. Overall, the programme has shown solid financial management, with cost structures that support effective delivery and reflect VfM principles.

E.2.3. VfM Good Practice Examples

The delivery partners reported a significant number of good practice examples. The examples were not only about reducing costs, but also trying to maximise impact in programme delivery. The themes of the examples can be summarised as follows: localised delivery, utilising partner resources, collaborating with other programmes and donors in the same country, outsourcing of services for efficiency, scrutinising contracts to achieve savings, combining trips and bundled TA support, submission of business cases internally for all travel, utilisation of pilots before fully committing to an activity, using online facilities to reduce travel costs, and creation of toolbox materials online for wider reach and sustainability.

The below table includes some of the highlights:

VfM Good Practices Selected Examples:

| Delivery partner | VfM Examples |
| --- | --- |
| GOAP | Local delivery: Focused on delivering with local providers, fellows and training of local experts increases the value for money of delivery but crucially this also works to enable enduring capacity within the partner countries. These individuals also have access to country-based networks but also through GOAP access to international networks, and leverage access to finance (example: Belize). Combining trips and leveraging events: Travel was packaged with multiple activities and regional visits (e.g., Maldives and Sri Lanka) were combined to reduce travel time and costs, global events (e.g. UN Ocean Conference) were used to engage multiple partners; online meetings used to reduce costs. |
| MMO | Training venues/ locations: Wherever possible, MMO seeks to use venues and facilities provided by in country partners to keep costs to a minimum, and has liaised with in country partners to ensure training is delivered in as cost effective and efficient manner as possible, without compromising delivery quality. (Example: Madagascar) |
| JNCC | Collaborating with other donors/ programmes: In Mozambique, JNCC ensured they shared work plans with the COAST programme as well as the Blue Economy Working group to ensure joined up approaches, and shared scoping needs assessment of the country’s priorities. This ensures stakeholders are not repeatedly asked scoping needs and the work can be taken forward by the most relevant programme. |
| CEFAS | Use of travel provider to organise large events: Taking this approach saved large amounts of time not having to processing complex T&S, saving on management time. The provider was also able to organise for the large meetings at a relatively short notice. |

Efficiency

E.2.4. Budget execution rate

This indicator seeks to assess efficient delivery through financial management performance. It stipulates that, being able to utilise funding adaptively using robust financial planning is a good indicator for efficiency. The delivery partners showed good performance in budget execution this reporting period, with utilisation reportedly ranging from 99% to 100%. This represents a good result also in light of the fund utilisation challenges of the previous programme years.

E.2.5. Volume of financing mobilised or leveraged vs. programme expenditure

This indicator aims to compare the £ value of financing leveraged or mobilised from other organisations, with the funding used to deliver OCPP activities. The premise is that the activities delivered by OCPP were considered successful by other donors to fund similar activities. Out of the delivery partners, only GOAP reports on this indicator as agreed within the VfM framework, and reported a good VfM result. The resulting ratio comparing the OCPP funding to GOAP (£13m) vs. what GOAP has leveraged for other funding commitments on Ocean Accounts (£160m) was >12. Compared to the result reported on the same indicator in the OCPP Interim Evaluation (>1), this indicates a good performance.

E.2.6. Length and Quality of partner engagement in TA delivery

This was planned as a qualitative indicator, which discusses the time lapsed on partnerships (in country or TA-recipient organisation level), and highlights lessons from that engagement, such as about responsiveness, prioritisation or targeting. In addition to documenting the quantitative aspects of TA delivery through periodic logframe indicators, this indicator attempts to investigate the quality aspects of the relationships with the counterpart institutions.

The delivery partners reported several examples each, from their engagements with counterparts in TA delivery across the OCPP countries. The partnerships were predominantly longer than 2-3 years. The examples of reflections included discussions on the theme of the TA, lessons on quality of engagement and responsiveness by the partners, likelihood of sustainability of interventions beyond OCPP, and finally recommendations for future engagement. These also included examples with less positive outcomes, which were mainly due to lack of partner engagement or limited capacity. Documenting these lessons constitutes a VfM good practice, as it generates learning for internal and external audiences.

Length and quality of engagement example: GOAP

Recipient Organisation: ISPONRE (Institute of Strategy and Policy on Natural Resources and Environment)​ Country: Vietnam​ Theme: Cross-cutting​ Type of TA: ocean accounts development, capacity building workshops, policy brief development, governance accounts training, solid waste accounting methodology, blue economy indicators development​ Duration: 36+ months (2021 – March 2025; ongoing across Phase 1 and Phase 2)

GOAP has provided sustained technical assistance to ISPONRE, a key Vietnamese government research institute, to develop the country’s first comprehensive ocean accounting framework. This included solid waste accounts, governance accounts, and blue economy indicators for Quang Ninh province. Working with a Technical Working Group led by Dr. Kim Thi Thuy Ngoc and Dr. Nguyen Dinh Tho, ISPONRE produced Vietnam’s first solid waste account using the System of Environmental-Economic Accounting Central Framework (SEEA-CF) methodology, published peer-reviewed articles, and developed policy briefs to inform decision-making. ISPONRE actively participated in international dialogues, sharing national experiences and strengthening Vietnam’s capacity for ocean accounts. The collaboration also helped secure GEF funding for expanded natural capital accounting, building on GOAP’s foundational support.

Equity

E.2.7. The extent to which the project results reach disadvantaged groups

This VfM category aims to ensure that the disadvantaged groups are considered and monitored among recipients of OCPP TA support. To report into this VfM category, OCPP utilises the logframe reporting for OP6.1 and OP6.2 and the disaggregation of TA support to individuals from OP1.3.  During the past year, the OCPP delivery partners made significant efforts to integrate GESI considerations and analyses in various aspects of the programme, per the reporting of logframe Indicators 6.1 and 6.2. The recommended score for that logframe output was A, meaning that the partners reached the milestones that had been agreed upon.

Further insight is provided by looking at the gender breakdown of individuals who received TA support from the programme as per output 1 of the logframe, presented in the table below. This is less straightforward to interpret from an equity performance standpoint, due to the issues in reporting accurately on ‘female’ and ‘male’ participants, per the ‘not feasible’ category. The lower representation of female individuals for ALB delivery is most likely due to the type of technical assistance being provided pertaining to the marine environment: staffing within governments in developing countries is predominantly male. While GOAP reported 41.5% female participants in their delivery, a high percentage of participants were flagged as ‘not feasible’ as being reported. It is likely that many participants who did not report their gender were male, given the predominance of male individuals within government.

On the whole, however, there has been a notable momentum to integrate GESI better by all the key programme actors over the year in review, underscored by the above output scores 6.1 and 6.2 above. Therefore, the programme has made notable strides towards considering and monitoring disadvantaged groups receiving TA support.

Disaggregation of TA recipients

| Delivery Partner | Female | Male | Not feasible |
| --- | --- | --- | --- |
| ALBs | 29.7% | 51.7% | 18.5% |
| GOAP | 41.5% | 35.1% | 23.3% |

# Annex 1. Outcome 2 Results

Of the eight (8) results reported for Outcome 2, three (3) results were reported for the bilateral (ALB) programme in Year 4. The target for ALBs is to achieve ten (10) results by Year 5:

One in Ghana, related to the implementation and independent use of fishnet bailers by the NGO, Chaint Afrique;

Two in Belize, with one related to best practice standards of marine spatial data used in the management of MPAs, and another for biosecurity measures being implemented at a government-run tilapia hatchery farm for food consumption.

GOAP reported five (5) results related to the integration and implementation of ocean accounting into government:

One in Fiji, where mangrove ecosystem accounts have been formally implemented and are being actively utilised by decision-makers;

One is Samoa, where the programme contributed to the development and finalisation of the National Marine Spatial Plan for Samoa 2024-2034, which incorporates ocean accounting into law;

Three results were recorded for Indonesia, related to the integration of ocean accounting into the legislation and practice of the government, including:

- SNI 9528 enacted in law by the Indonesia National Standard Agency Indonesian National Standard Agency (BSN) in October 2024, providing standardised data collection, analysis, and reporting frameworks for ocean accounts implementation.

- Incorporation of ocean accounts into the National Mid-Term Development Plan (RPJMN) 2025-2029, now approved by the government.

- Integration of ocean accounts into Regulation Number 99 of 2024 signed by Minister in Dec 2024. The regulation provides legal framework for valuing marine resources and ecosystem services.

# Annex 2. Inclusive consultation

An inclusive consultation process requires that key stakeholders (those that have interest or influence in the topic or area of focus for example, would be affected by policy proposals outlined in a policy brief) are identified and participate in the development of the output. Stakeholders are those groups or individuals who have a concern or interest in something. A wide range of stakeholders could include government, businesses, community members, NGOs for example.

To note, this process does not relate to formal government consultations but rather the processes that OCPP teams undertake themselves in developing outputs.

Levels of participation are described by Arnstein’s ladder, which is a well-recognised model of citizen engagement, based on eight levels of participation. They are described in the table below.

|  | Level of participation |  |
| --- | --- | --- |
| Nonparticipation | 1 | Manipulation: Non-participative engagement aimed and persuading stakeholders that they should support the proposed plan or recommendations. |
|  | 2 | Education: Non-participative engagement with stakeholders aimed at educating them to ensure they are onboard with the plan or recommendations outlined in the output. |
|  | 3 | Informing: Stakeholders are given information about the output but cannot provide feedback or inputs. |
| Participation | 4 | Consultation: Stakeholders are asked for their opinions which may be fed into the output being developed. However, ultimately decisions are made by the OCPP team on what is included or not. This would include asking stakeholders for comment on a document develop by OCPP for example. |
|  | 5 | Placation: Stakeholders are involved in shaping the ideas or information in the output but do not have the final say in what is included. |
| Citizen power | 6 | Partnership: Stakeholders work together with the OCPP team to develop the output. |
|  | 7 | Delegated power: Stakeholders develop the output themselves with inputs, support and final review from OCPP. |
|  | 8 | Citizen control: Stakeholders have the idea, propose the output and lead the process, requesting support from OCPP where they require. |

# Annex 3. Changes to the logframe

A review of the logframe and indicators was completed by Programme Directors in November 2024 to better reflect programming. These changes were informed by the Y3 monitoring data. From this review, the following changes were made to output indicators:

| Indicator​ | Type of change​ agreed in November 2024 and rationale | Revised indicator moving forward |
| --- | --- | --- |
| OP4.3 Number of in-country coalitions, governance structures, networks or task forces established, engaged or strengthened​ | Include the additional definition and additional disaggregation of ‘regional/global/in-country’ within the indicator​. OCPP’s work includes both in-country and cross-region ( a number of countries)​ | OP4.3 Number of coalition, governance structures, networks or task forces established, engaged or strengthened |
| OP1.3 Number of individuals receiving TA support ​ | Include disaggregation that captures the training that results in international certificates/accreditation/qualifications. Include capture of GOAP’s fellows. Include disaggregation by gender, age and/or disability and geography (urban/rural) if appropriate​ | Indicator remains the same; disaggregation updated. |
| ​OP3.2 Number of scholars who enrolled and % who achieved a qualification (Masters, PhD) in relevant topics ​ ​ | Include disaggregation by gender, age and/or disability and geography (urban/rural) if appropriate​. Include GOAP’s fellows in indicator and definition. Annual Review recommendation to include GESI disaggregation; also to be compliant with HMG policy. ​ | OP3.2 Number of scholars or fellows who enrolled and % who achieved a qualification (Masters, PhD) or undertook a fellowship in relevant topics |
| OP6.1 Number of scoping missions/reports that include detailed stakeholder mapping, GESI analysis and safeguarding risk assessment​ | Wording of this indicator was changed to reflect programme delivery and the scheduled independent country level analysis contracted for 2025. | OP6.1: Number of GESI analyses (at national, thematic or intervention level) completed and approved. |
| OP6.2 Number of intervention plans that reflect GESI recommendations and safeguarding measures​ | Adjust to demonstrate how the analysis being used in the delivery of activities. | OP6.2: Number of cases which demonstrate integration of GESI analysis recommendations into delivery. |

# Annex 4. Progress on Recommendations

Recommendation: GESI

1: GESI baseline analysis and self-assessment of the OCPP’s delivery must be conducted as soon as possible, this should include identification of GESI and safeguarding risks and mitigations and stakeholder groups and engagement approaches. The result must be embedded into country workplans to ensure integration into bilaterial programme design and delivery.

Progress: Completed. Cefas (as Tier 1 partner) commissioned and completed for following national, thematic and intervention level independent analyses:

4x SDDirect National GESI Analysis for Belize, Ghana, Senegal, Sri Lanka​;

2x SDDirect Thematic GESI Analysis for Madagascar & Bangladesh​;

MUVA National GESI Analysis for Mozambique;​

JEA Report for Maldives: GESI and SEAH status report for the Maldives.

From these analyses, six (6) out of the eight (8) countries where the commissioned GESI analyses were undertaken recorded adjusting their workplans based on the findings. These countries include: Belize, Ghana, Maldives, Mozambique, Senegal, and Sri Lanka. However, it should be noted that delivery teams for the bilateral partnership in Bangladesh and Solomon Islands reported utilising the GESI specialist/working group and/or other types of GESI-focused analysis to inform their workplans.

However, embedding GESI considerations in Year 4 of implementation has proved challenging. ALBs in particular reported difficulties integrating GESI into programme activities, as several workstreams were already at a more advanced stage of delivery, making it harder to adapt or pivot activities. For GOAP, GESI analyses commissioned by OCPP in Belize, Madagascar, Maldives, Mozambique, and Sri Lanka informed the planned development of social accounts in those countries, but did not lead to significant changes in activities already under implementation.

2. All OCPP delivery partners must ensure they have access to adequate GESI and safeguarding capacity and capability to ensure compliance with Defra ODA safeguarding and GESI guidance, and the ability to achieve GESI sensitive by December 2025.

Progress: Completed. GESI and SEAH working groups all established and running; training and upskilling took place throughout Year 4.

3: GESI output and indicators within the programme logframe should be refined and data disaggregated by sex, age, disability and geography.

Progress: Completed. The MEL delivery partner updated the appropriate indicators within the logframe and the indicator reference sheets where this level of disaggregation could potentially be provided (for OP1.3 and OP3.2). This was communicated to all delivery partners in monitoring and reporting guidance and during the biannual reporting period (January 2025) and again in the final reporting period for Year 4 (July 2025).

4: Delivery partners must address the SEAH safeguarding risks identified through the SEAH safeguarding self-assessment and demonstrate how they will mitigate these risks.

Progress: Completed. Advanced SEAH training was completed across all ALBs. A SEAH risk analysis was built into the GESI analysis at partnership and thematic level. The SEAH risks identified were fed back to teams and are continuously mitigated for through delivery and transition planning.

Recommendation: Poverty alleviation

5: Delivery partners must ensure they have access to development expertise to improve capacity and capability to integrate poverty alleviation into programme design and delivery.

Progress: Completed.

6: ALB partners should write a narrative that articulates the link between the programme’s bilateral delivery to poverty alleviation.

Progress: In progress.

In Year 4, Access to development expertise in the programme was strengthened through the leadership of an SRO and Tier 1 Programme Director with strong development backgrounds, as well as the mobilisation of NIRAS as MEL delivery partner, the Defra GESI group, and Social Development Direct as GESI expert. This enabled Defra to provide clearer guidance on development expectations and helped delivery partners mobilise expertise to strengthen their delivery.

- In addition, although poverty alleviation has always underpinned the OCPP, it was not embedded explicitly in the programme design from the outset. In Years 1 to 3, the theory of change focused primarily on systemic improvements in institutional capabilities for marine management, with poverty reduction assumed to follow indirectly through benefits to communities dependent on marine resources. This framing was agreed by Defra and ALBs but placed poverty benefits further upup the results chain. In Year 4, a renewed focus on poverty alleviation brought greater need to articulate when and how such outcomes were expected, and to document evidence of short-term change. Defra and ALBs recognised that the programme would have benefitted from integrating poverty alleviation more explicitly from the start, allowing activities to be shaped and embedded alongside these requirements.

7: Defra and OCPP programme leadership should consider exiting from bilateral partnership countries and/or activities. These criteria could include use of newly available evaluation and output data to inform decision-making about where the OCPP can deliver most impact and potential to impact on poverty reduction. Defra and OCPP programme leadership should then consider withdrawing from bilateral partnerships with countries and/or activities where output results are below expectations and/or where traction and engagement is difficult to deliver outputs and where there is limited poverty impact, to engender more focus and less fragmentation and maximise the impact of ALBs’ work. Any changes should consider the programme and country Theory of Change (ToC).

Progress: Completed. Solomon Islands and Vanuatu were selected for completion; however this was delayed due to an earthquake in Vanuatu. Transition documents have been developed with the delivery of transition on track. In addition, ALB Planning Days (January 2024) featured a review of the viable workstreams within each partnership and a selection process to consider which workstreams/activities should be removed from programming.

Recommendation: Strategic focus

8: The ALB’s strategic planning processes for bilateral partnerships need to better integrate the programme and country-level ToC. To strengthen effectiveness and encourage programme teams to aim towards the delivery of long-term change (including on poverty reduction) and a more strategic focus of their work, ALB programme teams need to start actively using the programme ToC in their programme planning and delivery. To ensure a more strategic engagement at country level, ALBs should use the country level ToCs (which are aligned to the OCPP programme level ToC) in their country planning and delivery.

Progress: Completed. In Year 4, delivery teams developed a stronger understanding of the programme’s ToC and how activities contribute to outcomes. ALBs produced Country Progress Reports that set out country-level theories of change, while Country Planning Days encouraged a more strategic approach, helping teams to connect workstreams to longer-term objectives. This has left delivery partners better positioned to assess progress towards common goals. However, this strategic shift has come relatively late in the programme’s implementation, and an earlier understanding would likely have enabled the programme to deliver stronger results.

Recommendation: In-country presence

9: ALB delivery partners to update delivery chain maps and assess whether they can improve their in-country presence e.g. through further use of in-country sub-contracting where appropriate.

Progress: In progress. Delivery chain mapping and procurement pipeline/subcontractor tracker is being used. In addition, IATI reporting underway: Cefas published data for FY24/25 and the goal is to have all ALBs publish their data by end of Q2 for FY24/25 and latest estimate for FY25/26.

Recommendation: Focus on policy change

10: ALB delivery partners need to plan what actions are needed to promote the adoption and use of their policy and guidance recommendations with partner governments and need to invest in and implement policy influencing activities to deliver policy change.

Progress: In progress. Policy integration (outcome and intermediate outcome level) is captured as a priority when reviewing transition plans and continuing workstreams

11: With elections planned in many partners countries in 2024, it is important that the OCPP engages with FCDO Posts and considers the relevance of Political Economy Analyses to assess the likelihood that the planned work will contribute to impact or whether planned programmes of work should be changed.

Progress: Completed. ALBs have been in communication with FCDO on funding plans. In addition the Progress Reports feature a summary on PEA. However, this analysis is not regularly updated, as this was deemed unfeasible as the programme progressed towards closing out in March 2026.

Recommendation: Sustainability and transition planning

12: Delivery partners must consider sustainability within all aspects of delivery planning and implementation.

Progress: Completed. In Year 4, ALBs developed transition plans for all bilateral partnerships (see update below). In addition to delivering transition activities, ALBs also worked on strategies to embed the sustainability of activities and their continuation beyond March 2026. For example,

In Senegal, ALBs secured additional funding to explore sustainable financing options for implementing marine spatial planning and marine protected areas. They contracted Finance Earth to carry out this work, which will produce a roadmap of priority financing mechanisms to be handed over to the government of Senegal.

In Bangladesh, OCPP supported the aquaculture network in applying for funding through the OCEAN fund. Although the application was unsuccessful, partners will reapply with OCPP support in drafting proposals for future opportunities.

In Sri Lanka, OCPP participated in a donor symposium convened by UNDP to showcase programme achievements and identify new avenues of donor support to integrate into transition planning.

Many transition activities are underway in bilateral partnerships. However, with a significant reduction in UK ODA funding, the sustainability of OCPP interventions remains a challenge. Strengthening these efforts into a coherent transition strategy at the country-level will be essential to safeguard the development gains achieved by OCPP.13: ALB delivery partners should develop transition plans for all bilaterial partnerships.

Progress: Completed. In Year 4, ALBs used best practice approaches developed by the MEL partner as a starting point and adapted them to reflect the complexities of each partnership and the different guidance coming from Posts and in-country stakeholders. In May 2025, ALBs ran a half-day workshop with Defra to present transition options, framed as bronze, silver, and gold packages. After the workshop, the teams fully scoped and costed the preferred options within the available ring-fenced budgets. Each partnership will deliver a minimum transition offer that includes:

Fulfilling any MOU criteria specified (if relevant);

Completing assets assessments;

Completing all technical input into a range of products tailored for country, regional, or thematic use, or for bespoke events;

Producing communications products such as infographics, blogs, technical repository content, final summary deliverables, YouTube content, and videos;

Publishing final reports and papers (including open access publication fees);

Handing over all OCPP outputs and assets to key in-country partners, including existing deployments and any regional event;

Preparing and distributing official letters of thanks to key stakeholders, coordinated with BHC;

Submitting detailed handover and lessons learned reports to FCDO/Posts, outlining approaches, opportunities, and future needs.

Facilitating cross-country learning on technical assistance where suitable.

Producing final country reports that summarise activities, highlight deliverables, and document handover details.

Updating and sharing the GESI toolkit and online repository (hosted by Cefas and JNCC).

ALBs are also planning additional activities for each partnership, tailored to each country’s context.

Recommendation: Resourcing in MEL

14: ALB partners should ensure they have access to dedicated MEL resource e.g. via contracting, a new hire or the assignment of this role to existing team.

Progress: Completed. While no provision of dedicated MEL resource (beyond reporting into the logframe) was made within the ALBs, there was a stronger engagement in Year 4 on the MEL monitoring and reporting process. The MEL provider has a clear route to engage with delivery partners and has provided capacity building and learning in MEL for the delivery teams. In Year 4, MEL reporting was on track.

15: Delivery Partner Programme Directors need to ensure delivery teams understand that MEL is foundational to the delivery of the programme and not supplemental.

Progress: Completed. There was a stronger engagement in Year 4 on the MEL monitoring and reporting processes. Overall, all delivery partners improved reporting in Year 4.

16: GOAP needs to explore ways of demonstrating evidence of use of ocean accounts in evidenced-based policy making, to remove constraints in GOAP’s reporting on use of ocean accounts into the OCPP logframe.

Progress: Completed. GOAP worked 1:1 with the MEL provider to ensure a clear understanding of monitoring and reporting. GOAP’s reporting in Year 4 was much stronger and provided clear evidence linked to reported results.

Recommendation: Programme governance

17: Defra programme management should seek to respond to delivery partner queries and decision-making requests within a two-week response time.

Progress: Completed. ALBs consider that there are now good response times from Defra.

18: Defra programme management should review the Defra-ALB MoU to ensure it is up to date, including the ALB delegated authority table to clarify roles, responsibilities and decision-making authority. ALB programme leadership should then ensure clear understanding across OCPP staff. Steers and messaging from Defra should be cascaded to delivery teams to ensure clear understanding.

Progress: Completed. MoU signed April 2025.

19: ALB Tier 1 Delivery Partner Cefas should ensure there are appropriate escalation routes of risks, issues and approvals identified in country level cross theme meetings to Defra country leads.

Progress: Completed. The Tier 1/Tier 2 structure led to a reorganisation of the risk management system for ALBs. In Year 4, risks were first managed at the country-level, discussed at fortnightly cross-ALB meetings, and included in progress reports. Where escalation is required, they were added to the programme-level RAID log. Both Defra and ALBs noted improvements in risk management, with the streamlined approach making the RAID log more practical and easier to use.

20: The ALB annual work planning process should be reviewed to increase efficiency and strategic focus. Aligning with lesson 3, recommendation 1.

Progress: Completed. ALBs held annual work planning days in January 2025 and established Progress Reports to track strategic focus. ALB internal reporting milestone documents require sign off from strategy team members and transition plans are being developed (or already in place).

Recommendation: Risk and issues management

21: Monthly risk meetings between delivery partners and Defra should be implemented immediately to improve the frequency of risks and issues reporting.

Progress: Completed. The RAID log was reviewed during the Planning Session held in January 2025. It has underpinned a monthly meeting with Programme Directors and the Defra Programme Team, and the quarterly Programme Management Board. Regarding GOAP’s risk management, a risk register was created and a new reporting structure was agreed upon. Under this structure, the Risk Lead provides monthly email updates, while high-priority risks are presented and discussed during quarterly meetings.

These counties are: Bangladesh, Belize, Costa Rica, Fiji, Ghana, India, Indonesia, Kenya, Madagascar, Maldives, Mozambique, Namibia, Samoa, Senegal, Solomon Islands, South Africa, Sri Lanka, Tonga, Vanuatu, Vietnam.

Blue Planet Fund - Independent Commission for Aid Impact