## Logframe
PROJECT TITLE | Defra ICF Blue Forests Project
IMPACT | Impact Indicator 1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | 2021 | 2022 | 2023 | Milestone 2024 (Year 8) | Target 2037 (Year 20)
Mangrove forests and ecosystem services (fisheries etc) protected and restored, preventing carbon emissions and supporting security of livelihoods in coastal communities. | Tonnes of CO2 emissions prevented or removed | Original | 0 | Total: 52,620; of which is verified: 0 | Total: 111,493; of which is verified: 0 | Total: 794,734; of which is verified: 0 | Total: 1,473,100; of which is verified: 0 | Total: 2,153,807; of which is verified: 63,594 | 0 | 0 | 0 | 0
|  | Planned | 0 | Total: 54,620 | Total: 111,493 | Total: 149,974 | Total: 432,021 | Total: 432,021 | Total: 668,173 | Total: 1,232,774 | Total: 1,805,263 | 9177844
|  | Achieved |  | Total estimated: 24,378; of which verified: 0 | Total estimated 50,475; of which verified: 0 | Total: 149,974; of which is verified: 0 | 308508 | 432021 | 668173 | 1232774 | 5039928
Source
Forest change analysis will only be done every 5 years (starting in 2015). So until 2020, the unverified figures will be extrapolations based on estimates of effectiveness on the ground.
| Impact Indicator 2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | Milestone 2024 (Year 8) | Target 2037 (Year 20)
| Total number of hectares where deforestation has been avoided (KPI 8) [Note: we have removed degradation from this KPI as it is not possible to measure simply] | Original | 0 | Total: 193; of which is verified: 0 | Total: 888; of which is verified: 0 | Total: 1,366; of which is verified: 0 | Total: 1,831; of which is verified: 0 | Total: 2,282; of which is verified: 174 | Total: 3,152; of which is verified: 343 | Total: 4,000; of which is verified: 508 | N/A | N/A
|  | Planned | 0 | Total: 193; of which is verified: 0 | Total: 380; of which is verified: 0 | Total: 251 | Total: 464 | 606 | 775 | 1003 | 1230 | 3834
|  | Achieved |  | Esimated Total: 43 (Site 1 & Site 2); of which is verified: 0. Can not include Site 3 yet as work not yet started. | Esimated Total: 84 (Site 1 & Site 2); of which is verified: 0. Can not include Site 3 yet as work still in its infancy. | 251 | 487 | 606 | 775 | 1003 | 2413
Source
GIS datsets showing baseline mangrove cover at the start of the intervention and GIS datasets showing current mangrove coverage
| Site 1 - Ambanja |  | 0 | 43 | 84 | 126 | 166 | 206 | 245 | 283 | 438 | 724
| Site 2 - Velondriake |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 125 | 321 | 400 | 479 | 557 | 991 | 1534
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 529 | 831
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 101 | 455 | 745
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | Milestone 2024 (Year 8) | Target 2024 (Year 8)
Improved sustainable mangrove forestry and fisheries management implemented by coastal communities at Blue Forests sites in Madagascar and Indonesia where coastal communities are supported by improved livelihoods and improved access to health care | Ha of mangrove forest area protected or under sustainable local management | Original | 250 | 5700 | 5700 | 8700 | 8700 | 39100 | 39100 | 89100 | - | 89100
|  | Planned | 250 | 5700 | 5700 | 8700 | 9299 | 30407 | 58177 | 77622 | 74395 | 74395
|  | Achieved | 0 | 5,700 ha are now protected. 4,600 of which are under draft management plans and 1,100 of which are secured under Marine Protected Area control. | 6,299 ha are now protected. 5,199 of which are under ratified management plans and 1,100 of which are secured under Marine Protected Area control. | 6,299 ha are now protected. 5,199 of which are under ratified management plans and 1,100 of which are secured under Marine Protected Area control. | 8512 | 30407 | 58402 | 77895 | 75727
Source
BV GIS datasets containing management plans/areas covered by dina and BV GIS datasets showing current (within 5 years) mangrove coverage
| Site 1 - Ambanja |  | 0 | 4,600 ha secured under draft management plans | 5,199 secured under management plans signed by the regional forestry services | 5,199 secured under management plans signed by the regional forestry services | 5199 | 5199 | 6000 | 7330 | 7631 | 6000
| Site 2 - Velondriake |  | 250 | 1,100 ha secured under MPA protection | 1,100 secured under both MPA protection and forestry management legislation | 1,100 secured under both MPA protection and forestry management legislation | 1100 | 1100 | 1100 | 1393 | 1393 | 1100
| Site 3 - Mahajamba |  | 0 | Protection/sustainable management options assessed for Site 3 | Protection/sustainable management options assessed for Site 3 | Management unit defined. Discussions underway with communities around management options | Management unit defined. Official management transfer delayed due to COVID-19 | 5000 | 5225 | 6008 | 6408 | 7000
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | Current management/protection status assessed for potential Site 4 | Current management/protection status assessed for Site 4 | 0 | 0 | 7664 | 7664 | 7664 | 7664 | 7664
| Site 5 - Kubu Raya |  | 0 | Current management/protection status assessed for potential Site 5 | Current management/protection status assessed for potential Site 5 | 0 | 2213 | 11444 | 38413 | 55500 | 52631 | 52631
| Outcome Indicator 1.2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | Milestone 2024 (Year 8) | Target 2024 (Year 8)
| Ecosystem services (KPI 10): Difference in mangrove forest ecosystem services income (shoreline protection; pollution abatement; protection from sedimentation) provided by standing mangroves compared to without project scenario. ($/yr.) | Original | 0 | 65340 | 147361 | 268088 | 386398 | 556503 | 811598 | 1061901 | - | 1061901
|  | Planned | 0 | 65340 | 147361 | 124112 | 207307 | 281680 | 659107 | 754776 | 848122 | 848122
|  | Achieved |  | We can only estimate 65,340 at present. | Estimate still at 147,361 updating figures following final site selection and regional/national figures validated | Estimate still at 124,112 updating figures following final site selection and regional/national figures validated | 281680 | 281680 | 659107 | 754776 | 1581803
Source
Hectares (Impact Indicator 2) will be used to calculate ES via the model developed in the business plan.
| Site 1 - Ambanja |  | 0 | 14452 | 46985 | 79274 | 168552 | 168552 | 449589 | 482568 | 1047580 | 513442
| Site 2 - Velondriake |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 3 - Mahajamba |  | 0 | 50888 | 100376 | 44838 | 113128 | 113128 | 173181 | 202126 | 365301 | 230915
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 0 | 24684 | 49233 | 103647 | 73739
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 11653 | 20849 | 65275 | 30026
| Outcome Indicator 1.3 |  | Baseline | 2017 | 2018 | Milestone 1 (2019 Y3) | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of sites implicated in Fisheries management including but not limited to Fisheries Improvement Projects (registered or actions plans being implemented) | Original | 0 | 0 | 1 | 2 | 2 | 5 | 5 | 6 | - | 6
|  | Planned | 0 | 0 | 1 | 2 | 2 | 5 | 5 | 5 | 5 | 5
|  | Achieved |  | 0 | 2 | 2 | 3 | 4 | 4 | 5 | 5 | 0
Source
Blue Ventures village activity log and FIP action documents
| Site 1 - Ambanja |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - Velondriake |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Outcome Indicator 1.4 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | 2021 | 2022 | 2023 | Milestone 2024 (Year 8) | Target 2037 (Year 20)
| Number of forest dependent people (ASSUMPTION: all people we work with are forest dependent) with livelihoods benefits (INCOME GENERATION AND FOOD SECURITY) protected or improved (KPI 3) | Original | 28,300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | 28,300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | Improved understanding of livelihood benefits in TH (4,542) and measurement criteria/methods for other sites | Improved understanding of livelihoods benefits in AB and TH (29,893). Census and baselines in Maha established. | Improved understanding of livelihoods benefits at 3 sites. Census and baselines in Indo established. Number of people estimated: 35,000 | Census and baselines in Indo established. Number of people estimated: 63,000 | Number of people estimated: 82,000 | 91659 | - | 119649
|  | Planned | 28,300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | 28,300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | Improved understanding of livelihood benefits in TH (4,542) and measurement criteria/methods for other sites | Improved understanding of livelihoods benefits in AB and TH (29,893). Census and baselines in Maha established. | Improved understanding of livelihoods benefits at 3 sites. Census and baselines in Indo established. Number of people estimated: 33,000 | Census and baselines in Indo established. Number of people estimated: 58,000 | Number of people estimated: 66,884 | Number of people estimated: 68,116 | Number of people estimated: 69,380 | Number of people estimated: 93,969
|  | Achieved |  | Baseline intake assessments for alternative livelihood projects developed, and population baselines established across the Velondriake LMMA (TH) against which project level benefits may be compared. | Baseline intake assessments for alternative livelihood project participants underway. Baseline for Velondriake; HH weekly income MGA/Week or $90.48 PPP; $2.72 (PPP) per person, per day | 29,893 - Census and baseline established in Site 3. | 32,855 (census being updated in site 1 in 2021, Site 4 work yet to start awaiting partnership agreement with Government) | 62967 | 69742 | 71297 | 77302
Source
Activity beneficiary data, local census data where available and reliable, or BV census data where necessary. Integrated social surveys will be carried out at each site every 5 years.
| Site 1 - Ambanja |  | 0 | 0 | 0 | 25351 | 25351 | 25351 | 30896 | 32281 | 36401 | 41508
| Site 2 - Velondriake |  | 0 | 0 | 4542 | 4542 | 4542 | 4542 | 4542 | 4533 | 4533 | 7437
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 2962 | 2962 | 2894 | 2954 | 4839 | 8647
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 11268 | 11268 | 11268 | 11268 | 12659
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 18844 | 20142 | 20261 | 20261 | 23617
| Outcome Indicator 1.5a |  | Baseline | 2017 | 2018 | Milestone 1 (2019 Y3) | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| % of active producers making agreed model profit from alternative activity | Original | 10% in Site 2 | 10% in Site 2 | 6.6667 | 16.6667 | 30 | 46.6667 | 46.6667 | 60 | - | 60
|  | Planned | 10% in Site 2 | 10% in Site 2 | 6.6667 | 16.6667 | 16 | 23.24 | 23.2 | 27 | 33 | 33
|  | Achieved |  | 10% in Site 2 | First sales due in October 2018 all figures to be updated with final sales data | 20.18 | 23.2 | 23 | 13.79 | 16 | 64.6
Source
Blue Ventures farmers log and sales data
| Site 1 - Ambanja |  | 0 | 0 | 0 | 0 | 53 | 71 | 31.25 | 68 | 100 | 40
| Site 2 - Velondriake |  | 10.67 | 10 | 10 | 40.35 | 63 | 45.2 | 37.7 | 6 | 44 | 45
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 40
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 66 | 20
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 20
| Outcome Indicator 1.5b |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Average savings per group member in monitored groups ($) (by gender) | Original
|  | Planned | [8 empty] | 71.5 | 71.5
|  | Achieved | [8 empty] | 41.48
| Site 1 - Ambanja | [9 empty] | 18 | 100
| Site 2 - Velondriake | [9 empty] | 67 | 100
| Site 3 - Mahajamba | [9 empty] | 32 | 40
Site 4 - Inhil
| Site 5 - Kubu Raya | [9 empty] | 48.92 | 46
| Outcome Indicator 1.6 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Milestone 2024 (Year 8) | Target 2024 (Year 8)
| % of health service delivery points that provide support and /or referral appropriate to meet the needs of Blue Forest programme communities | Original | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | Planned | [6 empty] | 58.8822 | 71 | 77.476 | 77.476
|  | Achieved | [5 empty] | 39.6032 | 62.48 | 75 | 74.8
Source
Service delivery point survey
| Site 1 - Ambanja | [6 empty] | 64.5161 | 89.2 | 95 | 87 | 85
| Site 2 - Velondriake | [6 empty] | 67.5 | 59.5 | 51 | 74 | 59.46
| Site 3 - Mahajamba | [6 empty] | 25 | 84.6 | 71 | 46 | 84.62
| Site 4 - Sembilang National Park / Inhil: 2022 onwards | [6 empty] | 0 | 33.3 | 67 | 75 | 75
| Site 5 - Kubu Raya | [6 empty] | 41 | 45.8 | 92 | 92 | 83.3
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | Milestone 2024 (Year 8) | Target 2024 (Year 8)
Validated implementation models for replication provided to coastal communities in other geographic locations | Extent to which ICF intervention is likely to have a transformational impact (KPI 15): Number of additional sites adopting models tested and proved within this project (outside of 5 sites) | Original | 6 | 10 | 12 | 16 | 20 | 23 | 26 | 29 | - | 29
|  | Planned | 27 | 35 | 40 | 57 | 72 | 78 | 78 | 89 | 99 | 99
|  | Achieved |  | 38 | 44 | 60 | 102 | 117 | 120 | 147 | 167
Source
BV partner support database and tracking system
| PHE model |  | 6 | 10 | 11 | 14 | 14 | 17 | 10 | 19 | 13 | 22
| Octopus model |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| FIP |  | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 8 | 4
| Closure |  | 21 | 28 | 32 | 43 | 83 | 96 | 106 | 117 | 142 | 70
| Mangrove crab model |  | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1
| Sea cucumber model |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0
| VCS model |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| Plan Vivo model |  | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1
| Bee keeping model |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0
| Homestay model |  | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | 2024 | Target 2024 (Year 8) | Assumptions* | * Assumptions to be reviewed in Programme Closure Review due December 2025
Sustainable community owned mangrove forestry management plans in place | Number of sites with community-led mangrove management plans | Original | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 5 | - | 5 | Community benefit from carbon payments or other ecosystem services and uphold management plans which include protection of mangroves, reducing deforestation/degradation - If management plans are in place and followed communities will be clear on the activities that need to be undertaken to acheive improved management
|  | Planned | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 5 | 5 | 5
|  | Achieved |  | 2 | 2 | 3 | 4 | 5 | 5 | 5 | 5
Source
| Site 1 - Ambanja |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - Velondriake |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Output Indicator 1.2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of sites with an estimated carbon baseline scenario | Original | 1 | 1 | 1 | 3 | 3 | 4 | 4 | 5 | - | 5
|  | Planned | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 4 | 5 | 5
|  | Achieved |  | 1 | 1 | 3 | 4 | 3 | 3 | 4 | 5
IMPACT WEIGHTING % |  |  | Source
30% | Site 1 - Ambanja |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - Velondriake |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | 2024 | Target 2024 (Year 8) | Assumptions*
Mangrove fisheries improvement projects in place | Number of fisheries being monitored | Original | 5 | 5 | 6 | 7 | 8 | 8 | 9 | 9 | - | 9 | - Fisheries Improvement Project accrues benefits to fishers (through increased catch rates, price or improved access to market) ensuring buy-in to managment/ improvement project. - FIP includes advisory on habitat management specific to mangroves. - FIP also reinforces local governance structures that may manage both mangroves and fisheries in one management plan.
|  | Planned | 5 | 5 | 6 | 7 | 9 | 9 | 10 | 10 | 10 | 10
|  | Achieved |  | 5; plus Fisheries Diagnostic started at Site 2 | 8; diagnostic to be completed once sites selected in 2018 | 9 | 9 | 11 | 10 | 12 | 12
Source
| Site 1 - Ambanja |  | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 4 (Fish, Crab, Sea cucumber and Shrimp) | 4 (Fish, Crab, Sea cucumber and Shrimp) | 3 (Fish, Crab and Sea cucumber)
| Site 2 - Velondriake |  | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish)
| Site 3 - Mahajamba |  | 0 | Fisheries diagnostic started | 3 (Fish, Crab and Shrimp) | 3 (Fish, Crab and Shrimp) | 3 (Fish, Crab and Shrimp) | 3 (Fish, Crab and Shrimp) | 3 (Fish, Crab and Shrimp) | 3 (Fish, Crab and Shrimp) | 3 (Fish, Crab and Shrimp) | 3 (Fish, Crab and Shrimp)
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | Fisheries diagnostics started | Fisheries diagnostic underway | Fisheries diagnostic ongoing | 1 (Crab) | 1 (Crab) | 2 (Crab and Shrimp) | 2 (Mudcrab and Shrimp) | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 1 (Crab) | 1 (Crab) | 2 (Crab, Finfish) | 1 (Crab) | 1 (mangrove crab) | 1 (mangrove crab) | 1 (mangrove crab)
| Output Indicator 2.2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of sites trialling/pilot locally relevant fisheries management (e.g. periodic closures, gear restrictions) | Original | 1 | 1 | 2 | 2 | 3 | 5 | 5 | 5 | - | 5
|  | Planned | 1 | 1 | 2 | 3 | 3 | 4 | 5 | 5 | 5 | 5
|  | Achieved |  | 1 | 2 | 3 | 4 | 4 | 4 | 4 | 5
Source
| Site 1 - Ambanja |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - Velondriake |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Output Indicator 2.3 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of local fisheries management plans developed (eg. Agreed harvest rules concerning a fishery or wider management contracts) | Original | 0 | 0 | 0 | 2 | 2 | 3 | 4 | 5 | - | 5
|  | Planned | 0 | 0 | 0 | 2 | 2 | 3 | 4 | 5 | 5 | 5
|  | Achieved |  | 2 in development | 1 developed in Site 1 validated by all 36 communities | 2 | 2 | 2 | 4 | 5 | 6
IMPACT WEIGHTING % |  |  | Source
25 | Site 1 - Ambanja |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - Velondriake |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
OUTPUT 3 | Output Indicator 3.1a |  | Baseline | 2017 | Milestone 1 (2018 Y2) | 2019 | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | 2024 | Target 2024 (Year 8) | Assumptions*
Implementation of improved livelihood mechanisms | Number of people engaged in alternative livelihoods | Original | 336 | 336; Sea cucumber farming developed in Site 1 | 798.95 | 982.6 | 1762.85 | 2543.1 | 3888.8 | 5234.5 | - | 5234.5 | - New livelihoods provide income to communities - New livelihoods provide sufficient income to reduce reliance on fishing
|  | Planned | 336 | 336; Sea cucumber farming developed in Site 1 | 799 | 983 | 886 | 991 | 1056 | 1178 | 744 | 744
|  | Achieved |  | 292 (8 beekeepers; 78 sea cucumber farmers; 212 seaweed farmers) | 506 | 691 | 848 | 1036 | 1015 | 1161 | 910
Source
| Site 1 - Ambanja |  | 8 | 8 | 70 | 80 | 17 | 14 | 16 | 68 | 48 | 16
| Site 2 - Velondriake |  | 328 | 290 | 436 | 611 | 831 | 914 | 954 | 870 | 517 | 370
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 100
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 208 | 150
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 108 | 45 | 91 | 110 | 108
| Output Indicator 3.1b |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of people engaged in monitored savings and loans groups (VSLA) (by gender) | Original
|  | Planned | [8 empty] | 3378 | 3378
|  | Achieved | [8 empty] | 3171
| Site 1 - Ambanja | [9 empty] | 1197 | 1190
| Site 2 - Velondriake | [9 empty] | 655 | 655
| Site 3 - Mahajamba | [9 empty] | 258 | 474
| Site 4 - Inhil | [9 empty] | 0 | 0
| Site 5 - Kubu Raya | [9 empty] | 1061 | 1059
| Output Indicator 3.2a |  | Baseline | 2017 | 2018 | 2019 | 2020 | Milestone 2 (2021 Year 5) | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Total income generated ($) | Original | 0 | 13776 | 53631.9 | 122690.4 | 281425.2 | 530670 | 783774.6 | 1319094 | - | 1319094
|  | Planned | 0 | 13776 | 53631.9 | 122694.4 | 152003 | 155044 | 94459 | 120675 | 45710 | 45710
|  | Achieved |  | $250 (beekeepers); $23,853 (seaweed). | 25782 | 116929.6093 | 137659 | 95208 | 74094 | $59,877 | 83920
Source
| Site 1 - Ambanja |  | 0 | 250 | 500 | 475.6093 | 1097 | 1543 | $1,024 | $1,264 | 677 | 1024
| Site 2 - Velondriake |  | 0 | 23853 | 25282 | 116454 | 136562 | 93665 | $73,070 | $58,522 | 69941 | 29000
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 0 | 0 | $0 | 0 | 1142 | 4000
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 0 | $0 | $91 | 4979 | 4200
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | $0 | 0 | 7181 | 7486
| Output Indicator 3.2b |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Total cumulative savings in monitored groups ($) | Original
|  | Planned | [8 empty] | 252219 | 252219
|  | Achieved | [8 empty] | 125320
| Site 1 - Ambanja | [9 empty] | 21541 | 119000
| Site 2 - Velondriake | [9 empty] | 43715 | 65500
| Site 3 - Mahajamba | [9 empty] | 8164 | 18960
| Site 4 - Inhil | [9 empty] | 0 | 0
| Site 5 - Kubu Raya | [9 empty] | 51900 | 48759
| Output Indicator 3.3a |  | Baseline | 2017 | 2018 | Milestone 1 (Y3 2019) | 2020 | Milestone 2 (Year 5 2021) | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of new alternative livelihoods developed by site (cumulative) | Original | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 6 | 8 | 9 | 9 | 9 | - | 9
|  | Planned | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 6 | 7 | 8 | 7 | 11 | 17 | 17
|  | Achieved |  | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 4 | 7 | 10 | 10 | 17 | 20
Source
| Site 1 - Ambanja |  | 1 in development (bee keeping) | 1 in development (bee keeping) | 1 in progress (Bees), 1 in development (SC) | 1 in progress (Bees), 1 in development (SC) | 2 | 4 | 2 | 3 | 4 | 3
| Site 2 - Velondriake |  | 2 (SC, SW) | 2 (SC, SW) | 2 in progress (SC, SW), 1 in development (Bees) | 3 (SC, SW, Bees) | 4 (SC, SW, Bees and Meals) | 4 | 4 | 4 | 5 | 4
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 4 | 4
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 5 | 6 | 5
| Output Indicator 3.3b(i) |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of savings and loans groups (VSLA) established (cumulative) | Original
|  | Planned | [8 empty] | 160 | 160
|  | Achieved | [8 empty] | 160
| Site 1 - Ambanja | [9 empty] | 49 | 49
| Site 2 - Velondriake | [9 empty] | 80 | 80
| Site 3 - Mahajamba | [9 empty] | 21 | 21
| Site 4 - Inhil | [9 empty] | 0 | 0
| Site 5 - Kubu Raya | [9 empty] | 10 | 10
| Output Indicator 3.3b(ii) |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of monitored savings and loans groups (VSLA) | Original
|  | Planned | [8 empty] | 113 | 113
|  | Achieved | [8 empty] | 105
| Site 1 - Ambanja | [9 empty] | 45 | 49
| Site 2 - Velondriake | [9 empty] | 33 | 33
| Site 3 - Mahajamba | [9 empty] | 17 | 21
| Site 4 - Inhil | [9 empty] | 0 | 0
| Site 5 - Kubu Raya | [9 empty] | 10 | 10
| Output Indicator 3.3c(i) |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of new approaches to value chain improvement implemented/piloted (cumulative) | Original
|  | Planned | [8 empty] | 9 | 9
|  | Achieved | [8 empty] | 11
| Site 1 - Ambanja | [9 empty] | 4 | 3
| Site 2 - Velondriake | [9 empty] | 3 | 3
| Site 3 - Mahajamba | [9 empty] | 3 | 3
| Site 4 - Inhil | [9 empty] | 0 | 0
| Site 5 - Kubu Raya | [9 empty] | 1 | 0
| Output Indicator 3.3c(ii) |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of value chain assessments completed (cumulative) | Original
|  | Planned | [8 empty] | 18 | 18
|  | Achieved | [8 empty] | 19
IMPACT WEIGHTING %
25 | Site 1 - Ambanja | [9 empty] | 2 | 2
| Site 2 - Velondriake | [9 empty] | 2 | 2
| Site 3 - Mahajamba | [9 empty] | 2 | 2
| Site 4 - Inhil | [9 empty] | 1 | 1
| Site 5 - Kubu Raya | [9 empty] | 12 | 11
OUTPUT 4 | Output Indicator 4.1 A |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8) | Assumptions*
Increased access to health services | Number of women accessing sexual and reproductive health and rights services (Mada only) | Original | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | Planned | [6 empty] | 9752 | 10600 | 12721 | 12721
|  | Achieved | [5 empty] | 8480 | 12819 | 9955 | 11346
Source
| Site 1 - Ambanja | [6 empty] | 3773 | 7634 | 6901 | 6524 | 5660
| Site 2 - Velondriake | [6 empty] | 3335 | 4551 | 2393 | 4221 | 5003
| Site 3 - Mahajamba | [6 empty] | 1372 | 634 | 661 | 601 | 2058
| Output Indicator 4.1 B |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of outpatient consultations (Indo only) | Original | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | Planned | [6 empty] | 1034 | 1239 | 1314 | 1314
|  | Achieved | [5 empty] | 641 | 1220 | 1888 | 1442
Source
| Site 4 - Inhil | [6 empty] | 0 | 256 | 395 | 567 | 150
| Site 5 - Kubu Raya | [6 empty] | 641 | 964 | 1493 | 875 | 1164
| Output Indicator 4.2 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of people attending community health sessions or health promotion activities | Original | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | Planned | [6 empty] | 10218 | 12324 | 12374 | 12374
|  | Achieved | [5 empty] | 8204 | 12030 | 16512 | 16517
Source
| Site 1 - Ambanja | [6 empty] | 2829 | 6705 | 9934 | 9270 | 6705
| Site 2 - Velondriake | [6 empty] | 3976 | 2318 | 4229 | 4435 | 2318
| Site 3 - Mahajamba | [6 empty] | 1258 | 2279 | 1382 | 1939 | 2279
| Site 4 - Inhil | [6 empty] | 0 | 256 | 203 | 286 | 200
| Site 5 - Kubu Raya | [6 empty] | 141 | 472 | 764 | 587 | 872
| Output Indicator 4.3 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Number of healthcare workers or community health ambassadors who report improved skills and knowledge in health delivery | Original | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | Planned | [6 empty] | 211 | 259 | 274 | 274
|  | Achieved | [5 empty] | 123 | 207 | 259 | 290
IMPACT WEIGHTING (%) |  |  | Source
10 | Site 1 - Ambanja | [6 empty] | 28 | 33 | 34 | 38 | 34
| Site 2 - Velondriake | [6 empty] | 38 | 34 | 35 | 35 | 34
| Site 3 - Mahajamba | [6 empty] | 12 | 10 | 13 | 12 | 10
| Site 4 - Inhil | [6 empty] | 0 | 20 | 44 | 72 | 50
| Site 5 - Kubu Raya | [6 empty] | 45 | 110 | 133 | 133 | 146
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8) | Assumptions*
Organisational and financial structures in place to support 20 year project vision | Organisational capacity - number of relevant community structures (organisational/financial/administrative) in place to support local mangrove and fisheries management | Original | 2 | 2 | 3 | 3 | 5 | 5 | 5 | 5 | - | 5 | By having clear community led organisational and financial strutures both mangrove and fisheries management plans are supported, and more likely to be sustained in the long term beyond the scope of this funding.
|  | Planned | 2 | 2 | 3 | 2 | 3 | 3 | 23 | 23 | 23 | 23
|  | Achieved |  | 2 Site 1 Madagascar - 1 Federation officialised to coordinate the mangrove and fisheries management activities of the 11 associations. Site 2 Madagascar - 1 management association in place to manage mangrove and marine conservation in the project area. | 2 Site 1 Madagascar - 1 Federation officialised to coordinate the mangrove and fisheries management activities of the 11 associations. Site 2 Madagascar - 1 management association in place to manage mangrove and marine conservation in the project area. | 2 but discussions underway for establishment in site 3 | 15 Site 1 - Federation (11 associations) Site 2 - 1 management association Site 3 - 7 community associations Site 4 - awaiting agreeement Site 5 - 6 Lembaga Pengelola Hutan Desa (Village forest management body) | 18 | 27 | 26 | 31
Source
| Site 1 - Ambanja |  | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 7 | 1
| Site 2 - Velondriake |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 7 | 7 | 9 | 9 | 12 | 9
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 6 | 5 | 8 | 7 | 7 | 8
| Output Indicator 5.2 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Monitoring capacity - number of sites where community resource monitoring protocol is in place | Original | 0 | 1 | 2 | 2 | 5 | 5 | 5 | 5 | - | 5
|  | Planned | 0 | 1 | 2 | 3 | 4 | 4 | 5 | 5 | 5 | 5
|  | Achieved |  | Site 2 Madagascar - Protocol and key indicators to be monitored have been defined. Recruitment ongoing and training starting by end of Q4 2017. | 2 CSE being trialled in TH, forest guards officalised in AAB | 3 | 3 | 5 | 5 | 5 | 5
Source
| Site 1 - Ambanja |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - Velondriake |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Output Indicator 5.3 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Enforcement capacity - number of sites where a community-led coastal management law enforcement protocol is in place | Original | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 6 | - | 6
|  | Planned | 1 | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 5 | 5
|  | Achieved |  | Site 2 Madagascar - Enforcement committee and enforcement procedure in place. | 2 Site 2 Madagascar - Enforcement committee and enforcement procedure in place. Forest guards in place in Site 1 Madagascar | 2 | 4 | 4 | 5 | 5 | 5
Source
| Site 1 - Ambanja |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - Velondriake |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Output Indicator 5.4 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | 2024 | Target 2024 (Year 8)
| Conservation agreements - number of sites with functioning, transparent community conservation agreements | Original | 0 | 0 | 2 | 2 | 5 | 5 | 5 | 5 | - | 5
|  | Planned | 0 | 0 | 2 | 3 | 4 | 4 | 5 | 5 | 5 | 5
|  | Achieved |  | No agreements in place yet, although a pilot, based around mangrove reforestation, is being designed at Site 1. | 2 1 signed on mangrove carbon project, a second in development for aquaculture leasing agreements | 3 (Site1 restoration, Site 2 Aquaculture and Carbon project) | 3 | 4 | 4 | 5 | 5
IMPACT WEIGHTING (%) |  |  | Source
10 | Site 1 - Ambanja |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - Velondriake |  | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
| Site 3 - Mahajamba |  | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 1 | 1
| Site 4 - Sembilang National Park / Inhil: 2022 onwards |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 1 | 1
OUTPUT 6 | Output Indicator 6.1 |  | Baseline | 2017 | Milestone 1 (2018, Y2) | 2019 | 2020 | Milestone 2 (2021, Year 5) | 2022 | 2023 | 2024 | Target 2024 (Year 8) | Assumptions*
Increased evidence base for conservation models | Number of new pieces of evidence (per year) for individual conservation models (eg. crab fishery closure model, Plan Vivo model) | Original | 0 | 2 | 2 | 2 | 5 | 4 | 5 | 5 | - | 5
|  | Planned | 0 | 2 | 2 | 2 | 5 | 4 | 5 | 5 | 5 | 5
|  | Achieved |  | Results from the models have been analysed and we have additional understanding (“new pieces of evidence”) from which to replicate work. [Crab and Health] | PDD for TH, manuscript on sea cucumber model, 3 theses dissertations on sea cucumber model from UoE, draft crab manuscript on effectiveness of periodic crab closures, ISS paper = Number completed, vs number pending | 7 FIP pre-assessment report published by MSC, PDD for TH, Crab good pratice guide (Kasprzyk and Levrel 2019), peer-reviewed paper on participatory mangrove management (Rakotomahazo et al 2019), MMM5 poster on Ambanja soil carbon, Evaluation of health integration (Singleton et al 2019) Others - Accepted 2019: The role of PHE in the response to cyclone Haruna in Madagascar In review 2019: AAB soil carbon paper | 5 peer reviewed papers (losses of soil organic carbon, reef fish biomass recovery, overfishing in small-scale fisheries, Lessons learned in Velondriake, and Google Earth Engine Mangrove Mapping tool), 2 technical reports (fish smoking factsheet and sandfish farming manual), 1 case study in FAO report (mud crab fishery), and three sections accepted in marine chapter of Natural History of Madagascar book (seagrass, mangroves and coral reefs) | 6 | 5 | 4 | 2
IMPACT WEIGHTING (%) |  |  | Source
0 | Octopus FIP model |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1
| Mangrove crab model |  | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1
| Sea cucumber model |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
| VCS model |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1
| Plan Vivo model |  | 0 | 0 | 1 | 2 | 1 | 1 | 1 | 4 | 0 | 1
| HE integration |  | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0