CHANGE CONTROL NOTICE

| Change Control Notice number: | CCN001 |
| --- | --- |
| Grant Funding Agreement title: | Global Ocean Accounts Partnership Yr2-4 |
| Reference: | Ecm_66200 |
| Variation title: | Expanded activities during Blue Planet Fund (BPF) Phase 2 |
| Number of pages attached: | 3 |

WHEREAS the Grant Recipient and the Authority entered into a Grant Funding Agreement for the Approved Project dated  (the "Original Grant Funding Agreement") and now wish to amend the Original Grant Funding Agreement

IT IS AGREED as follows

- CHANGES

  - With effect from the Original Grant Funding Agreement shall be amended as set out in this Change Control Notice:

| Change requestor/originator: |  |
| --- | --- |
| Summary and reason for change: | Additional related activities to be completed within FY22/23 in accordance with the planning note at Annex A, which should be added to Schedule 2 in its entirety. Required to target capacity building and planning for multi-country development of the ‘low-level’ data systems on which accounts are built. Proposed activities and budget; Activity; Budget (£); Milestone. A1. Establishing spatial data framework and specification for ocean accounting; , submission o framework and invoice. A2. Development of regional implementation plan for the spatial data framework coverin all ODA-eligible Pacific Island Countries.; g; submission o implementation plan an invoice. |
| Original Grant Funding: Additional Grant Funding: | £6,000,000.00 £200,000.00 |
| Revised Total Grant Funding: | £6,200,000.00 |
| Revised Agreed Outputs | See Schedule 3 – Agreed Outputs and Long Term Outcomes |
| Revised payment schedule: | See Schedule 5-Revised Payment Schedule |
| Original Grant Funding Period: | 01/07/2022 – 31/03/2025 |
| Other change: (e.g. change of grant manager) | Additional condition and definition to be added to the Grant Agreement in relation to Branding as follows; Insert Definition to Condition 2 Definitions and Interpretation: “Branding Manual means the HM Government of the United Kingdom of Great Britain and Northern Ireland Branding Manual Funded by UK Government first published by the Cabinet Office in November 2022, and is available at https://gcs.civilservice.gov.uk/guidance/marketing/brandingguidelines/ , including any subsequent updates from time to time.” Insert Condition 35: “35. Branding 35.1 The Grant Recipient shall at all times during and following the end of the Funding Period: - comply with requirements of the Branding Manual https://gcs.civilservice.gov.uk/guidance/marketing/brandingguidelines/ in relation to the Funded Activities; and - cease use of the Funded by UK Government logo on demand if directed to do so by the Authority.” |

  - Save as herein amended all other terms and Conditions of the Original Grant Funding Agreement shall remain in full force and effect.

Please confirm your acceptance of this CCN by electronically signing this document using the Authority’s e-tendering system within 7 days from the date of this letter. Please remember to quote the reference number above in any future communications relating to this grant. All communications should be made using the messaging section in the e-tendering grant record.

| I confirm the agreement of Unive of New South Wales to the term and conditions in this Change Co Notice and its Schedules |  | rsity s ntrol |  | Accepted on Behalf of the Authority |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Grant-Recipient-Signature anchor for docusign] | [text |  |  | Authority-Signature [ for docusign] | text anchor |  |
| Full Name: Job Title/Role: Secretariat Dir |  | ector |  | Full Name: Job Title/Role: Category Lead |  |  |

Date Signed:		Date Signed:

Schedule 3 – Table 1

Delete Table 1 Milestone Deliverables – in its entirety

Insert:

Table 1 – Agreed Outputs

Table 1 is an indicative timetable of outputs, which can be varied with agreement from the Grant Manager

| 2 | End Q2 (November 2022) |  | - O1.1 Prepare a consultation plan and develop a consultation draft OA Country Delivery Plan for new in-country pilots, aligned to OCPP country plans. - O1.2 Prepare a consultation plan and develop a consultation draft OA Country Delivery Plan for continuing pilots, aligned to OCPP Country Delivery plans. - O2.1 Prepare a consultation plan and develop consultation draft Communities of Practice and Capacity Support Plans for Asia-Pacific, Africa, Americas, including communication, capacity building and outreach components - O2.2 Draft terms of reference for Ocean Accounting Fellowships / Training Opportunities - O3.2 Develop a discussion draft Knowledge Production Needs Statement / Research Agenda - O4.1 Co-develop a draft Collaboration Plan with the OCPP and Blue Planet Fund programme staff - O4.2 Co-develop a draft Regionalisation and Mainstreaming Collaboration Plans for Asia-Pacific, Pacific, Africa, Americas, including: - collaboration with development finance institutions, regional oceans governance mechanisms, bilateral development programs, and other initiatives as appropriate). - advisory support for “Mainstreaming Pilots” see above. |
| --- | --- | --- | --- |
| 3 | End Q3 (January 2023) |  | - O1.2 Finalise OA Country Delivery Plan for continuing pilots, aligned to OCPP Country Delivery plans. - O2.1 Co-develop Communities of Practice and Capacity Support Plans for Asia-Pacific, Africa, Americas, including communication, capacity building and outreach components - O2.2 Publish Ocean Accounting Fellowships / Training Opportunities - O3.2 Finalise and publish Knowledge Production Needs Statement / Research Agenda; and develop early consultation draft technical papers for the most urgent needs. - O4.1 Finalise the co-developed Collaboration Plan with the OCPP and Blue Planet Fund programme staff - O4.2 Finalise the co-developed Regionalisation and Mainstreaming Collaboration Plans for Asia-Pacific, Pacific, Africa, Americas. |
| 4 | End Q4 (March 2023) |  | - O1.1 Activities and outcomes report for new-country pilots, focusing on technical accounting progress and policy / practice impacts, including updated ocean accounts and associated policy / practice outcomes. - O1.2 Activities and outcomes report for continuing country pilots, focusing on technical accounting progress and policy / practice impacts, including updated ocean accounts and associated policy / practice outcomes. - O2.1 Activities and outcomes report for Communities of Practice and Capacity Support, including final event documentation and reporting. - O2.2 Activities and outcomes report for Ocean Accounting Fellowships / Training Opportunities, including detailed capacity outcomes statement. |

|  |  |  | - O2.3 Host Regional Dialogues through GOAP regional Communities of Practice (physical in-person events). - O3.1 - O3.1 Meeting report for Global Policy Advisory Panel, including recommendations for Year 2. - O3.2 Final technical papers addressing knowledge gaps identified in Knowledge Products Needs Statement / Research Agenda, and annual revision to GOAP Technical Guidance - O4.1 Activities and outcomes report for OCPP Collaboration Plan, including impact/outcome assessment - O4.2 Activities and outcomes report for Regionalisation and Mainstreaming Collaboration Plans, including impact/outcome assessment - A1 Establishing spatial data framework and specification for ocean accounting - A2 |
| --- | --- | --- | --- |
| Years 2-3 (same milestones for each year) |  |  |  |
| 1 | End Q1 (June) |  | Informed by Year 1 Evaluation and Recommendations from Policy Advisory Panel: - O1.1 Co-develop Country Delivery Plan for new in-country pilots. - O1.2 Revised Country Delivery Plan for continuing pilots. - O2.1 Revised Communities of Practice and Capacity Support Plans for Asia-Pacific, Africa, Americas, including communication, capacity building and outreach components - O2.2 Re-publish Ocean Accounting Fellowships / Training Opportunities (if required) - O2.4 Host Annual Global Dialogue on Ocean Accounting (tentative Defra) (tentatively hybrid in-person/online, with fallback exclusively online likely in 2023). - O3.2 Publish Revised Knowledge Production Needs Statement / Research Agenda (annex to public Global Dialogue Report below) - O4.3 Publish formal outcome report and action agenda from GOAP Global Dialogue, including revised Collaboration Plans (see O4.1 / 4.2 from Year 1 Milestone 1) |
| 2 | End Q2 (September) |  | - O1.1 Activities and outcomes report for new-country pilots, focusing on technical accounting progress and policy / practice impacts. - O1.2 Outcomes report for continuing country pilots, focusing on technical accounting progress and policy / practice impacts. - O2.1 Activities and outcomes report for Communities of Practice and Capacity Support - O2.2 Activities and outcomes report for Ocean Accounting Fellowships / Training Opportunities - O3.1 Meeting report for Global Expert Panel. - O3.2 Consultation draft technical papers addressing knowledge gaps identified in Knowledge Products Needs Statement / Research Agenda - O4.1 Activities and outcomes report for OCPP Collaboration Plan • O4.2 Activities and outcomes report for Regionalisation and Mainstreaming Collaboration Plans. |
| 3 | End Q3 (December) |  | - O1.1 Activities and outcomes report for new-country pilots, focusing on technical accounting progress and policy / practice impacts. - O1.2 Outcomes report for continuing country pilots, focusing on technical accounting progress and policy / practice impacts. - O2.1 Activities and outcomes report for Communities of Practice and Capacity Support - O2.2 Activities and outcomes report for Ocean Accounting Fellowships / Training Opportunities - O3.2 Revised draft technical papers addressing knowledge gaps identified in Knowledge Products Needs Statement / Research Agenda - O4.1 Activities and outcomes report for OCPP Collaboration Plan - O4.2 Activities and outcomes report for Regionalisation and Mainstreaming Collaboration Plans. |
| 4 | End Q4 (March) |  | - O1.1 Activities and outcomes report for new-country pilots, focusing on technical accounting progress and policy / practice impacts, including updated ocean accounts and associated policy / practice outcomes. - O1.2 Outcomes report for continuing country pilots, focusing on technical accounting progress and policy / practice impacts, including updated ocean accounts and associated policy / practice outcomes. - O2.1 Activities and outcomes report for Communities of Practice and Capacity Support, including final event documentation and reporting. - O2.2 Activities and outcomes report for Ocean Accounting Fellowships / Training Opportunities, including detailed capacity outcomes statement. - O2.3 Host Regional Dialogues through GOAP regional Communities of Practice (physical in-person events). - O2.4 Host Annual Global Dialogue on Ocean Accounting. - O3.1 Meeting report for Global Policy Advisory Panel, including recommendations for future action. - O3.2 Final technical papers addressing knowledge gaps identified in Knowledge Products Needs Statement / Research Agenda - O4.1 Activities and outcomes report for OCPP Collaboration Plan, including impact/outcome assessment - O4.2 Activities and outcomes report for Regionalisation and Mainstreaming Collaboration Plans, including impact/outcome assessment |

Schedule 5

REVISED PAYMENT SCHEDULE

Please note this grant is subject to review each financial year.

| Milestone | Amount of Grant Funding Payable | Expected date of invoice |
| --- | --- | --- |
| Year 1 |  |  |
| 1 |  | November 2022 |
| 2 |  | January 2023 |
| 3 |  | March 2023 |
| Year 2 |  |  |
| 1 |  | June 2023 |
| 2 |  | September 2023 |
| 3 |  | December 2023 |
|  |  | March 2024 |
| Year 3 |  |  |
| 1 |  | June 2024 |
| 2 |  | September 2024 |
| 3 |  | December 2024 |
| 4 |  | March 2025 |
| Total | £6,000,000 | No later than 31st March 2025 |

Annex A – Planning note to be added to Schedule 2 in its entirety.

Page 8 of 8

28-Feb-23 ECM_66200