CONTRACT CHANGE NOTE

| Contract Change Note Number | CCN03 |
| --- | --- |
| Contract Reference Number and Title | Global Ocean Accounts Partnership Years 2-4 |
| Variation Title | CCN03 |
| Number of Pages | 4 |

The Supplier, University of New South Wales, and the Buyer, DEFRA, entered a Contract for the provision of the Global Ocean Accounts Partnership dated and now wish to amend the Original Contract.

It is agreed as follows:

- With effect from the Original Contract shall be amended as set out in this Contract Change Note:

| Change Requestor / Originator |  |  |
| --- | --- | --- |
| Summary of Change | Change of Payment Schedule and Milestone Reporting as specified in the Annex. |  |
| Reason for Change | Change due to not being able to meet original timelines. |  |
| Revised Contract Price | Original Contract Value | £6,000,000 |
|  | Previous Contract Changes | £ 7,200,000 |
|  | Contract Change Note 001 | £ Nil |
|  | New Contract Value | £13,200,000 |
| Revised Payment Schedule | As listed in Annex A |  |
| Revised Specification | As listed in Annex B |  |
| Revised Contract Period | 1st March 2023 – 31st March 2026 |  |
| Change in Contract Manager(s) | N/A |  |
| Other Changes | N/A |  |

- Save as herein amended all other terms and conditions of the Original Contract shall remain in full force and effect.

Execution of the Contract Change Note is carried out in accordance with EU Directive 99/93

(Community framework for electronic signatures) and the Electronic Communications Act 2000. The revised Contract is formed on the date on which both Parties communicate acceptance of its terms on the Authority’s electronic contract management system (“Atamis”).

Reference: LIT 58403 	Version: 2.0 	Security classification: OFFICIAL 	Page 1 of 4

Uncontrolled when printed: 16:23

Contractor’s signature

Authority’s signature

Annex A – Payment Schedule

| Milestone | Amount of Grant Funding Payable | Expected date of invoice |
| --- | --- | --- |
| Year 1 |  |  |
| 1 |  | November 2022 |
| 2 |  | January 2023 |
| 3 |  | March 2023 |
| 4 |  | June 2023 |
| Year 2 |  |  |
| 1 |  | June 2023 |
| 2 |  | September 2023 |
| 3 |  | December 2023 |
| 4 |  | March 2024 |
| Year 3 |  |  |
| 1 |  | August 2024 – CCN03 Change |
| 2 |  | September 2024 |
| 3 |  | December 2024 |
| 4 |  | March 2025 |
| Year 4 |  |  |
| 1 |  | June 2025 |
| 2 |  | September 2025 |
| 3 |  | December 2025 |
| 4 |  | March 2026 |
| Total | £13,200,000 | No later than 31st March 2026 |

Annex B – Specification – Milestone Reporting

| Milestone | Report Due | Report Type |
| --- | --- | --- |
| Year 1 |  |  |
| 1 | End of Q2 (October 2022) | Quarterly formal progress report |
| 2 | End of Q3 (January 2023) | Quarterly formal progress report |
| 3 | End of Q4 (March 2023) | Annual formal progress report |
| Year 2 |  | Formal progress report |
| 1 | End of Q1 (June 2023) | Quarterly formal progress report |
| 2 | End of Q2 (September 2023) | Quarterly progress report |
| 3 | End of Q3 (December 2023) | Quarterly progress report |
| 4 | End of Q4 (March 2024) | Annual progress report |
| Year 3 |  |  |
| 1 | Q2 (August 2024) – CCN03 Change | Quarterly progress report |
| 2 | End of Q2 (September 2024) | Quarterly progress report |
| 3 | End of Q3 (December 2024) | Quarterly progress report |
| 4 | End of Q4 (March 2025) | Annual progress report |
| Year 4 |  |  |
| 1 | End of Q1 (June 2025) | Quarterly progress report |
| 2 | End of Q2 (September 2025) | Quarterly progress report |
| 3 | End of Q3 (December 2025) | Quarterly progress report |
| 4 | End of Q4 (March 2026) | Annual progress report |