## Programme Level Logframe
PROJECT TITLE | UNDP Climate Promise
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Countries advance net zero emission and climate resilient development, in line with the Paris Agreement and the 2030 Agenda, including by protecting, restoring and sustainably managing nature and ecosystems, while supporting people’s livelihoods | ICF KPI 15: Extent to which ICF intervention is likely to lead to Transformational Change | Planned | 0
|  | Achieved |  |  | 4 | 4 | 4 | 5
Source
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Countries have effectively strengthened inclusive and gender-responsive forests/land-use/nature-related governance and financing mechanisms to enable delivery and tracking towards the achievement of NDC targets across sectors (Scale and Speed) | Number of Countries with inclusive policies and measures (including legislation and regulations) developed and/or implemented to support NDC implementation, including those that are gender-responsive (GRF 1.1.1) (ICF TA KPI 3) | Planned | 0 | 0 | 5 - Cambodia, Cote d'Ivoire, Ecuador, Kenya, Liberia | 3 - Liberia, Ecuador, Indonesia |  | 8 - Cambodia, Cote d'Ivoire, Ecuador, Ecuador, Indonesia, Kenya, Liberia, Liberia
|  | Achieved |  | 0 | 5 - Cambodia, Cote d'Ivoire, Ecuador, Kenya, Liberia | 2 - Ecuador, Liberia | 1 - Indonesia | 8 - Cambodia, Cote d'Ivoire, Ecuador, Ecuador, Indonesia, Kenya, Liberia, Liberia
Source
Ecuador, Cote d'Ivoire, Liberia, Kenya, Indonesia, Cambodia
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.1 | Output Indicator 1.1.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Institutional capacities and whole-of government coordination mechanisms are strengthened to support effective, gender-responsive and inclusive NDC implementation processes (GRF 1.2) | Number of countries with horizontal and vertical coordination mechanisms established or strengthened to support whole-of government climate action, including those that are gender responsive (GRF 1.2.1) | Planned | 0 | 0 | 2 - Republic of Congo, Cote d'Ivoire | 1 - Cambodia |  | 3 - Cambodia, Republic of Congo, Cote d'Ivoire
|  | Achieved |  | 0 | 2 - Republic of Congo, Cote d'Ivoire |  | 1 - Cambodia | 3 - Cambodia, Republic of Congo, Cote d'Ivoire
Source
Republic of Congo, Cote d'Ivoire, Cambodia
| Output Indicator 1.1.2 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025)
| Number of countries, where institutional capacities for NDC implementation have been strengthened (GRF 1.2.2) | Planned | 0 | 0 | 1 - Kenya | 4 - Cambodia, Colombia, Ecuador, Cote d'Ivoire |  | 5 - Cambodia, Colombia, Ecuador, Cote d'Ivoire, Kenya
|  | Achieved |  | 0 | 1 - Kenya | 2 - Cambodia, Colombia | 1 - Ecuador | 4 - Cambodia, Colombia, Ecuador, Kenya
Source
Cambodia, Colombia, Ecuador, Cote d'Ivoire, Kenya
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.2 | Output Indicator 1.2.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Inclusive and gender responsive forests/land-use/nature-related financing strategies, plans or investment frameworks are developed to define and mobilize diverse sources of finance to support implementation of NDC actions and drive green recovery across key sectors(GRF 1.3) | Number of countries which have developed finance strategies/ plans for their climate agenda, including those linked to Integrated National Financing Framework, development plans and/or green recovery strategies, and those that are gender responsive (GRF 1.3.1) | Planned | 0 | 0 | 1 - Viet Nam | 2 - Liberia, Cote d'Ivoire |  | 3 - Viet Nam, Liberia, Cote d'Ivoire
|  | Achieved |  | 0 | 1 - Viet Nam | 1 - Liberia |  | 2 - Viet Nam, Liberia
Source
Viet Nam, Cote d'Ivoire, Liberia
| Output Indicator 1.2.2 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025)
| Number of countries that have developed or strengthened policy or measures that are conducive to the mobilization of private capital for NDC implementation (GRF 1.3.3)(formerly 1.3.2) | Planned | 0 | 0 | 1 - Ecuador |  |  | 1 - Ecuador
|  | Achieved |  | 0 | 1 - Ecuador |  |  | 1 - Ecuador
Source
Ecuador
| Output Indicator 1.2.3 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025)
| Number of countries that have established or strengthened financing mechanisms or instruments for climate finance mobilization (GRF 1.3.4)(formerly 1.3.3) | Planned | 0 | 0 | 1 - Cambodia | 2 - Viet Nam, Kenya |  | 3 - Cambodia, Viet Nam, Kenya
|  | Achieved |  | 0 | 1 - Cambodia | 2 - Viet Nam, Kenya |  | 3 - Cambodia, Viet Nam, Kenya
Source
Viet Nam, Cambodia, Kenya
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.3 | Output Indicator 1.3.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Data and transparency systems and processes for the Enhanced Transparency Framework established or strengthened to measure the achievement of NDC targets | Number of countries with strengthened or established MRV/M&E institutional capacities, processes or systems (for mitigation, adaptation or finance) to track NDC progress, including those that are gender responsive (GRF 1.4.1) | Planned | 0 | 0 | 2 - Liberia, Dominica | 5 - Cambodia, Viet Nam, Cote d'Ivoire, Republic of Congo, Indonesia |  | 7 - Dominica, Cambodia, Cote d'Ivoire, Indonesia, Liberia, Viet Nam, Republic of Congo
|  | Achieved |  | 0 | 2 - Liberia, Dominica | 4 - Cambodia, Cote d'Ivoire, Republic of Congo, Viet Nam | 1 - Indonesia | 7 - Dominica, Cambodia, Cote d'Ivoire, Indonesia, Liberia, Viet Nam, Republic of Congo
Source
Cambodia, Viet Nam, Liberia, Cote d'Ivoire, Dominica, Republic of Congo, Indonesia
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Countries have established long-term net-zero and climate resilient development pathways aligned with the goals of the Paris Agreement (Amplifying Ambition) | Number of countries with revised NDCs that are of higher quality, including alignment with LT/LEDS or NAP (a) aligned with criteria in the UNDP quality review checklist (GRF 2.1.1) | Planned | 0 | 0 | 1 - Viet Nam |  |  | 1 - Viet Nam
|  | Achieved |  | 0 | 1 - Viet Nam |  |  | 1 - Viet Nam
Source
Cambodia, Dominica, Viet Nam
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2.1 | Output Indicator 2.1.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Countries are enabled to enhance their NDC as part of the next revision cycle and global/regional stocktaking, aligned to long-term mitigation and adaptation pathways | Number of countries with revised NDCs of higher ambition (b) mitigation, adaptation and finance in line with the criteria in the UNDP quality review checklist (GRF 2.1.2) | Planned | 0 | 0 |  | 1 - Ecuador |  | 1 - Ecuador
|  | Achieved |  | 0 |  | 1 - Ecuador |  | 1 - Ecuador
Source
Colombia, Dominica, Ecuador
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2.2 | Output Indicator 2.2.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Forests/land-use/nature-related strategies, resources and political will for long-term net-zero, climate resilient pathways are established or strengthened, including those with just transition measures | Number of countries supported to develop or update long-term strategies or goals aligned with NDC targets, including considerations of just transition (GRF 2.2.1) | Planned | 0 | 0 | 1 - Dominica | 1 - Cambodia |  | 2 - Dominica, Cambodia
|  | Achieved |  | 0 | 1 - Dominica | 1 - Cambodia |  | 2 - Dominica, Cambodia
Source
Cambodia, Dominica
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Key actors within society are systematically engaged and empowered to contribute to accelerated NDC implementation and long-term net-zero and climate-resilient development pathways (Lasting Inclusivity) | Number of countries where women, girls, youth, indigenous people and/or vulnerable groups are represented in decision-making mechanisms and processes to support climate action. (GRF 3.1.1) | Planned | 0 | 0 | 2 - Colombia, Dominica | 3 - Cambodia, Cote d'Ivoire, Ecuador |  | 5 - Colombia, Dominica, Cambodia, Cote d'Ivoire, Ecuador
|  | Achieved |  | 0 | 2 - Colombia, Dominica |  | 2 - Cambodia, Ecuador | 4 - Colombia, Dominica, Cambodia, Ecuador
Source
Cambodia, Colombia, Cote d'Ivoire, Dominica, Ecuador
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3.1 | Output Indicator 3.1.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
National stakeholder engagement processes established or strengthened to empower key actors (e.g. indigenous people, women, youth, and vulnerable groups), in participating in and leading NDC implementation processes and long-term climate action | Number of countries where private sector is represented in decision-making mechanisms and processes to support climate action. (GRF 3.1.2) | Planned | 0 | 0 | 1 - Ecuador |  |  | 1 - Ecuador
|  | Achieved |  | 0 | 1 - Ecuador |  |  | 1 - Ecuador
Source
Ecuador
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3.2 | Output Indicator 3.2.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Innovative engagement mechanisms and initiatives are leveraged, developed and/or scaled up to promote social mobilisation for climate action | Number of countries where engagement mechanisms and initiatives have been leveraged, developed and/or scaled up to promote social mobilisation for climate action (GRF 3.2.1) | Planned | 0 | 0 | 1 - Ecuador | 4 - Cambodia, Colombia, Indonesia, Kenya |  | 5 - Ecuador, Cambodia, Colombia, Indonesia, Kenya
|  | Achieved |  | 0 | 1 - Ecuador | 2 - Cambodia, Kenya | 2 - Colombia, Indonesia | 5 - Ecuador, Cambodia, Colombia, Indonesia, Kenya
Source
Cambodia, Colombia, Dominica, Ecuador, Indonesia, Kenya, Republic of Congo
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3.3 | Output Indicator 3.3.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
National/sub-national knowledge sharing and awareness-raising mechanisms established or strengthened to build capacity of broader society and inform NDC implementation and long-term pathways | Number of countries where knowledge sharing or awareness raising to build the capacity of broader society on NDC implementation or long-term pathways has been undertaken or strengthened, including on gender responsive approaches (GRF 3.3.1) | Planned | 0 | 0 | 4 - Colombia, Cote d'Ivoire, Ecuador, Liberia | 1 - Republic of Congo |  | 5 - Colombia, Cote d'Ivoire, Ecuador, Liberia, Republic of Congo
|  | Achieved |  | 0 | 4 - Colombia, Cote d'Ivoire, Ecuador, Liberia |  | 1 - Republic of Congo | 5 - Colombia, Cote d'Ivoire, Ecuador, Liberia, Republic of Congo
Source
Colombia, Cote d'Ivoire, Ecuador, Liberia, Republic of Congo
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 4 | Outcome Indicator 4.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Regional and global awareness, advocacy, and partnerships are strengthened to contribute to enhanced NDC and LTS ambition and delivery capacity | Number of regional or global high-profile events or meetings to which the Programme contributed through experiences and key messages, including key milestones of the UNFCCC processes (GRF 4.3.1) (formerly 4.2.2) | Planned | 0 | 0 | 1 | 1 | 0 | 2
|  | Achieved |  | 0 | 1 | 5 | 0 | 6
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4.1 | Output Indicator 4.1.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Enhanced forests/land-use/nature-related knowledge exchange and partnerships through global and regional forums/mechanisms | Number of peer-to-peer exchanges carried out at regional and global level (GRF 4.1.1) | Planned | 0 | 0 | 3 | 4 | 0 | 7
|  | Achieved |  | 0 | 5 | 1 | 0 | 6
Source
| Output Indicator 4.1.2 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025)
| Number of knowledge products generated and disseminated (GRF 4.1.2) | Planned | 0 | 0 | 8 | 2 | 0 | 10
|  | Achieved |  | 0 | 9 | 3 | 0 | 12
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4.2 | Output Indicator 4.2.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Engagement in UNFCCC processes is enhanced, and international partnerships and advocacy are strengthened to promote ambition and full implementation of the Paris Agreement (GRF 4.3) | Number of strategic partnerships developed and/or strengthened to advance activities under the Programme, including with UN sister agencies and other international partners, public and private (GRF 4.3.2) | Planned | 0 | 0 | 1 | 1 | 0 | 2
|  | Achieved |  | 0 | 3 | 4 | 0 | 7
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 5 | Outcome Indicator 5.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Nature and ecosystems are protected, restored and sustainably managed, and support people’s livelihoods | ICF KPI 17: Area under Sustainable Management Practices | Planned | 0 | 0 |  | 0 | 0 | 0
|  | Achieved |  | 0 |  | 13,126.86 ha | 0 | 13,126.86 ha
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5.1 | Output Indicator 5.1.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Countries are supported to introduce nature-related policies | Number of countries supported by International Climate Finance technical assistance (ICF TA KPI 1) | Planned | 0 | 0 | 10 | 10 | 10 | 10 - Cambodia, Colombia, Cote d’Ivoire, Dominica, Ecuador, Indonesia, Kenya, Liberia, Republic of Congo, Vietnam
|  | Achieved |  | 0 | 9 | 9 | 10 | 10 - Cambodia, Colombia, Cote d’Ivoire, Dominica, Ecuador, Indonesia, Kenya, Liberia, Republic of Congo, Vietnam
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5.2 | Output Indicator 5.2.1 |  | Baseline | Milestone 1 - 2022 | Milestone 2 - 2023 | Milestone 3 - 2024 | Milestone 4 - 2025 | End of Programme Target (2025) | Assumptions
Enhanced rights and sustainable livelihoods for people | Number of people with improved land tenure or access rights (ICF DI KPI 8) | Planned | 0 | 0 |  | 0 | 0 | 0
|  | Achieved |  | 0 |  | 3083 | 1370 | 4453
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)