## Programme Logframe
ORGANISATION NAME | Defra
PROJECT NAME | Ocean Country Partnership programme 2023
IMPACT | Impact Indicator 1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
Partner countries better address the challenges to their marine environments and biodiversity, enhance marine dependent livelihoods, and the wellbeing of those that depend on them, sustainably, equitably and inclusively.​ | BPF 6. Area of marine ecosystems protected, enhanced or under sustainable management due to BPF finance | Planned |  |  |  |  | ALBs to provide | ALBs to provide
Achieved
Source
Method: BPF KPI 6 methodology provided by Defra
| Impact Indicator 2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Proportion of surveyed respondents in communities where OCPP has carried out direct activities, who report an improvement in marine dependent livelihoods and wellbeing (in case study countries) | Planned
Achieved
Source
Evaluation survey
| Impact Indicator 3 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| I3: Extent to which the intervention is likely to lead to transformational change | Planned
Achieved
Source
Evaluation 2026
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumptions
Partner country stakeholders take action to effectively and sustainably manage and protect their marine environments | Number of partner countries where there is evidence of strengthened preparedness to respond to emergencies | Planned | [5 empty] | 10 countries | Inclusive and empowered governance of the marine environment translates into benefits for coastal communities Policy and management changes leads to livelihood and environmental (e.g., biodiversity resilience-building) benefits for direct and wider beneficiaries Effective integration with and additionality to other BPF and other donor programmes Co-benefits with wider BPF outcomes on critical marine habitats, small-scale fisheries and sustainable aquaculture that is coherent with the Convention on Biological Diversity and other international agreements. Significant crises during the programme create a gap or shift that distract from OCPP’s prioritisation within partner countries’
Achieved
Source
EPR Rubric for Sri lanka, Maldives, Senegal, Ghana, Bangladesh, India, Mozambique, Sierra Leone, Vanuatu and Solomon islands
| Outcome Indicator 2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of improved policies, regulations and guidelines or recommended practices implemented | Planned | [5 empty] | 10
Achieved
Source
Outcome assessment tool Stories of Change tool, official records, meeting minutes, budget (to be captured via outcome tracker)
| Outcome Indicator 3 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of countries where enforcement or monitoring activities are implemented and resourced. | Planned | [5 empty] | 11
Achieved
Source
Number of monitoring datasets , reports regarding enforcement, monitoring and ensuring continuation of training. Resourcing more complicated- use number of successful Sustainable Finance uptake
| Outcome Indicator 4 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| (BPF 3): Increased effective and equitable representation and participation of coastal resources stakeholders in management | Planned | [5 empty] | 10 countries
Achieved
Source
Key informant interviews / focus group discussions in case study countries; to be captured by NIRAS MEL team in evaluation
INTERMEDIATE OUTCOME | Intermediate outcome Indicator 1.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumption
Improved policies or regulations and practices established with enhanced awareness, capabilities and inclusive governance in place to implement and enforce them | Number of cases where there is evidence of uptake of policy recommendations or demonstration of practical improvements and /or uptake of sustainable practices by country stakeholders | Planned | [5 empty] | 30 | Communities, including women and marginalised groups, have the adequate social and economic incentives and motivations to build ownership and engage in action to improve stewardship of the marine environment and comply with improved management of the marine environment Public-private funding and innovations in financing are available to support implementation of improved policy, regulatory framework, and improvement in the sustainable ocean economies in partner countries Interventions are targeting marginalised groups, including the poorest, and women and girls Assumptions are formulated adequately to ensure that they can help drive adaptive management principles that promote the systematic capture of lessons and related adjustments in the pathway toward achieving the OCPP’s objectives.
Achieved
Source
Stories of Change tool, Policy drafts, meeting minutes, reports,
| Internediate outcome Indicator 1.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Extent to which partner countries have demonstrated change in 5 key dimensions of the policy process | Planned |  |  |  |  | N/A
Achieved
Source
Policy process assessment tool
| Intermediate outcome Indicator 1.3 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of projects / planning and/or governance processes with increased inclusion of local people and their knowledge in decision making | Planned
Achieved
|  | Source | [6 empty] | RISK RATING
Policy process assessment tool
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumptions
Partner country stakeholders have strengthened capacity and capability in marine science, management and governance | Participants report increased knowledge and capacity following training and /or mentoring | Planned | 0 |  |  |  | ALBs: 80% of all participants from 1.3 GOAP: 80% of 1.3 | GOAP: 80% of 1.3 | Capacity, capability and evidence generated through the programme effectively translate into policy and management change Integrated coordination supports learning, adaptation and minimises duplication of work between Delivery Partners
Achieved
Source
Training records and pre-, post-training surveys
| Output Indicator 1.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Target organisations / institutions in partner countries have increased access to functioning marine scientific equipment and staff trained in its use | Planned | 0 |  |  |  | ALBs: 15 organisations GOAP: 0 | GOAP: 0
Achieved
Source
Key informant interviews at organisation, training records, direct observation
| Output Indicator 1.3 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of individuals receiving TA support | Planned | 0 |  |  |  | ALBs: 1,600 individuals GOAP: 220 | GOAP: 120
Achieved
|  | Source | [6 empty] | RISK RATING
Method: ICF KPI TA1, 3, 4. Programme records, training assessments
| Output Indicator 1.4 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of organisations receiving TA support | Planned | 0 |  |  |  | ALBs: 120 GOAP: 35 | GOAP: 20
Achieved
|  | Source | [6 empty] | RISK RATING
Method: ICF KPI TA1, 3, 4. Programme records, training assessments
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumptions
Policy and regulatory recommendations proposed and guidelines developed. | Number of outputs (policy briefs, roadmaps, recommendations, guidelines) developed that contribute to sustainable management | Planned | 0 |  |  |  | ALBS: 50 GOAP: 20 | GOAP: 10 | Governments and stakeholders willing to engage OCPP and are committed to protecting the marine environment Programme delivery adheres to Do No Harm principles, Safeguarding Principles and signed Frameworks
Achieved
Source
Programme records, policy briefs, recommendations, roadmaps, guidelines
| Output Indicator 2.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| % of outputs developed that included inclusive consultation processes | Planned | 0 |  |  |  | ALBs: 60% GOAP: 60% | GOAP: 60%
Achieved
Source
Delivery partner records, consultation attendance records
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumptions
Enhanced education, awareness and exchange of scientific, technical knowledge and data in relevant sustainable marine management topics | Number of datasets or monitoring systems developed or improved; ocean accounts compiled or educational resources produced | Planned | 0 |  |  |  | ALBS: 105 GOAP: 10 | GOAP: 3 | Majority of required datasets are made available for composition of ocean accounts
Achieved
Source
Delivery partner records
| Output Indicator 3.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of scholars and % who achieve a qualification (Masters, PhD) in relevant topics | Planned | 0 |  |  |  | ALBS: 20
Achieved
|  | Source | [6 empty] | RISK RATING
Delivery partner records; institution registration documents
| Output Indicator 3.4 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Scientific papers, reports, strategies, tools and/or databases developed or published which are freely available and accessible | Planned | 0 |  |  |  | ALBS: 4 GOAP:10 | GOAP: 5
Achieved
|  | Source | [6 empty] | RISK RATING
Deivery partner publication records, papers, reports, tools, databases
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumption
Active ocean-science related knowledge networks and partnerships (either UK – partner country or in-country coalitions) developed or supported by OCPP activities | Number of MoUs or similar agreement between OCPP and partner country stakeholders signed | Planned | 0 |  |  |  | ALBs:6 GOAP: 5 | GOAP: 3
Achieved
Source
Deliverty partner records, MOUs, similar country-level agreements
| Output Indicator 4.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of public- private sector or business clusters mobilised | Planned | 0 |  |  |  | N/A for ALBs GOAP: 0 | GOAP: 0
Achieved
Source
Delivery partner records; partnership agreements; business cluster ToRs
| Output Indicator 4.3 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of in-country coalitions, governance structures, networks or taskforces established, engaged or strengthened | Planned | 0 |  |  |  | ALBs:10 GOAP: 8 | GOAP: 0
Achieved
|  | Source | [6 empty] | RISK RATING
Delivery partner records; network or task force ToRs / purpose documents; meeting minutes or attendance records for events
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumption
Innovative initiatives piloted that support equitable market access and value chain improvement | Number of pilots designed and tested by stakeholder networks | Planned | 0 |  |  |  | N/A for ALBs
Achieved
Source
Delivery partner records; pilot initiative plans; progress reports
| Output Indicator 5.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of initiatives planned to take to scale that support value chain improvement and equitable market access​ | Planned | 0 |  |  |  | N/A for ALBs
Achieved
Source
Delivery partner records, initiative scaling plans
OUTPUT 6 | Output Indicator 6.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumption
OCPP intervention design adequately considers gender, equity and social inclusion and safeguarding | Number of scoping missions/reports that include detailed stakeholder mapping, GESI analysis and safeguarding risk assessment | Planned | 0 |  |  |  | AL Bs: 12 (at least 1 per country). TO BE REVIEWED
Achieved
Source
Scoping mission reports
| Output Indicator 6.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of intervention plans that reflect GESI recommendations and safeguarding measures | Planned | 0 |  |  |  | 12 (at least 1 per country) TO BE REVIEWED
Achieved
Source
Intervention plans
Note on I25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This could take a long time to see/measure –note that implemented would require evidence of policy approved, resource allocation, action plan etc). It could be safer to aim for 3-4 policies by the end of 2026 but let’s review this figure in 6 months.