## Programme Logframe
ORGANISATION NAME | Defra
PROJECT NAME | Ocean Country Partnership programme 2023
IMPACT | Impact Indicator 1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
Partner countries better address the challenges to their marine environments and biodiversity, enhance marine dependent livelihoods, and the wellbeing of those that depend on them, sustainably, equitably and inclusively.​ | BPF 6. Area of marine ecosystems protected, enhanced or under sustainable management due to BPF finance | Planned | [5 empty] | TBC if GOAP and ALBs can report this
|  | Achieved | [5 empty] | TBC if GOAP and ALBs can report this
Source
Method: BPF KPI 6 methodology provided by Defra
| Impact Indicator 2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| [Placeholder: Proportion of surveyed respondents in communities where OCPP has carried out direct activities, who report an improvement in marine dependent livelihoods and wellbeing (in case study countries)] | Planned | [5 empty] | N/A for evaluation
Achieved
Source
Evaluation survey
| Impact Indicator 3 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| I3: Extent to which the intervention is likely to lead to transformational change | Planned | [5 empty] | N/A for evaluation
Achieved
Source
Evaluation 2026
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumptions
Partner country stakeholders take action to effectively and sustainably manage and protect their marine environments | Number of partner countries where there is evidence of strengthened preparedness to respond to emergencies | Planned | [5 empty] | ALBs: 7 countries GOAP: n/a FOA: n/a | Inclusive and empowered governance of the marine environment translates into benefits for coastal communities Policy and management changes leads to livelihood and environmental (e.g., biodiversity resilience-building) benefits for direct and wider beneficiaries Effective integration with and additionality to other BPF and other donor programmes Co-benefits with wider BPF outcomes on critical marine habitats, small-scale fisheries and sustainable aquaculture that is coherent with the Convention on Biological Diversity and other international agreements. Significant crises during the programme create a gap or shift that distract from OCPP’s prioritisation within partner countries’
|  | Achieved |  |  |  | 2 | 6
|  | This is a cumulative indicator. | Source
EPR Rubric for Sri lanka, Maldives, Senegal, Ghana, Bangladesh, India, Mozambique, Sierra Leone, Vanuatu and Solomon islands
| Outcome Indicator 2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of improved policies, regulations and guidelines or recommended practices implemented | Planned | [5 empty] | 10 (ALBs) GOAP:10 FOA: TBC
|  | Achieved |  |  |  | 2 (ALBs) | 10 ALBs: 5 GOAP: 5
|  | This is a cumulative indicator. | Source
Outcome assessment tool Stories of Change tool, official records, meeting minutes, budget (to be captured via outcome tracker)
| Outcome Indicator 3 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of cases where enforcement or monitoring activities are implemented and resourced. | Planned | [5 empty] | ALBs: 7 cases GOAP: 1 case FOA: N/A
|  | Achieved |  |  |  | 1 (ALBs) | 4 ALBs: 3 GOAP: 1
|  | This is a cumulative indicator. | Source
Number of monitoring datasets , reports regarding enforcement, monitoring and ensuring continuation of training. Resourcing more complicated- use number of successful Sustainable Finance uptake
| Outcome Indicator 4 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| (BPF KPI 3): Increased effective and equitable representation and participation of coastal resources stakeholders in management | Planned | [5 empty] | Gender Sensitive
|  | Achieved |  |  |  | not reported for Y3 | Partially Gender Sensitive
Source
Key informant interviews / focus group discussions in case study countries; to be captured by NIRAS MEL team in evaluation
INTERMEDIATE OUTCOME | Intermediate outcome Indicator 1.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumption
Improved policies or regulations and practices established with enhanced awareness, capabilities and inclusive governance in place to implement and enforce them | Number of cases where there is evidence of uptake of policy recommendations or demonstration of practical improvements and /or uptake of sustainable practices by country stakeholders | Planned |  |  |  |  | n/a: not targeted | n/a: not targeted for ALBs and GOAP FOA: 1 | Communities, including women and marginalised groups, have the adequate social and economic incentives and motivations to build ownership and engage in action to improve stewardship of the marine environment and comply with improved management of the marine environment Public-private funding and innovations in financing are available to support implementation of improved policy, regulatory framework, and improvement in the sustainable ocean economies in partner countries Interventions are targeting marginalised groups, including the poorest, and women and girls Assumptions are formulated adequately to ensure that they can help drive adaptive management principles that promote the systematic capture of lessons and related adjustments in the pathway toward achieving the OCPP’s objectives.
|  | Achieved |  |  |  | 7 | 18
Source
Outcome tracker tool, evidenced by meeting minutes, emails.
| Internediate outcome Indicator 1.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Extent to which partner countries have demonstrated change in 5 key dimensions of the policy process | Planned |  |  |  |  | n/a: not targeted | n/a: not targeted
|  | Achieved |  |  |  | 9 | 9
Source
Outcome tracker tool, evidenced by meeting minutes, emails.
|  |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumptions
Partner country stakeholders have strengthened capacity and capability in marine science, management and governance | Participants report increased knowledge and capacity following training and /or mentoring | Planned | 0 |  |  | Flat milestone: 80% | ALBs: 80% GOAP: 80% | ALBs: 80% GOAP: 80% | Capacity, capability and evidence generated through the programme effectively translate into policy and management change Integrated coordination supports learning, adaptation and minimises duplication of work between Delivery Partners
|  | Achieved |  |  |  | Overall: 95.5% AlLB progress: 95.5% GOAP progress: 100% | Total: 87%, A ALB: 88% GOAP: 87% FOA: N/A
Source
Training records and pre-, post-training surveys
| Output Indicator 1.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Cumulative Target July 2026
| Target organisations / institutions in partner countries have increased access to functioning marine scientific equipment and staff trained in its use | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with discrete reporting) 70% (A): 10.5 60% (B): 9 <60% (C) | ALBs: 8 organisations GOAP: 0 | ALBs: 22 GOAP: N/A
|  | Achieved |  |  |  | Overall: 2 ALB progress: 2 FOA and GOAP: N/A | Total: 17 ALBs: 17 GOAP: N/A FOA: N/A
|  | This is a cumulative indicator. | Source
Key informant interviews at organisation, training records, direct observation
| Output Indicator 1.3 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Cumulative Target July 2026
| Number of individuals receiving TA support | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with year-on-year overlap) (A): 1092 50% (B): 910 <50% (C) | Total: 1,938 ALB: 1,600 GOAP: 320 FOA: 18 (23/24) | ALBs: 3,000 GOAP: 1,611
|  | Achieved |  |  |  | Overall: 1276 ALB progress: 1022 GOAP progress: 244 FOA progress: 18 | Total: 4,161 ALBs: 2,737 GOAP: 1,447 FOA: 18 (23/24)
|  | This is a cumulative indicator. | Source | [5 empty] | RISK RATING
Method: ICF KPI TA1, 3, 4. Programme records, training assessments
| Output Indicator 1.4 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Cumulative Target July 2026
| Number of organisations receiving TA support | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with year-on-year overlap)60% (A): 93 50% (B): 77.5 <50% (C) | Total: 402 ALB: 366 GOAP: 50 FOA: 52 (23/24) | ALB: 700 GOAP: 445 FOA: 102
|  | Achieved |  |  |  | Overall: 370 ALB progress: 296 GOAP progress: 46 FOA progress: 52 | Total: 1,057 ALB: 680 GOAP: 420 FOA: 52 (23/24)
|  | This is a cumulative indicator. | Source | [5 empty] | RISK RATING
Method: ICF KPI TA1, 3, 4. Programme records, training assessments
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Cumulative Target July 2026 | Assumptions
Policy and regulatory recommendations proposed and guidelines developed. | Number of outputs (policy briefs, roadmaps, recommendations, guidelines) developed that contribute to sustainable management | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with discrete reporting) 70% (A): 49 60% (B): 42 <60% (C) | Total: 81 ALB: 50 GOAP: 28 FOA: 3 | ALBs: 90 GOAP: 67 FOA: 7 | Governments and stakeholders willing to engage OCPP and are committed to protecting the marine environment Programme delivery adheres to Do No Harm principles, Safeguarding Principles and signed Frameworks
|  | Achieved |  |  |  | "Overall: 45 ALB progress: 24 GOAP progress: 18 FOA progress: 3" | Total: 110, A+ ALB: 60 GOAP : 47 FOA: 3 (23/24)
|  | This is a cumulative indicator. | Source
Programme records, policy briefs, recommendations, roadmaps, guidelines
| Output Indicator 2.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| % of outputs developed that included inclusive consultation processes | Planned | 0 |  |  | Flat milestone: 60% | ALBs: 60% GOAP: 60% | ALBs: 60% GOAP: 50% FOA: 80%
|  | Achieved |  |  |  | "Overall: 88% ALB progress: 83% GOAP progress: 100% FOA progress: 100%" | Total: 73% ALB progress: 89% GOAP progress: 53%
|  | This is a flat milestone. | Source
Delivery partner records, consultation attendance records
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | CumulativeTarget July 2026 | Assumptions
Enhanced education, awareness and exchange of scientific, technical knowledge and data in relevant sustainable marine management topics | Number of datasets or monitoring systems developed or improved; ocean accounts compiled or educational resources produced | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with discrete reporting) 70% (A): 80.5 60% (B): 69 <60% (C) | Total: 105 ALB: 80 GOAP: 25 FOA: N/A | ALBs: 90 | Majority of required datasets are made available for composition of ocean accounts
|  | Achieved |  |  |  | Overall: 60 ALB progress: 37 GOAP progress: 23 | Total: 102 ALB: 71 GOAP: 31 FOA: N/A
|  | This is a cumulative indicator. | Source
Delivery partner records
| Output Indicator 3.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of scholars or fellows who enrolled and % who achieved a qualification (Masters, PhD) or undertook a fellowship in relevant topics | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with year-on-year overlap) 60% (A): 93 50% (B): 77.5 <50% (C) | Total: 114 ALB: 94 GOAP: 20 FOA: N/A | ALBs: 102 (80% of the total number of scholars) GOAP: 24
|  | Achieved |  |  |  | "Overall: 94 ALB progress: 94 GOAP progress: Data not yet collected due to the late addition of GOAP into reporting requirements for this indicator Gender disaggregation: 52% (49) of scholars enrolled this year were female 48% (45) of scholars enrolled this year were male" | Total: 126 ALB: 102 GOAP : 24 FOA: N/A Gender ALBs: 52% (53) of scholars are female and 48% (49) male. GOAP: 67% (16) of fellows were male and 33% (8) female. Age GOAP: 92% (22) of fellows are between te ages of 25-64 years and 8% (2) fellows are between 15 - 24 years. Geography GOAP: 42% (10) of fellows reported originating from an urban location and 17% (4) from a rural location. It was not feasible to collect this infofrmation from 42% (10) of fellows. It was not feasible for delivry partners to report against disability disaggregations.
|  | This is a cumulative indicator. | Source | [5 empty] | RISK RATING
Delivery partner records; institution registration documents
| Output Indicator 3.3 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Cumalative Target July 2026
| Scientific papers, reports, strategies, tools and/or databases developed or published which are freely available and accessible | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with discrete reporting) 70% (A): 21 60% (B): 18 <60% (C) | Total: 54 ALB: 15 GOAP: 28 FOA: 11 | ALBs: 70 GOAP: 66
|  | Achieved |  |  |  | Overall: 43 ALB progress: 8 GOAP progress: 24 FOA progress: 11 | Total: 105 ALB: 38 GOAP: 56 FOA: 11 (23/24)
|  | This is a cumulative indicator. | Source | [5 empty] | RISK RATING
Deivery partner publication records, papers, reports, tools, databases
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Cumulative Target July 2026 | Assumption
Active ocean-science related knowledge networks and partnerships (either UK – partner country or in-country coalitions) developed or supported by OCPP activities | Number of MoUs or similar agreement between OCPP and partner country stakeholders signed | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with discrete reporting) 70% (A): 7.7 60% (B): 6.6 <60% (C) | Total: 21 ALB: 6 GOAP: 14 FOA: 1 | ALBs: 8 GOAP: 15
|  | Achieved |  |  |  | Overall: 14 ALB progress: 4 GOAP progress: 9 FOA progress: 1 | Total: 21 ALB: 8 GOAP: 12 FOA: 1 (23/24)
|  | This is a cumulative indicator. | Source
Deliverty partner records, MOUs, similar country-level agreements
| Output Indicator 4.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Cumulative Target July 2026
| Number of public- private sector or business clusters mobilised | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with discrete reporting) No milestone | Total: 12 ALB: 10 GOAP: N/A FOA: N/A | ALBs: 9 GOAP: N/A FOA: 3
|  | Achieved |  |  |  | Overall: 8 ALB progress: 6 GOAP progress: NA FOA progress: 2 | Total: 10 ALB: 8 GOAP: N/A FOA: 2 (23/24)
|  | This is a cumulative indicator. | Source
Delivery partner records; partnership agreements; business cluster ToRs
| Output Indicator 4.3 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Cumulative Target July 2026
| Number of coalitions, governance structures, networks or taskforces established, engaged or strengthened | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with year-on-year overlap) 60% (A): 10.8 50% (B): 9 <50% (C) | Total: 41 ALB: 20 GOAP: 15 FOA: N/A | ALBs: 29 GOAP:40 FOA: 7
|  | Achieved |  |  |  | Overall: 28 ALB progress: 9 GOAP progress: 13 FOA progress: 6 | Total: 68 ALB: 22 GOAP: 40 FOA: 6 (23/24)
|  | This is a cumulative indicator. | Source | [5 empty] | RISK RATING
Delivery partner records; network or task force ToRs / purpose documents; meeting minutes or attendance records for events
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026 | Assumption
Innovative initiatives piloted that support equitable market access and value chain improvement | Number of pilots designed and tested by stakeholder networks | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with year-on-year overlap) No milestone" | N/A for ALBs and GOAP | N/A for ALBs and GOAP FOA: 4
|  | Achieved |  |  |  | Overall: 3 ALB progress: N/A GOAP progress: N/A FOA progress: 3 | ALB progress: N/A (23/24) GOAP progress: N/A (23/24) FOA progress: 3
|  | This is a cumulative indicator. | Source
Delivery partner records; pilot initiative plans; progress reports
| Output Indicator 5.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Target July 2026
| Number of initiatives planned to take to scale that support value chain improvement and equitable market access​ | Planned | 0 |  |  | 23/24 thresholds (Cumulative milestones with year-on-year overlap) No milestone | N/A for ALBs and GOAP | N/A for ALBs and GOAP and FOA
|  | Achieved |  |  |  | Overall: 3 ALB progress: NA GOAP progress: NA FOA progress: 3 | Overall: 3 (23/24) ALB progress: N/A (23/24) GOAP progress: N/A (23/24) FOA progress: 3
|  | This is a cumulative indicator. | Source
Delivery partner records, initiative scaling plans
OUTPUT 6 | Output Indicator 6.1 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Cumulative Target July 2026 | Assumption
OCPP intervention design adequately considers gender, equity and social inclusion and safeguarding | Number of GESI analyses(at a national, thematic or intervention level) completed | Planned | 0 |  |  | "23/24 thresholds (Cumulative milestones with discrete reporting) 70% (A): 8.4 60% (B): 7.2 <60% (C) " | Total: 9 | ALBs: 9 GOAP: 13 FOA: 2
|  | Achieved |  |  |  | Overall: 1 ALB progress: 0 GOAP progress: NA FOA progress: 1 | Total: 9 ALB: 8 FOA: 1 (23/24)
|  | This is a cumulative indicator. | Source
GESI analysis reports
| Output Indicator 6.2 |  | Baseline | Milestone July 2022 | Milestone July 2023 | Milestone July 2024 | Milestone July 2025 | Cumulative Target July 2026
| Number of cases which demonstrate integration of GESI analysis recommendations into delivery | Planned | 0 |  |  | "23/24 thresholds (Cumulative milestones with discrete reporting) 70% (A): 8.4 60% (B): 7.2 <60% (C) " | Total: 9 ALB: 8 GOAP: 0 FOA: N/A | ALBs: 8 cases GOAP: 7 cases FOA: 1 case
|  | Achieved |  |  |  | Overall: 1 ALB progress: 0 GOAP progress: NA FOA progress: 1 | Total: 9, A ALB: 6 GOAP: 5 FOA: 1 (23/24)
|  | This is a cumulative indicator. | Source
GESI Analysis Tracker

## GESI disaggregations
OP1.3 # of individuals receiving TA support - cumulative disaggregations
Disaggregation by gender
Delivery Partner | ALB | FOA | GOAP | Total | Disaggregation by Geography |  |  |  |  | Disaggregation by Disability |  |  |  |  | Disaggregation by Age
Gender | Individuals | Individuals | Individuals | Individuals | Row Labels | ALB | FOA | GOAP | Grand Total | Row Labels | ALB | FOA | GOAP | Grand Total | Row Labels | ALB | FOA | GOAP | Grand Total
| 39 |  | 111 | 150 | Left blank | 1178 | 18 | 309 | 1496 | Left blank | 1098 | 18 | 309 | 1416 |  | 1215 | 18 | 459 | 1681
Female | 851 | 13 | 610 | 1454 | Not Feasable | 7 |  |  | 7 | Disabled | 4 |  |  | 4 | Adult (25-64) | 1068 |  |  | 1068
Male | 1471 | 5 | 515 | 1978 | Not feasible | 911 |  | 1127 | 2023 | Not disabled | 1001 |  |  | 1001 | Child (0-14) | 4 |  |  | 4
Not feasible | 249 |  | 168 | 417 | Rural | 347 |  |  | 347 | Not feasible | 814 |  | 1127 | 1925 | Elder (65+) | 7 |  |  | 7
Not reported | 182 |  | 32 | 213 | Urban | 447 |  |  | 447 | Grand Total | 2721 | 18 | 1421 | 4118 | Not feasible | 379 |  | 985 | 1359
Total | 2721 | 18 | 1421 | 4118 | Grand Total | 2721 | 18 | 1421 | 4118 | [5 empty] | Youth (15-24) | 196 |  |  | 196
[15 empty] | Grand Total | 2721 | 18 | 1421 | 4118
OP3.2 ACU scholars
Column1 | Female | Male | Totals
Year 3 | 49 | 45 | 94
Year 4 | 4 | 4 | 8
Total | 53 | 49 | 102
ALBs: 52% (53) of scholars are female and 48% (49) male.
It was not feasible for delivery partners to report against age, geographic location, or disability.
OP3.2 GOAP Fellows/Scholars
Female | Male | Total
8 | 16 | 24
GOAP: 67% (16) of fellows were male and 33% (8) female.
Age
GOAP: 92% (22) of fellows are between te ages of 25-64 years and 8% (2) fellows are between 15 - 24 years.
Geography
GOAP: 42% (10) of fellows reported originating from an urban location and 17% (4) from a rural location. It was not feasible to collect this infofrmation from 42% (10) of fellows.
It was not feasible for delivery partners to report against disability disaggregations.